## Cover
EBRORA
ebrora.com
Concrete Cube Test Results Log
Track and verify concrete cube compressive strength test results against specified design strengths with automatic pass/fail assessment.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Cube Test Log' sheet — this is your main working area.
2. The top panel (rows 3–6) shows a live compliance summary — total samples, pass/fail counts, average 28-day strength, and overall pass rate. These update automatically.
3. Enter each cube test result starting from row 10 downward. Fill in Sample Ref, Date Cast, Pour Location, Mix Grade, and Specified Strength.
4. When 7-day test results come back from the lab, enter the test date and result. The template flags results below 65% of specified strength in amber.
5. When 28-day results are received, enter the test date and result. The Pass/Fail and Strength Ratio columns calculate automatically.
6. Use the [+] button above column N to expand optional fields (Slump, Air Temp, Curing Method, Lab Ref) if needed.
7. Filter by Pass/Fail status or Mix Grade using the header dropdowns to isolate problem batches quickly.
8. Set the print area as needed — the default covers 50 rows of data on A4 landscape.
Colour Key
| Light teal cells | Editable — enter your data here
| Dark navy headers | Do not edit — column headers and labels
| Green fill | PASS — 28-day result meets or exceeds specified strength
| Red fill | FAIL — 28-day result below specified strength
| Amber fill | Warning — 7-day result below 65% of specified strength
Tips
• Cast at least 3 cubes per 50m³ of concrete (or per pour) as a minimum — check your spec for exact requirements.
• Store cubes in a curing tank at 20°C ± 2°C as per BS EN 12390-2 for standard cured specimens.
• If a 28-day result fails, investigate immediately — consider additional cores or non-destructive testing before condemning the element.

## Cube Test Log
CONCRETE CUBE TEST RESULTS LOG — COMPLIANCE SUMMARY
Total Samples |  | 28-Day Tests Done |  | Passes |  | Failures |  | Pass Rate |  | Avg 28-Day Strength
5 |  | 4 |  | 3 |  | 1 |  | 75% |  | 41.4 | N/mm²
● ACTION REQUIRED
▸ Optional Fields — Click [+] to expand
Sample Ref | Date Cast | Pour Location / Element | Mix Grade | Specified Strength (N/mm²) | 7-Day Test Date | 7-Day Result (N/mm²) | 7-Day % of Spec | 28-Day Test Date | 28-Day Result (N/mm²) | Strength Ratio | Pass / Fail | Tested By | Slump (mm) | Air Temp (°C) | Curing Method | Lab Reference
CC-001 | 2026-02-10 | Pad Foundation PF-01 | C30/37 | 37 | 2026-02-17 | 26.5 | 71.62% | 2026-03-10 | 39.2 | 1.0595 | PASS | ABC Testing Ltd | 75 | 8 | Standard (Water Tank) | LAB-4421
CC-002 | 2026-02-12 | Ground Floor Slab Bay 1 | C28/35 | 35 | 2026-02-19 | 24.8 | 70.86% | 2026-03-12 | 36.1 | 1.0314 | PASS | ABC Testing Ltd | 80 | 6 | Standard (Water Tank) | LAB-4435
CC-003 | 2026-02-15 | Column C4 Base | C40/50 | 50 | 2026-02-22 | 30.1 | 60.2% | 2026-03-15 | 47.8 | 0.956 | FAIL | XYZ Labs | 65 | 7 | Standard (Water Tank) | LAB-4450
CC-004 | 2026-02-18 | Retaining Wall Section 2 | C32/40 | 40 | 2026-02-25 | 28.9 | 72.25% | 2026-03-18 | 42.5 | 1.0625 | PASS | ABC Testing Ltd | 70 | 5 | Standard (Water Tank) | LAB-4468
CC-005 | 2026-02-20 | Pile Cap PC-03 | C35/45 | 45 | 2026-02-27 | 22.1 | 49.11% |  |  | 0 |  | XYZ Labs | 60 | 9 | Site Cured | LAB-4480

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.