## Cover
EBRORA
ebrora.com
Manhole / Chamber Installation Log
Track manhole and chamber installations with level verification, connection checks, and water test status for adoptable drainage works.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Chamber Log' sheet. The summary panel shows total chambers, installation progress, and test status.
2. Enter each manhole/chamber with its reference, type, date installed, and the design invert and cover levels.
3. After installation, enter the as-built invert and cover levels. Depth auto-calculates (cover minus invert).
4. Invert Variance and Cover Variance auto-calculate — showing mm difference between design and as-built.
5. Record the water test result and number of connections made. The Overall Status auto-assesses compliance.
6. Items with level variances exceeding ±15mm flag amber; exceeding ±25mm flag red.
7. Expand optional columns [+] for benching type, step irons, frame/cover type, and CCTV reference.
8. Filter by status to find chambers needing remedial work or outstanding water tests.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | COMPLETE — installed, tested, within tolerance
| Amber | REVIEW — minor variance or test pending
| Red | ACTION — exceeds tolerance or test failed
Tips
• Check cover levels against finished surface design — a misset cover is a trip hazard and an adoption failure.
• Water test all manholes before backfilling — Sewers for Adoption requires a drop test to specified criteria.
• Photograph each chamber internally before and after benching for the adoption package.

## Chamber Log
MANHOLE / CHAMBER INSTALLATION LOG
Total Chambers |  | Installed |  | Water Tested |  | Complete |  | Action Needed |  | Completion %
5 |  | 4 |  | 3 |  | 2 |  | 2 |  | 40%
▸ Optional Fields — Click [+] to expand
MH Ref | Type | Date Installed | Design Invert (m) | Design Cover (m) | As-Built Invert (m) | As-Built Cover (m) | Depth (m) | Invert Var (mm) | Cover Var (mm) | Water Test | No. Conns | Status | Notes | Benching Type | Step Irons | Frame / Cover Type | CCTV Ref
MH-01 | Precast Concrete | 2026-02-10 | 39.85 | 41.05 | 39.855 | 41.048 | 1.193 | 5 | -2 | Pass | 3 | COMPLETE | All connections verified | Full | Yes | D400 Ductile Iron | CCTV-001
MH-02 | Precast Concrete | 2026-02-12 | 39.45 | 40.85 | 39.445 | 40.855 | 1.41 | -5 | 5 | Pass | 2 | COMPLETE |  | Full | Yes | D400 Ductile Iron | CCTV-002
MH-03 | Precast Concrete | 2026-02-14 | 38.92 | 40.62 | 38.94 | 40.615 | 1.675 | 20 | -5 | Pending |  | REVIEW | Invert 20mm high — check impact on falls | Half | Yes | D400 Ductile Iron
MH-04 | Plastic (PPIC) | 2026-02-15 | 40.1 | 41.2 | 40.098 | 41.23 | 1.132 | -2 | 30 | Fail |  | ACTION | Cover 30mm high — reduce riser section | N/A | N/A | B125 Plastic
MH-05 | Inspection Chamber |  | 40.55 | 41.1 |  |  | 0 | -40550 | -41100 |  |  | ACTION | Not yet installed — awaiting pipe run PR-05 | N/A | N/A
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.