## Cover
EBRORA
ebrora.com
Budget vs Actual Cost Tracker
Monitor project costs against budget by category with automatic
variance calculation, forecast tracking, and overspend alerts.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Budget vs Actual' sheet. The layout is organised by cost category — each section (Preliminaries, Substructure, Superstructure, etc.) has its own banded header with line items beneath and a subtotal row.
2. | The Grand Summary block at the top (rows 3–5) automatically totals all category subtotals. Use this as your headline cost position for reporting.
3. | For each line item, enter the Budget (£) first. As costs are incurred, update Actual to Date (£) and Committed (£). The Forecast, Variance, and % Spent columns calculate automatically.
4. | Forecast Final Cost = Actual to Date + Committed. Variance = Budget – Forecast. Positive variance means underspend; negative (shown in red) means overspend.
5. | Add new line items by inserting rows within a category band. Adjust the subtotal SUM ranges if you add or remove rows.
Optional Fields
6. | Click [+] to expand optional columns: Original Budget, Approved VOs, Revised Budget, Accruals, and Payment Cert Ref. These are useful for formal CVR reporting and final account reconciliation.
7. | If you use the VO columns, Revised Budget = Original Budget + Approved VOs. The formula is pre-built.
Colour Key
Light teal cells (#E8F6F7) — User input. Enter your cost data here.
Dark navy headers — Do not edit. Column headers and category bands.
Teal band rows — Category section headers (Preliminaries, Substructure, etc.).
Bold rows with grey fill — Subtotal rows. These contain SUM formulas.
Green variance — Underspend (positive variance).
Red variance — Overspend (negative variance).
Amber % Spent — Between 80–99% of budget used.
Red % Spent — 100%+ of budget used (overspent).
Tips
Tip 1: | Update this tracker at minimum fortnightly, ideally weekly. Stale cost data leads to surprise overspends at final account.
Tip 2: | Use the Committed column to capture subcontractor orders and purchase orders that haven’t yet been invoiced. This gives a true forecast, not just what’s been paid.
Tip 3: | Present the Grand Summary block in your monthly commercial meeting — it gives an instant project cost health check.

## Budget vs Actual
BUDGET VS ACTUAL COST TRACKER
GRAND TOTAL |  | Budget (£) | Actual to Date (£) | Committed (£) | Forecast Final (£) | Variance (£) | % Spent
PROJECT TOTAL |  | 3589000 | 1897000 | 1185700 | 3082700 | 506300 | 52.86%
▸ Optional Fields — Click [+] to expand
Cost Code | Description | Budget (£) | Actual to Date (£) | Committed (£) | Forecast Final Cost (£) | Variance (£) | % Spent | Notes | Original Budget (£) | Approved VOs (£) | Revised Budget (£) | Accruals (£) | Payment Cert Ref
1.0 PRELIMINARIES
1.01 | Site establishment & setup | 85000 | 78500 | 4200 | 82700 | 2300 | 92.35%
1.02 | Site management & supervision | 320000 | 195000 | 125000 | 320000 | 0 | 60.94%
1.03 | Temporary services (water, power, welfare) | 45000 | 32000 | 10000 | 42000 | 3000 | 71.11%
1.04 | Hoarding, signage & security | 28000 | 26500 | 0 | 26500 | 1500 | 94.64%
1.05 | Insurance & bonds | 18000 | 18000 | 0 | 18000 | 0 | 100%
| Subtotal — PRELIMINARIES | 496000 | 350000 | 139200 | 489200 | 6800 | 70.56% |  | 0 | 0 | 0 | 0
2.0 SUBSTRUCTURE
2.01 | Excavation & earthworks | 150000 | 142000 | 5000 | 147000 | 3000 | 94.67%
2.02 | Piling | 280000 | 275000 | 0 | 275000 | 5000 | 98.21%
2.03 | Ground beams & pile caps | 95000 | 88000 | 3500 | 91500 | 3500 | 92.63%
2.04 | Below-ground drainage | 65000 | 48000 | 12000 | 60000 | 5000 | 73.85%
| Subtotal — SUBSTRUCTURE | 590000 | 553000 | 20500 | 573500 | 16500 | 93.73% |  | 0 | 0 | 0 | 0
3.0 SUPERSTRUCTURE
3.01 | Structural steel frame | 520000 | 380000 | 140000 | 520000 | 0 | 73.08%
3.02 | Precast concrete floors | 210000 | 205000 | 0 | 205000 | 5000 | 97.62%
3.03 | Blockwork & masonry | 175000 | 92000 | 78000 | 170000 | 5000 | 52.57%
3.04 | Roofing & waterproofing | 140000 | 25000 | 110000 | 135000 | 5000 | 17.86%
| Subtotal — SUPERSTRUCTURE | 1045000 | 702000 | 328000 | 1030000 | 15000 | 67.18% |  | 0 | 0 | 0 | 0
4.0 MECHANICAL & ELECTRICAL
4.01 | HVAC installation | 310000 | 85000 | 200000 | 285000 | 25000 | 27.42%
4.02 | Electrical first & second fix | 280000 | 95000 | 160000 | 255000 | 25000 | 33.93%
4.03 | Plumbing & sanitary ware | 120000 | 35000 | 75000 | 110000 | 10000 | 29.17%
4.04 | Fire detection & alarm systems | 65000 | 12000 | 48000 | 60000 | 5000 | 18.46%
4.05 | BMS & controls | 90000 | 8000 | 75000 | 83000 | 7000 | 8.889%
| Subtotal — MECHANICAL & ELECTRICAL | 865000 | 235000 | 558000 | 793000 | 72000 | 27.17% |  | 0 | 0 | 0 | 0
5.0 EXTERNAL WORKS
5.01 | Hard landscaping & paving | 95000 | 0 | 85000 | 85000 | 10000 | 0%
5.02 | Soft landscaping & planting | 45000 | 0 | 0 | 0 | 45000 | 0%
5.03 | External drainage & services | 78000 | 15000 | 55000 | 70000 | 8000 | 19.23%
| Subtotal — EXTERNAL WORKS | 218000 | 15000 | 140000 | 155000 | 63000 | 6.881% |  | 0 | 0 | 0 | 0
6.0 CONTINGENCY & RISK
6.01 | Design contingency | 120000 | 0 | 0 | 0 | 120000 | 0%
6.02 | Construction contingency | 180000 | 42000 | 0 | 42000 | 138000 | 23.33%
6.03 | Client risk allowance | 75000 | 0 | 0 | 0 | 75000 | 0%
| Subtotal — CONTINGENCY & RISK | 375000 | 42000 | 0 | 42000 | 333000 | 11.2% |  | 0 | 0 | 0 | 0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.