## Cover
EBRORA
ebrora.com
Interim Valuation Summary
Structured interim payment valuation with automatic calculation of
retention, deductions, VAT, and amount due per certificate period.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Interim Valuation' sheet. The top section is a form-style header — fill in the project name, employer, contractor, contract reference, valuation number, and the period dates.
2. | The main valuation table is split into work categories. For each line, enter the Contract Sum allocation (original budget per item), Cumulative Value to Date (total value of work completed), and Previous Certified amount (value certified in all prior valuations).
3. | This Period Value calculates automatically: Cumulative – Previous. This is the new value being claimed in this certificate.
4. | Below the valuation table, the Deductions & Payment block calculates retention, adds approved variations, deducts contra charges, applies VAT, and arrives at the Amount Due This Certificate.
5. | Adjust the retention percentage in the input cell (default 5%). The template handles retention on the gross valuation automatically.
Layout Explanation
6. | This is a single-certificate form. Duplicate the 'Interim Valuation' sheet for each new valuation period, updating the header details and Previous Certified column from the prior sheet.
7. | The % Complete column is auto-calculated as Cumulative / Contract Sum. This gives a visual read of progress per category.
Colour Key
Light teal cells (#E8F6F7) — User input. Fill in your valuation data here.
Dark navy headers — Do not edit. Section headers and labels.
Grey rows — Subtotal and total rows with SUM formulas.
Green % Complete — 90%+ complete.
Amber % Complete — 50–89% complete.
Red (negative variance) — This period value is negative (reduction).
Tips
Tip 1: | Always agree the valuation with the QS or contract administrator before issuing. The summary format is designed to accompany a detailed measured breakdown.
Tip 2: | Track retention separately — note that retention is automatically calculated as a percentage of the gross valuation, not of this period’s value.
Tip 3: | Keep a copy of each completed valuation sheet as your payment audit trail. Name tabs IPC-01, IPC-02, etc.

## Interim Valuation
INTERIM VALUATION SUMMARY
Project Name: | Riverside Business Park — Phase 2 |  |  | Valuation No: | IPC-05
Employer: | Riverside Developments Ltd |  |  | Valuation Date: | 2026-02-28
Main Contractor: | Kier Construction Ltd |  |  | Period From: | 2026-02-01
Contract Ref: | RBP2-MC-001 |  |  | Period To: | 2026-02-28
Ref | Work Element | Contract Sum (£) | Cumulative Value (£) | Previous Certified (£) | This Period (£) | % Complete
1.0 PRELIMINARIES
1.1 | Site establishment | 85000 | 85000 | 85000 | 0 | 100%
1.2 | Site management | 320000 | 260000 | 225000 | 35000 | 81.25%
1.3 | Temporary services | 45000 | 38000 | 32000 | 6000 | 84.44%
1.4 | Insurance & bonds | 18000 | 18000 | 18000 | 0 | 100%
| Subtotal — PRELIMINARIES | 468000 | 401000 | 360000 | 41000 | 85.68%
2.0 SUBSTRUCTURE
2.1 | Excavation & earthworks | 150000 | 150000 | 150000 | 0 | 100%
2.2 | Piling | 280000 | 280000 | 280000 | 0 | 100%
2.3 | Ground beams | 95000 | 95000 | 88000 | 7000 | 100%
2.4 | Below-ground drainage | 65000 | 52000 | 42000 | 10000 | 80%
| Subtotal — SUBSTRUCTURE | 590000 | 577000 | 560000 | 17000 | 97.8%
3.0 SUPERSTRUCTURE
3.1 | Structural steel frame | 520000 | 480000 | 420000 | 60000 | 92.31%
3.2 | Precast floors | 210000 | 210000 | 205000 | 5000 | 100%
3.3 | External envelope | 310000 | 185000 | 120000 | 65000 | 59.68%
3.4 | Roofing | 140000 | 45000 | 18000 | 27000 | 32.14%
| Subtotal — SUPERSTRUCTURE | 1180000 | 920000 | 763000 | 157000 | 77.97%
4.0 M&E SERVICES
4.1 | HVAC | 310000 | 125000 | 85000 | 40000 | 40.32%
4.2 | Electrical | 280000 | 110000 | 72000 | 38000 | 39.29%
4.3 | Plumbing | 120000 | 42000 | 28000 | 14000 | 35%
4.4 | Fire systems | 65000 | 18000 | 8000 | 10000 | 27.69%
4.5 | BMS & controls | 90000 | 12000 | 5000 | 7000 | 13.33%
| Subtotal — M&E SERVICES | 865000 | 307000 | 198000 | 109000 | 35.49%
5.0 EXTERNAL WORKS
5.1 | Hard landscaping | 95000 | 0 | 0 | 0 | 0%
5.2 | Soft landscaping | 45000 | 0 | 0 | 0 | 0%
5.3 | External services | 78000 | 18000 | 10000 | 8000 | 23.08%
| Subtotal — EXTERNAL WORKS | 218000 | 18000 | 10000 | 8000 | 8.257%
| GROSS VALUATION TOTAL | 3321000 | 2223000 | 1891000 | 332000 | 66.94%
DEDUCTIONS & AMOUNT DUE
A. Gross Valuation This Period |  |  |  |  | 332000
B. Retention Percentage |  |  |  |  | 5%
C. Retention on Cumulative Valuation |  |  |  |  | 111150
D. Previous Retention Held |  |  |  |  | 80425
E. Retention Deducted This Period (C – D) |  |  |  |  | 30725
F. Approved Variations This Period |  |  |  |  | 25300
G. Contra Charges / Deductions |  |  |  |  | -3200
H. Net Valuation This Period (A – E + F + G) |  |  |  |  | 323375
I. VAT @ 20% |  |  |  |  | 64675
AMOUNT DUE THIS CERTIFICATE |  |  |  |  | 388050
Prepared by: |  |  |  | Approved by:
Name / Date |  |  |  | Name / Date

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.