## Constraint Log
ebrora.com
PLANNING CONSTRAINT AND BLOCKER LOG
Project: |  |  |  | Programme Mgr: |  |  |  | Rev:
No. | Date Raised | Constraint / Blocker Description | Category | Affected Activity / Work Package | Impact on Programme (Days) | Priority (H/M/L) | Owner / Responsible | Resolution Action Required | Target Resolution Date | Actual Resolution Date | Days Open | Status | Escalated? (Yes/No) | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
SUMMARY
Total Constraints: |  | 0
Open: |  | 0
Resolved: |  | 0
High Priority Open: |  | 0
Total Programme Impact (Days): |  | 0
Formulas:
Days Open = IF([Date Raised]="","",IF([Actual Resolution Date]<>"",[Actual Resolution Date]-[Date Raised],TODAY()-[Date Raised]))

## Instructions
ebrora.com
INSTRUCTIONS — Planning Constraint and Blocker Log
How to Use This Template
1. Record any constraint or blocker that prevents planned work from proceeding.
2. Select the category from the dropdown (design info, access, material, etc.).
3. Identify the affected activity and estimate programme impact in days.
4. Assign priority (H/M/L) and an owner responsible for resolution.
5. Describe the required resolution action and set a target date.
6. Days open auto-calculates. Track status until resolved.
7. Escalate unresolved high-priority constraints — flag in the Escalated column.
8. Review constraints weekly at programme/coordination meetings.
References:
NEC4 Clause 32 — Early Warning and Risk Reduction
Last Planner System — Constraint Analysis