## 3-Week Lookahead
ebrora.com
3-WEEK LOOKAHEAD PLANNER
Project: |  |  |  | Week Commencing: |  |  | Prepared By:
[6 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3
No. | Task / Activity | Responsible Contractor | Location / Area | Priority (H/M/L) | Status | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
SUMMARY
Total Tasks: |  | 0
Complete: |  | 0
Delayed: |  | 0
PPC (%):
KEY: X=Planned, P=In Progress, C=Complete, D=Delayed. Shaded columns=weekends.

## Instructions
ebrora.com
INSTRUCTIONS — 3-Week Lookahead Planner
How to Use This Template
1. Enter the week commencing date — this defines the 3-week period.
2. List all planned activities with responsible contractor, location, and priority.
3. Mark days using X=Planned, P=In Progress, C=Complete, D=Delayed.
4. Update status column as tasks progress.
5. Weekend columns are shaded grey for visibility.
6. PPC (Percent Plan Complete) calculates automatically in the summary.
7. Issue weekly and update at coordination meetings.
8. 30 task rows provided — add more as needed.
PPC (Last Planner System):
PPC = Tasks completed on time ÷ Tasks planned × 100
Target PPC: typically 75–85% is considered good performance.
References:
NEC4 Clause 32 — Programme Revisions and Short-Term Planning
Last Planner System (Lean Construction Institute)