## Site Diary
ebrora.com
DAILY SITE DIARY LOG
Project: |  |  |  | Date:
Site Manager: |  |  |  | Day:
WEATHER CONDITIONS
| AM | PM | Temperature (°C) | Wind | Rainfall
Conditions:
LABOUR ON SITE
| Contractor / Trade | Operatives | Supervision | Total | Hours Worked | Notes
1
2
3
4
5
6
7
8
9
10
| TOTAL | 0 | 0 | 0
WORKS CARRIED OUT TODAY
1
2
3
4
5
6
PLANT ON SITE
1
2
3
4
DELIVERIES RECEIVED
1
2
3
ISSUES / DELAYS / STOPPAGES
1
2
3
VISITORS TO SITE
1
2
3
HEALTH & SAFETY NOTES
Accidents/Incidents:
Near Misses:
Completed By: |  |  | Signature:

## Instructions
ebrora.com
INSTRUCTIONS — Daily Site Diary Log
How to Use This Template
1. Complete one diary sheet per day.
2. Record weather conditions, labour numbers by contractor/trade.
3. Describe all works carried out, plant on site, and deliveries received.
4. Note any issues, delays, stoppages, or disputes.
5. Record all visitors to site.
6. Note any H&S incidents, near misses, or observations.
7. Total labour counts auto-calculate in the summary row.
8. Sign and date the diary at end of each day.
Why Site Diaries Matter:
Contemporaneous records are critical evidence for delay/disruption claims.
NEC4 Clause 60–65 relies on timely records of events.
References:
NEC4 / JCT contract record-keeping requirements
CDM 2015 — Principal Contractor record-keeping duties