Temporary Works Category Guide

| Document Ref: | Enter document reference |
| --- | --- |
| Revision: | Enter revision number |
| Date: | DD / MM / YYYY |
| Project Name: | Enter project name |
| Contract No.: | Enter contract number |
| Prepared By: | Enter name and role |
| Approved By: | Enter name and role |

# Purpose

This guide explains how temporary works are categorised on this project in accordance with BS 5975:2019. Correct categorisation determines the level of design, checking, and management control required. All project staff involved in planning, designing, installing, or managing temporary works must be familiar with this guide.

# Category Definitions

| Category | Risk Level | Design Requirement | Check Requirement |
| --- | --- | --- | --- |
| Category 1 | Low risk – simple, repetitive, well-understood items with low consequence of failure | Design by competent person using standard details, supplier information, or tabulated data | No independent design check required. TWC to verify compliance with standard details. |
| Category 2 | Medium risk – non-standard, significant consequence of failure, or affecting permanent works or third parties | Formal design by a competent designer producing drawings and calculations | Independent design check required by a checker who is independent of the designer |
| Category 3 | High risk – complex, novel, high consequence of failure, adjacent to public, or involving significant structural risk | Full design by Chartered Engineer with detailed calculations, drawings, and specifications | Full independent design check by a Chartered Engineer independent of the designer. May require third-party review. |

# Examples by Category

## Category 1 – Low Risk Examples

- Standard proprietary scaffolding erected to manufacturer’s guidance (basic scaffold to TG20 compliance)

- Trench boxes used within manufacturer’s rated depth and soil conditions

- Simple edge protection to standard details

- Proprietary formwork systems used within manufacturer’s load tables

- Standard hoarding and fencing (non-structural)

- Small mobile elevated work platforms (MEWPs) and access towers within manufacturer’s guidance

- Standard temporary signage and barriers

## Category 2 – Medium Risk Examples

- Bespoke scaffolding designs (tied scaffolds, loading bays, cantilevered sections)

- Propping to existing structures during alteration or demolition

- Formwork and falsework for reinforced concrete structures

- Sheet piling and trench support beyond standard tabulated data

- Crane pads and hardstandings requiring ground bearing calculations

- Temporary steel bracing to structures under construction

- Dewatering systems affecting adjacent structures or services

- Temporary retaining walls and slopes with surcharge loading

- Temporary access roads over soft ground requiring design

## Category 3 – High Risk Examples

- Cofferdams and caissons

- Complex falsework for heavy or long-span structures

- Temporary bridges and platforms over live carriageways or railways

- Major propping schemes adjacent to occupied buildings

- Temporary works in or over water (rivers, reservoirs, marine)

- Launch nose and incremental launch systems

- Heavy lifting frames and specialist rigging

- Temporary works affecting Network Rail or Highways England assets

- Novel or untried temporary works methods

# Categorisation Decision Factors

When categorising temporary works, the TWC must consider the following factors. If any factor suggests a higher category, the temporary works must be placed in the higher category.

| Factor | Considerations |
| --- | --- |
| Consequence of Failure | Could failure result in injury, death, damage to permanent works, or harm to the public? |
| Complexity | Is the design straightforward or does it require specialist engineering judgement? |
| Proximity to Public | Are the temporary works adjacent to public highways, footpaths, or occupied buildings? |
| Ground Conditions | Are ground conditions well-understood, or is there uncertainty about bearing capacity or water levels? |
| Loading | Are loads well-defined and static, or are there dynamic, cyclic, or uncertain loads? |
| Duration | Are the temporary works short-term or will they remain in place for an extended period? |
| Adjacent Structures | Could failure affect existing structures, buried services, or adjacent properties? |
| Novelty | Has this type of temporary works been done before, or is it a new or untried approach? |
| Environmental Factors | Are there significant environmental risks (e.g. flooding, tidal, high winds)? |

# Process Summary by Category

| Requirement | Cat 1 | Cat 2 | Cat 3 |
| --- | --- | --- | --- |
| Registered on TW Register | Yes | Yes | Yes |
| Design Brief Required | No (standard details) | Yes | Yes |
| Formal Design Calculations | No | Yes | Yes |
| Independent Design Check | No | Yes | Yes (Chartered Eng.) |
| Design Check Certificate | No | Yes | Yes |
| Method Statement | Risk-assessed procedure | Yes | Yes (detailed) |
| Completion Inspection | TWC or delegate | TWC | TWC |
| Permit to Load | TWC | TWC | TWC |
| Inspection During Use | Periodic | Regular | Frequent / monitored |
| Permit to Dismantle | TWC | TWC | TWC |

# Notes / Additional Comments

Regulatory References: BS 5975:2019, CDM 2015, CIRIA C779, CIRIA R165 (Temporary Works Design Checking).

# Document Control

| Revision | Date | Description of Change | Author | Approved By |
| --- | --- | --- | --- | --- |
| 01 |  | Initial issue |  |  |