## Cover
EBRORA
ebrora.com
Goods Received Note Log
Log all goods received on site with order matching, quantity verification, condition assessment, and discrepancy tracking.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'GRN Log' sheet. The summary shows total deliveries, acceptance rate, and discrepancy count.
2. Log each delivery with the GRN number, date, supplier, PO number, and delivery note reference.
3. Enter the material description, quantity ordered, and quantity received. Discrepancy auto-calculates.
4. Assess the condition of goods on arrival and select the overall receipt status from the dropdown.
5. Status options: Accepted (all correct), Partial (short delivery), Rejected (damaged/wrong), or Query.
6. Discrepancies (qty received ≠ qty ordered) auto-highlight. Record details in the notes column.
7. Expand optional columns [+] for MTC received status, storage location, and who signed for the delivery.
8. Cross-reference GRNs with purchase orders and supplier invoices to prevent overpayment.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | Accepted — correct quantity and condition
| Amber | Partial or Query — discrepancy noted
| Red | Rejected — damaged, wrong, or refused
Tips
• Check deliveries against the PO immediately — don't sign for goods without counting and inspecting.
• Photograph any damage before accepting the delivery — this protects your claim against the carrier/supplier.
• File delivery notes with the matching GRN and PO — this three-way match is essential for invoice approval.

## GRN Log
GOODS RECEIVED NOTE LOG
Total GRNs |  | Accepted |  | Partial / Query |  | Rejected |  | Acceptance Rate |  | With Discrepancy
5 |  | 3 |  | 2 |  | 0 |  | 60% |  | 2
▸ Optional Fields — Click [+] to expand
GRN No. | Date | Supplier | PO Number | Del. Note Ref | Material / Description | Qty Ordered | Qty Received | Discrepancy | Condition | Receipt Status | Notes | MTC Received | Storage Location | Received By
GRN-001 | 2026-02-20 | Tata Steel UK | PO-2240 | DN-T4521 | UC 254x254x89 — S355 J2 (12 No.) | 12 | 12 | 0 | Good | Accepted | MTCs received with delivery | Yes | Steel Laydown SA-01 | Kev O'Brien
GRN-002 | 2026-02-20 | Hanson Concrete | PO-2260 | DN-88420 | C30/37 Ready-Mix (18m³ — 3 loads) | 18 | 18 | 0 | Good | Accepted | All 3 loads delivered on time | N/A | Direct to pour | Dave Murphy
GRN-003 | 2026-02-20 | Jewson | PO-2265 | DN-J7832 | 18mm Formwork Plywood (40 sheets) | 40 | 38 | -2 | Acceptable | Partial | 2 sheets short — supplier to send remainder | N/A | Carpentry Store | Raj Patel
GRN-004 | 2026-02-21 | Lindapter | PO-2241 | DN-L2205 | Grade 8.8 Bolts M20×60 (200 No.) | 200 | 200 | 0 | Good | Accepted |  | Yes | Secure Store SA-02 | Site Office
GRN-005 | 2026-02-21 | ABC Aggregates | PO-2268 | DN-ABC-991 | Type 1 Sub-base (20 tonnes) | 20 | 18.5 | -1.5 | Acceptable | Query | Weighed 18.5t on arrival — 1.5t short. Queried with supplier. | N/A | Road Store Area | Raj Patel
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.