## Cover
EBRORA
ebrora.com
Storage Area Allocation Plan
Plan and manage site storage zones with material assignments, capacity tracking, utilisation monitoring, and access requirements.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Storage Plan' sheet. The summary shows total storage area, overall utilisation, and zone count.
2. Define each storage zone with its reference, description, area (m²), and type (covered, open, secure, etc.).
3. Assign materials/items to each zone and record the responsible person or subcontractor.
4. Enter the capacity as a percentage estimate of how full the zone is. Utilisation auto-colours: green/amber/red.
5. Record any access restrictions (COSHH, locked, permit required) and the zone's availability dates.
6. Status auto-calculates: AVAILABLE (<50% full), BUSY (50–80%), FULL (>80%), or CLOSED.
7. Review and update weekly as materials arrive and get used — zones should turn over, not stay permanently full.
8. Pair this with the site layout drawing — number zones on the drawing to match this register.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | Available — zone has capacity
| Amber | Busy — 50–80% full
| Red | Full (>80%) or Closed
Tips
• Keep high-value and theft-attractive materials (copper, tools, fuel) in locked/secure zones only.
• Plan storage around the construction sequence — don't store materials far from where they'll be used.
• COSHH materials must have dedicated, bunded storage with spill kits — never co-locate with general materials.

## Storage Plan
STORAGE AREA ALLOCATION PLAN
Total Zones |  | Total Area (m²) |  | Avg Utilisation |  | Full Zones |  | Available Zones |  | Closed Zones
6 |  | 572 |  | 55% |  | 1 |  | 3 |  | 0
Zone Ref | Zone Description | Type | Area (m²) | Materials / Items Assigned | Responsible Person | Utilisation (%) | Status | Access Restrictions | Available From | Available To | Notes
SA-01 | Steel Laydown Area — North | Open Laydown | 200 | UC sections, UB beams, base plates, holding down bolts | Kev O'Brien (Steel Foreman) | 65% | BUSY | Open Access | 2026-01-15 | 2026-06-30 | Crane access required for offloading
SA-02 | Secure Tool & Material Store | Container | 30 | Power tools, laser levels, torque wrenches, fixings | Site Manager | 80% | BUSY | Locked | 2026-01-15 |  | Double-locked — key with SM and stores
SA-03 | COSHH Store | COSHH Store | 12 | Paints, solvents, adhesives, release agents, fuel additives | H&S Advisor | 45% | AVAILABLE | COSHH Trained Only | 2026-01-15 |  | Bunded, ventilated. Spill kit on site.
SA-04 | Pipe & Fittings Laydown | Open Laydown | 150 | DN100–DN300 pipe, fittings, valves, gaskets | Pipework Foreman | 30% | AVAILABLE | Open Access | 2026-02-01 | 2026-05-31 | Dunnage provided — keep off ground
SA-05 | Waste & Skip Area | Waste Area | 100 | Skips (general, timber, inert), waste bins | Waste Coordinator | 90% | FULL | Open Access | 2026-01-15 |  | Segregated streams — signage in place
SA-06 | Temporary Material Store — South | Temporary | 80 | Bricks, blocks, bagged aggregates, cement | Bricklaying Gang | 20% | AVAILABLE | Open Access | 2026-03-01 | 2026-04-30 | Temporary — relocates when groundworks reach south end
Formulas:
Status = IF([Total Zones]="","",IF([Closed Zones]<>"",IF([Closed Zones]<TODAY(),"CLOSED",IF([Full Zones]>0.8,"FULL",IF([Full Zones]>0.5,"BUSY","AVAILABLE"))),IF([Full Zones]>0.8,"FULL",IF([Full Zones]>0.5,"BUSY","AVAILABLE"))))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.