## Cover
EBRORA
ebrora.com
Subcontractor Deliverables Matrix
Track O&M manuals, as-built drawings and test packs due vs received from every subcontractor — one matrix, full visibility.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — Subcontractor Deliverables Matrix
Step-by-Step Instructions
1. | Go to the 'Deliverables Matrix' sheet. Enter the Project Name and Contract Number in the info strip at the top.
2. | The matrix rows (column A) list each Subcontractor. The description in column B records their scope of works. Update these to match your project's subcontract structure.
3. | The matrix columns (C onwards) represent the standard deliverable categories required from each subcontractor at handover. Pre-populated with common requirements — update to match your contract.
4. | In each intersection cell, enter the deliverable status using the dropdown: ✓ Received, ⧖ Due, ✗ Outstanding, or N/A.
5. | The cell colour updates automatically: green for Received, amber for Due, red for Outstanding, grey for N/A.
6. | Column B shows the % of applicable deliverables received for each subcontractor — this drives the at-a-glance readiness score.
7. | The completion % row at the bottom shows column-by-column receipt rates across all subcontractors.
8. | Review this matrix at the monthly progress meeting. Any subcontractor showing Outstanding items 4 weeks before practical completion needs a formal notice.
9. | For each Outstanding cell, add the reason or expected date in the Notes column (far right). This becomes the action log for the handover chase.
10. | Print landscape for the Monthly Progress Report or Pre-Handover Submission to the Employer's Representative.
Colour Key
✓ Received — Deliverable has been received and accepted.
⧖ Due — Deliverable is expected imminently or within the agreed programme.
✗ Outstanding — Deliverable has not been received and no submission date confirmed.
N/A — This deliverable category does not apply to this subcontractor's scope.
Light teal % complete column — Auto-calculated per row and column.
Tips
* | Build this matrix into every subcontract — list the required deliverables in the subcontract documents and reference this register as the tracking mechanism. Subcontractors who know deliverables are being tracked submit earlier.
* | O&M manuals and as-built drawings are the most commonly late items at handover. Chase these at 12 weeks, 8 weeks, and 4 weeks before practical completion. Don't wait until the last month.
* | If a subcontractor's scope changes during the project, update the N/A cells and add a note. A change in scope that reduces deliverables must be formally agreed — not just reflected in this matrix.

## Deliverables Matrix
Project Name: |  | [Enter Project Name] |  |  |  |  | Contract No: |  | [Contract No]
Subcontractor / Scope |  |  | Handover Deliverables ¦ ✓ = Received ⧖ = Due ✗ = Outstanding N/A = Not Applicable
Subcontractor | Scope of Works | % Received | O&M Manual Submitted | O&M Manual Approved | As-Built Drawings | Test Packs & Certs | Material Certs | Commissioning Records | Spare Parts List | Warranty Certs | RAMS Final | H&S File Contribution | Training Records | Snag List Cleared | Notes / Outstanding Actions
Groundworks Ltd | Earthworks, pipelaying, concrete works, drainage | 77.78% | ✓ Received | ⧖ Due | ✓ Received | ✓ Received | ✓ Received | N/A | N/A | ✓ Received | ✓ Received | ✓ Received | N/A | ⧖ Due | O&M approved. As-builts still being finalised — target 15/04.
Walsh MEP Ltd | Pumps, valves, pipework, mechanical installation | 36.36% | ⧖ Due | ✗ Outstanding | ⧖ Due | ✓ Received | ✓ Received | ✗ Outstanding | ✗ Outstanding | ✗ Outstanding | ✓ Received | ✓ Received | N/A | ✗ Outstanding | O&M Rev 1 received — review in progress. Chase spare parts list urgently.
Roberts Electrical Ltd | MCC, LV distribution, cable installation, earthing | 36.36% | ⧖ Due | ✗ Outstanding | ⧖ Due | ✓ Received | ✓ Received | ✗ Outstanding | ✗ Outstanding | ✗ Outstanding | ✓ Received | ✓ Received | N/A | ✗ Outstanding | O&M Rev 1 submitted 10/03 — under review. Wiring diagrams as-builts by 30/03.
InControl Systems Ltd | SCADA, PLC, instrumentation, control panels | 33.33% | ✗ Outstanding | ✗ Outstanding | N/A | N/A | N/A | ✗ Outstanding | N/A | N/A | ✓ Received | ✓ Received | ✗ Outstanding | N/A | SAT procedure outstanding — required 4 weeks before commissioning. Training records TBC.
Hargreaves Plant Ltd | Cranage, lifting, temporary works | —
Protective Coatings Ltd | Internal and external coatings, tank linings | —
Steelco Ltd | Structural steelwork, handrails, grating | —
Redimix Concrete Ltd | Ready-mix concrete supply | —
Polypipe Ltd | HDPE duct supply and installation | —
Walsh MEP Commissioning | Commissioning support and wet runs | —
COLUMN RECEIPT % |  |  | 25% | 0% | 33.33% | 100% | 100% | 0% | 0% | 33.33% | 100% | 100% | 0% | 0%

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.