## Cover
EBRORA
ebrora.com
Survey / Setting Out Check Register
Verify as-built positions against design coordinates with automatic deviation calculation and tolerance checking.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Setting Out Checks' sheet. The summary panel shows live accuracy statistics.
2. The column layout splits into three banded sections: Design Coordinates, As-Built Coordinates, and Deviation Analysis.
3. Enter each survey point with its reference, description, and the design Easting, Northing, and Level from your drawings.
4. After the setting out check, enter the as-built Easting, Northing, and Level from the total station / GPS readout.
5. Plan Deviation (mm) auto-calculates using Pythagoras — the horizontal distance between design and as-built positions.
6. Level Deviation (mm) auto-calculates as the absolute vertical difference × 1000.
7. Enter the tolerance (mm) for the element — this varies by element type (foundations ±25mm, steelwork ±5mm, etc.).
8. The 'Within Tolerance' column flags OK (both deviations within limit) or OVER (either exceeds tolerance).
Colour Key
| Light teal cells | Editable — enter your data
| Dark navy headers | Do not edit
| Teal band | Section group header
| Green fill | OK — within tolerance
| Red fill | OVER — exceeds tolerance
Tips
• Always verify the instrument calibration certificate is current before taking measurements.
• Record the total station / GPS setup position and backsight reference for traceability.
• Typical tolerances: foundations ±25mm plan / ±15mm level; steelwork ±5mm; RC walls ±15mm — always check your project spec.

## Setting Out Checks
SURVEY / SETTING OUT CHECK REGISTER
Total Points |  | Checked |  | Within Tol. |  | Over Tol. |  | Compliance |  | Max Plan Dev |  | Max Level Dev
5 |  | 5 |  | 3 |  | 2 |  | 60% |  | 60.208 | mm | 12 | mm
IDENTIFICATION |  |  | DESIGN COORDINATES |  |  | AS-BUILT COORDINATES |  |  | DEVIATION ANALYSIS |  |  |  | SIGN-OFF |  | ▸ Optional
Point Ref | Date | Element / Description | Design Easting | Design Northing | Design Level (m) | As-Built Easting | As-Built Northing | As-Built Level (m) | Plan Dev (mm) | Level Dev (mm) | Tolerance (mm) | Within Tolerance | Checked By | Notes | Instrument | Setup Ref | Weather
SP-001 | 2026-02-10 | Pad Foundation PF-01 (NE Corner) | 463250.125 | 178340.68 | 42.15 | 463250.132 | 178340.688 | 42.147 | 10.6301 | 3 | 25 | OK | R. Khan | Within spec | Leica TS16 | STN-A01 | Clear
SP-002 | 2026-02-10 | Column C3 Base Plate (Centre) | 463255 | 178345.2 | 42.15 | 463254.997 | 178345.204 | 42.153 | 5 | 3 | 10 | OK | R. Khan |  | Leica TS16 | STN-A01 | Clear
SP-003 | 2026-02-11 | RC Wall W2 (Top of Kicker) | 463248.5 | 178338.1 | 42.3 | 463248.518 | 178338.112 | 42.308 | 21.6333 | 8 | 15 | OVER | S. Okonkwo | Check formwork alignment | Leica TS16 | STN-A02 | Overcast
SP-004 | 2026-02-12 | Manhole MH-04 (Invert) | 463260.32 | 178350.45 | 40.875 | 463260.315 | 178350.448 | 40.878 | 5.3852 | 3 | 25 | OK | R. Khan |  | Trimble R12 | GPS-01 | Light rain
SP-005 | 2026-02-12 | Steel Base Plate BP-07 (Centre) | 463242.1 | 178336.8 | 42.15 | 463242.14 | 178336.755 | 42.162 | 60.208 | 12 | 5 | OVER | S. Okonkwo | Over tolerance — reposition required | Leica TS16 | STN-A02 | Clear
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.