## Cover
EBRORA
ebrora.com
Temporary Services Register
Track all temporary site services — power, water, and welfare facilities — with supplier details, inspection scheduling, and cost tracking.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Services Register' sheet. Services are grouped into three colour-coded bands: Power (amber), Water (blue), and Welfare (purple).
2. | Each row represents one temporary service item. Enter the Ref, description, location on site, supplier, and installation date.
3. | Set the Status using the dropdown: Active, Planned (not yet installed), Disconnected, or Fault.
4. | Enter the Next Inspection date. This column highlights red if the date has passed and amber if it's within 7 days.
5. | Expand the optional columns (click [+]) for weekly cost, contract reference, meter readings, capacity, and planned removal date.
6. | Each category band has a mini-counter showing total items and how many are currently active.
7. | Add rows within any band as needed. Keep items in the correct category band for clarity.
Colour Key
Amber-tinted rows — Power services.
Blue-tinted rows — Water services.
Purple-tinted rows — Welfare facilities.
Green status — Active.
Amber status — Planned.
Red status — Fault.
Grey status — Disconnected.
Tips
Tip 1: | Review this register monthly with your commercial team. Temporary services are a significant prelims cost — disconnect anything you no longer need promptly.
Tip 2: | Set calendar reminders for inspection dates. Temporary electrical installations must be inspected every 3 months under BS 7671. Water systems need regular Legionella checks.
Tip 3: | Before any service disconnection, confirm with all trades on site. An unexpected power cut during a concrete pour or curing cycle can be extremely costly.

## Services Register
TEMPORARY SERVICES REGISTER
Project: | Riverside Gateway Phase 2 |  | Site Address: | Regent Road, Salford, M5 4QT
Last Updated: | 2026-03-22 |  | Updated By: | S. Patel
▸ Optional Fields — Click [+] to expand
⚡ POWER & ELECTRICAL | [6 empty] | Items: | 5 | Active: | 4
Ref | Service / Item | Location | Supplier | Install Date | Status | Next Inspection | Cost / Week (£) | Contract Ref | Meter Reading | Capacity | Removal Date
PWR-001 | Temporary distribution board — Main DB-01 | Site compound | Aggreko | 2026-01-10 | Active | 2026-04-10 | 85 | AGG-20261 | 320A | 400A
PWR-002 | Generator 100kVA (diesel) | South compound | Speedy Hire | 2026-01-10 | Active | 2026-04-10 | 420 | SPD-44012 | 1,842 hrs | 100kVA
PWR-003 | Temporary lighting — tower crane area | Crane base | HSS | 2026-02-01 | Active | 2026-05-01 | 65 | HSS-7890 |  | 4x 1000W
PWR-004 | Festoon lighting — Block A internal | Block A L0-L2 | Site team | 2026-02-15 | Active | 2026-05-15 |  |  |  | 110V
PWR-005 | Temporary DB — Block B sub-dist | Block B L1 | Aggreko | 2026-03-05 | Planned | 2026-06-05 | 45 | AGG-20262 |  | 200A
WATER SERVICES | [6 empty] | Items: | 4 | Active: | 4
Ref | Service / Item | Location | Supplier | Install Date | Status | Next Inspection | Cost / Week (£) | Contract Ref | Meter Reading | Capacity | Removal Date
WTR-001 | Temporary mains connection — 25mm MDPE | Site boundary (south) | United Utilities | 2026-01-08 | Active | 2026-07-08 |  | UU-TEMP-4401 | 142 m³ | 25mm
WTR-002 | Bowser — 1000L potable water tank | Welfare block | GAP Hire | 2026-01-08 | Active | 2026-04-08 | 35 | GAP-1122 |  | 1000L
WTR-003 | Dewatering pump — excavation PF area | Grid A1-A6 | Selwood Pumps | 2026-02-20 | Active | 2026-03-20 | 180 | SEL-5567 | Running 24hr | 6"/150mm
WTR-004 | Temporary drainage — silt settlement tank | South outfall | Site team | 2026-01-15 | Active | 2026-04-15 |  |  |  | 10,000L
WELFARE FACILITIES | [6 empty] | Items: | 6 | Active: | 5
Ref | Service / Item | Location | Supplier | Install Date | Status | Next Inspection | Cost / Week (£) | Contract Ref | Meter Reading | Capacity | Removal Date
WEL-001 | Site office — 24ft x 10ft portable cabin | Main compound | Portakabin | 2026-01-05 | Active |  | 110 | PK-88901 |  | 6 desks
WEL-002 | Canteen / drying room — 32ft x 10ft | Main compound | Portakabin | 2026-01-05 | Active |  | 130 | PK-88902 |  | 30 persons
WEL-003 | Toilet block — 4+2 unit | Main compound | Tardis Hire | 2026-01-05 | Active | 2026-03-29 | 95 | TAR-3301 |  | 4M + 2F
WEL-004 | Changing / locker unit — 20ft | Main compound | Portakabin | 2026-01-05 | Active |  | 75 | PK-88903 |  | 20 lockers
WEL-005 | First aid room — 10ft x 8ft | Main compound | Portakabin | 2026-01-05 | Active |  | 65 | PK-88904 |  | 1 bed + sink
WEL-006 | Security gatehouse — 8ft x 6ft | Main entrance | Portakabin | 2026-01-05 | Fault | 2026-03-25 | 55 | PK-88905 |  | 1 person | Heating fault — repair booked

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.