## Cover
EBRORA
ebrora.com
Temporary Works Register
Manage all temporary works on site — track design status, installation, permits to load, and dismantling in one BS 5975-aligned register.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Go to the “Temporary Works Register” tab. Each row records one temporary works item on site.
2. | Enter the Date Raised and a clear Description of the temporary works (e.g. “Propping to slab S03 during demolition of internal wall W7”).
3. | Record the Location on site and select the Category from the dropdown: Propping, Shoring, Falsework, Formwork, Hoarding, Scaffolding, Cofferdam, Temporary Access, Dewatering, or Other.
4. | Enter the name of the Temporary Works Coordinator (TWC). Under BS 5975:2019, the TWC is the competent person responsible for managing all temporary works on site.
5. | Indicate whether a Design Check is required (Yes/No). Category 1 (low risk, standard solutions) items may not need a formal design check. Category 2 and 3 items always do.
6. | Track the Design Status through its stages: Not Started, In Progress, Approved, or N/A. No temporary works may be installed until the design is Approved (or marked N/A for items not requiring design).
7. | Track the Installation Status: Not Installed, In Progress, Installed, or Removed. Update this as work progresses.
8. | Record whether a Permit to Load has been issued (Yes/No). The permit to load confirms the temporary works have been inspected, are in accordance with the design, and may be loaded. No loading is permitted without this.
9. | For additional detail, expand the optional columns: Designer/Checker, Design Ref, Installation Inspection Date, Dismantling Date, Risk Level, and Notes.
10. | The dashboard auto-calculates design and installation status breakdowns, items awaiting approval, and flags items installed without a permit to load.
Colour Key
• | Light teal cells = User input / editable fields.
• | Dark navy headers = Column headers. Do not edit.
• | Design Status: Green = Approved, Amber = In Progress, Red = Not Started.
• | Installation Status: Green = Installed, Amber = In Progress, Red = Not Installed, Grey = Removed.
• | Red flag on Permit to Load = “No” when Installation Status is “Installed” — this is a critical non-compliance.
• | Risk Level: Green = Low, Amber = Medium, Red = High.
Tips
• | BS 5975:2019 requires a formal temporary works register on every construction project. This template supports compliance but should be used alongside your project’s temporary works procedure.
• | Never load temporary works without a signed permit to load. The register flags this as a critical non-compliance if Permit to Load is “No” while Installation Status is “Installed”.
• | Review the register at every temporary works coordination meeting (typically fortnightly). Filter by Design Status to chase items awaiting approval.

## Temporary Works Register
TEMPORARY WORKS REGISTER |  |  |  | Total TW Items: | 5 |  | Awaiting Design Approval: | 1
|  |  |  | Design — Approved: | 2 | In Progress: | 1 | Not Started: | 0
|  |  |  | Install — Installed: | 3 | In Progress: | 1 | Removed: | 0
|  |  |  | Installed WITHOUT Permit: | 0 |  | High Risk Items: | 2
|  |  |  | Propping: | 1 | Falsework: | 1 | Formwork: | 0
▸ Optional Fields — Click [+] to expand
TW Ref No. | Date Raised | Description of Temporary Works | Location | Category | TW Coordinator | Design Check Req | Design Status | Installation Status | Permit to Load | Designer / Checker | Design Ref | Install Inspection Date | Dismantling Date | Risk Level | Notes
TW-001 | 2026-03-10 | Propping to slab S03 during demolition of internal wall W7 — 4No. Acrow props at 1.2m centres | Block A, Ground Floor, Grid B2–B5 | Propping | R. Thomas | Yes | Approved | Installed | Yes | J. Griffiths (Design) / A. Patel (Check) | TWD-001-Rev02 | 2026-03-14 |  | Medium | Props installed 14/03. Permit to load issued same day. Monitoring weekly.
TW-002 | 2026-03-12 | Falsework to in-situ concrete beam B12 — Peri Multiprop system, 8.2m span | Block B, Level 1, Grid C1–C4 | Falsework | R. Thomas | Yes | Approved | Installed | Yes | Peri Formwork (Design) / J. Griffiths (Check) | TWD-002-Rev01 | 2026-03-16 |  | High | Cat 3 temporary works. Design approved by TWC and independent checker. Pour scheduled 24/03.
TW-003 | 2026-03-15 | Temporary edge protection to lift shaft opening — steel handrail and mesh infill panels | Block A, Level 1–3, Lift Shaft LS-01 | Other | R. Thomas | No | N/A | Installed | Yes |  |  | 2026-03-15 |  | Low | Standard proprietary system. No bespoke design needed. Cat 1 item.
TW-004 | 2026-03-17 | Trench shoring to drainage excavation DR-05 — hydraulic drag boxes, 3.5m depth | Block C, External, Grid E1–E6 | Shoring | R. Thomas | Yes | In Progress | Not Installed | No | Mabey Hire (Design) | TWD-004-Draft |  |  | High | Design submitted 17/03. Checker review in progress. Excavation on hold until design approved and shoring installed.
TW-005 | 2026-03-18 | Site hoarding extension — 2.4m plywood hoarding along new south boundary, 45m run | South boundary, adjacent to public footpath | Hoarding | R. Thomas | No | N/A | In Progress | No |  |  |  |  | Low | Standard hoarding detail. Installation 60% complete. Wind loading check done by TWC — no formal design needed.

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.