## Cover
EBRORA
ebrora.com
Traffic Management Plan Checklist
A scored assessment checklist for construction site traffic management — with automatic compliance calculation and category-level RAG rating.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'TMP Checklist' sheet. Fill in the project details and inspection date at the top.
2. | The checklist contains 35 items across 7 categories. Score each item using the dropdown: 0 = Non-Compliant, 1 = Partial, 2 = Compliant, 3 = Exceeds Standard.
3. | Use N/A if an item doesn't apply to your site. N/A items are excluded from the percentage calculation.
4. | The compliance dashboard at the top auto-calculates: overall score percentage, a RAG rating, and per-category scores.
5. | Add actions or observations in the Action Required column for any item scoring 0 or 1.
6. | Complete the sign-off at the bottom. Re-inspect at least monthly, or after any significant change to site layout.
Scoring Guide
0 = Non-Compliant — Item is missing, defective, or not in place. Immediate action required.
1 = Partial — Item exists but doesn't fully meet requirements. Improvement needed.
2 = Compliant — Item meets the required standard.
3 = Exceeds — Item exceeds the minimum standard (best practice).
N/A = Not applicable to this site or inspection.
Colour Key
Green — Score 2 or 3 (Compliant / Exceeds). Category ≥75%.
Amber — Score 1 (Partial). Category 50–74%.
Red — Score 0 (Non-Compliant). Category <50%.
Tips
Tip 1: | Walk the full site perimeter and every pedestrian/vehicle route during the inspection. Don't assess from the site office — conditions change daily.
Tip 2: | Photograph any non-compliant items and reference the photo number in the Action column. Photographic evidence strengthens your audit trail.
Tip 3: | Share results with subcontractors at the next coordination meeting. Traffic management is everyone's responsibility, not just the principal contractor's.

## TMP Checklist
TRAFFIC MANAGEMENT PLAN — COMPLIANCE CHECKLIST
Project: | Riverside Gateway Phase 2 |  | Inspection Date: | 2026-03-22 | Rev: 03
Inspector: | S. Patel |  | Weather: | Dry, overcast
OVERALL SCORE: | 71.43% | RAG: | AMBER | Scored: | 35 / 35
Pedestrian: 67% ¦ Vehicle: 67% ¦ Signage: 60% ¦ Barriers: 73% ¦ Banksmen: 80% ¦ Docs: 73% ¦ Emergency: 80%
A. PEDESTRIAN ROUTES
1 | Designated pedestrian walkways clearly marked | 3
2 | Walkways separated from vehicle routes by physical barriers | 2
3 | Pedestrian routes adequately lit (including night works) | 2
4 | Step-free access where reasonably practicable | 1 | Step-free access blocked by material storage at Block B entrance | Site foreman | 2026-03-25
5 | Pedestrian crossings at vehicle route intersections | 2
B. VEHICLE ROUTES
6 | One-way system in operation where required | 2
7 | Speed limit signs displayed (typically 5-10 mph) | 2
8 | Road surface in good condition (no potholes, standing water) | 1 | Pothole forming near south gate turning circle — needs grading | Briggs GW | 2026-03-24
9 | Adequate turning/reversing areas provided | 2
10 | Vehicle routes wide enough for largest expected vehicle | 3
C. SIGNAGE & MARKINGS
11 | Site entrance signage visible from public highway | 3
12 | Internal directional signage at all junctions | 2
13 | Speed limit signs at regular intervals | 2
14 | Pedestrian route signs clearly visible | 2
15 | Hazard warning signs at blind corners / pinch points | 0 | No hazard warning sign at blind corner behind Block A — install immediately | S. Patel | 2026-03-23
D. BARRIERS & SEGREGATION
16 | Heras fencing / barriers separating pedestrians from vehicles | 2
17 | Barriers in good condition (not damaged, leaning, or missing) | 2
18 | Segregation maintained at loading/unloading areas | 3
19 | Protection at excavation edges near traffic routes | 2
20 | Public interface barriers and hoarding in place | 2
E. BANKSMEN & PERSONNEL
21 | Trained banksmen deployed at key locations | 3
22 | Banksmen wearing hi-vis and using standard hand signals | 3
23 | Reversing operations controlled by banksman | 2
24 | All personnel briefed on TMP via site induction | 2
25 | Emergency procedures understood by all traffic marshals | 2
F. DOCUMENTATION
26 | Written TMP available on site and up to date | 2
27 | TMP drawing displayed in site office | 2
28 | TMP included in site induction pack | 2
29 | Risk assessment for traffic management reviewed | 3
30 | Method statement for deliveries and vehicle movements | 2
G. EMERGENCY ACCESS
31 | Emergency vehicle access route maintained at all times | 3
32 | Fire assembly point accessible without crossing vehicle routes | 2
33 | Emergency access not blocked by parked vehicles or materials | 2
34 | Emergency route clearly signed and known to all personnel | 2
35 | Width of emergency route adequate (≥3.7m for fire appliance) | 3
SIGN-OFF
Inspected By: | S. Patel |  | Date: | 2026-03-22 | Signature:
Reviewed By: |  |  | Date: |  | Signature:
ebrora.com — Free professional construction management templates

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.