## Cover
EBRORA
ebrora.com
Emergency Drill
Tracker
Record and track emergency drills including fire musters,
confined space rescue, spill response, and first aid exercises.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Drill Tracker' sheet. Each row records one emergency drill or exercise.
2. | Enter the Drill Ref, Date, Drill Type (from dropdown), and Location/Scenario description.
3. | Record the number of participants, muster time (for fire drills), and the overall outcome: Pass, Partial, or Fail.
4. | Document findings and any corrective actions arising from the drill in the respective columns.
5. | Track the Next Due date for each drill type — typically quarterly for fire, 6-monthly for confined space rescue.
6. | Expand optional columns for weather conditions, observer name, photos, corrective action close-out, and linked risk assessment.
Colour Key
Light teal cells = Input
Green = Pass
Amber = Partial pass (issues noted but acceptable)
Red = Fail or overdue drill
Tips
Tip 1: | Vary drill scenarios — a fire muster from the same location every time teaches people one route, not emergency thinking.
Tip 2: | Confined space rescue drills must be realistic. Use the actual rescue equipment, the actual confined space, and time the extraction.
Tip 3: | Failed drills are valuable — they reveal gaps. Document the findings thoroughly and re-drill within 2 weeks after corrective actions.

## Drill Tracker
Drill Ref | Date | Drill Type | Location / Scenario | Participants | Muster Time | Outcome | Findings | Corrective Actions | Actions Closed | Next Due | Notes | Weather | Observer | Photo Ref | CA Close-Out Date | Linked RA Ref
ED-001 | 2026-01-08 | Fire Muster / Evacuation | Full site evacuation from compound and all work areas to Assembly Point A | 42 | 3 min 45 sec | Pass | All personnel accounted for within 4-minute target. Good response time. | None required | N/A | 2026-04-08 | Quarterly drill | Dry, 14°C | J. Davies | PHOTO-ED-001 |  | RA-FIRE-001
ED-002 | 2026-01-23 | Confined Space Rescue | Simulated casualty rescue from wet well at inlet pumping station. Tripod/winch extraction. | 8 | N/A | Pass | Rescue team extracted casualty in 6 minutes. All equipment functional. Comms clear. | Replace worn karabiner on rescue harness H-003 | Yes | 2026-07-22 | 6-monthly drill | Overcast, 11°C | M. Thompson | PHOTO-ED-002 | 2026-01-28 | RA-CS-003
ED-003 | 2026-02-12 | Spill Response | Simulated ferric chloride spill at chemical dosing kiosk. Deploy spill kit and containment. | 6 | N/A | Partial | Spill kit deployed correctly. However, one operative not wearing correct RPE. Bund drain valve left open initially. | 1) Retrain all chemical handlers on RPE requirements. 2) Add bund drain valve to pre-use checklist. | No | 2026-05-13 | Quarterly drill | Rain, 8°C | R. Evans | PHOTO-ED-003 |  | RA-COSHH-005
ED-004 | 2026-03-04 | First Aid Exercise | Simulated crush injury at pipe-laying trench. First aider response and ambulance call. | 4 | N/A | Pass | First aider on scene in 2 minutes. Correct assessment and treatment. 999 called with accurate location info. | Update emergency contact card with new site address | Yes | 2026-06-02 | Quarterly drill | Dry, 15°C | A. Khan |  |  | 2026-03-09 | RA-GEN-001
ED-005 | 2026-03-19 | Fire Muster / Evacuation | Unannounced night-shift evacuation. Reduced manning (12 personnel). | 12 | 2 min 50 sec | Pass | Excellent response despite dark conditions. All torches working. Assembly point lighting adequate. | None required | N/A | 2026-06-17 |  | Dry, dark, 6°C | J. Davies | PHOTO-ED-005 |  | RA-FIRE-001
SUMMARY | Total Drills: | 5 | Pass: | 4 | Partial/Fail: | 1 | Open Actions: | 1

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.