## Cover
EBRORA
ebrora.com
Concrete Works Daily Record
Record daily concrete pours with mix details, delivery tickets, slump results, volumes placed, and cube sample tracking.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Concrete Record' sheet. Each row is one delivery/load. The summary panel shows cumulative volume.
2. Enter the pour reference, date, element being poured, and the mix grade from the delivery ticket.
3. Record the delivery ticket number, load volume, and the batching plant details.
4. Enter the slump result on arrival. The template flags out-of-spec slumps (±25mm tolerance is typical).
5. Record whether cubes were taken from this load and the cube sample reference for traceability.
6. Volume Placed and Cumulative Volume track automatically. Overconsumption % shows actual vs theoretical volume.
7. Expand optional columns [+] for air temperature, concrete temperature, admixtures, and water additions.
8. Use this as a daily record — one sheet per day or per pour depending on your project's documentation requirements.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | Slump within tolerance / cubes taken
| Amber | Slump marginal or no cubes for this load
| Red | Slump out of spec — reject consideration
Tips
• Always check the delivery ticket matches the specified mix before accepting the load on site.
• Take slump tests from the first load and every 50m³ thereafter as a minimum — your spec may require more.
• Never add water to the mix on site unless authorised by the concrete supplier — it voids the design mix.

## Concrete Record
CONCRETE WORKS DAILY RECORD
Total Loads |  | Total Volume (m³) |  | Cubes Taken |  | Slump Passes |  | Slump Fails |  | Avg Slump (mm)
5 |  | 34 |  | 3 |  | 4 |  | 1 |  | 86
DATE / REF |  | DELIVERY DETAILS |  |  |  | QUALITY CHECKS |  |  |  | TRACKING |  |  |  | ▸ Optional — Conditions
Pour Ref | Date | Element / Location | Mix Grade | Ticket No. | Supplier / Plant | Load Vol (m³) | Slump (mm) | Target Slump (mm) | Slump OK? | Cubes Taken | Cube Ref | Cumul. Vol (m³) | Notes | Air Temp (°C) | Conc Temp (°C) | Admixtures | Water Added?
PC-001 | 2026-02-15 | Pad Foundation PF-01 | C30/37 | DT-44210 | Hanson Concrete — Theale | 6 | 80 | 75 | OK | Yes | CC-001 | 6 | First load — slump tested | 8 | 12 | None | No
PC-001 | 2026-02-15 | Pad Foundation PF-01 | C30/37 | DT-44211 | Hanson Concrete — Theale | 6 | 70 | 75 | OK | No |  | 12 |  | 8 | 13 | None | No
PC-001 | 2026-02-15 | Pad Foundation PF-01 | C30/37 | DT-44212 | Hanson Concrete — Theale | 6 | 85 | 75 | OK | Yes | CC-002 | 18 | Cubes taken at 12m³ | 9 | 14 | None | No
PC-002 | 2026-02-16 | Ground Floor Slab Bay 1 | C28/35 | DT-44225 | Hanson Concrete — Theale | 8 | 65 | 75 | OK | Yes | CC-003 | 26 | First load | 6 | 11 | Fibres 0.9kg/m³ | No
PC-002 | 2026-02-16 | Ground Floor Slab Bay 1 | C28/35 | DT-44226 | Hanson Concrete — Theale | 8 | 130 | 75 | REJECT | No |  | 34 | Slump high — load rejected, returned to plant | 7 | 15 | Fibres 0.9kg/m³ | No

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.