## Cover
EBRORA
ebrora.com
Formwork Inspection Checklist
Pre-pour formwork inspection checklist with scored categories, automatic overall assessment, and sign-off for concrete readiness.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Formwork Checklist' sheet. Fill in the project, element, and inspection details at the top.
2. The checklist is organised into 6 categories. Each check item has a Pass/Fail/N-A dropdown in column C.
3. Work through each item systematically — enter Pass, Fail, or N/A for every line.
4. Each category auto-calculates a section pass rate. Any single Fail blocks the category from achieving 100%.
5. The OVERALL ASSESSMENT at the bottom auto-calculates: READY TO POUR (all categories pass) or NOT READY.
6. Use the Comments column (D) to record any specific observations or defects found.
7. Sign off at the bottom — the inspector's name, date, and authorisation status.
8. Print as a single-page A4 portrait checklist for site use — the print area is pre-set.
Colour Key
| Light teal | Editable — select Pass/Fail/N-A or enter comments
| Dark navy | Headers and category bands
| Teal | Category section headers
| Green | Pass — item or category satisfactory
| Red | Fail — item or category has defects
Tips
• Complete this checklist BEFORE every pour — never pour concrete without a signed formwork inspection.
• If any item fails, stop and rectify before proceeding. A single failure should prevent the pour from being authorised.
• Keep completed checklists filed with the pour record — they form part of the quality evidence package.

## Formwork Checklist
FORMWORK INSPECTION CHECKLIST
Project:
Element:
Pour Ref:
Date:
Inspector:
No. | Inspection Item | Result | Comments | Section Score
ALIGNMENT & DIMENSIONS |  |  |  | 100%
1 | Formwork aligned to setting-out marks / survey positions | Pass
2 | Internal dimensions checked and match design drawings | Pass
3 | Formwork plumb (vertical elements checked with spirit level) | Pass
4 | Correct cover to reinforcement maintained on all faces | Pass
STRUCTURAL SUPPORT |  |  |  | 75%
5 | Props/falsework correctly positioned and tightened | Pass
6 | Base plates on solid bearing — no soft spots or voids | Pass
7 | Bracing adequate — no lateral movement when pushed | Fail | Bracing loose on south face — tighten before pour
8 | Proprietary formwork components correctly assembled per manufacturer guidance | Pass
JOINTS & SEALING |  |  |  | 100%
9 | All panel joints tight — no gaps that will cause grout loss | Pass
10 | Foam tape / sealant applied to construction joints | Pass
11 | Kicker joint sealed and kicker surface clean and damp | Pass
12 | Day joints / stop ends correctly positioned and secure | Pass
SURFACE & RELEASE AGENT |  |  |  | 100%
13 | Formwork faces clean — no debris, ice, or standing water | Pass
14 | Release agent applied evenly to all contact surfaces | Pass
15 | No contamination of reinforcement by release agent | Pass
16 | Tie holes / spacers correctly positioned and flush | Pass
INSERTS & EMBEDMENTS |  |  |  | 100%
17 | All cast-in items positioned per drawing (holding down bolts, sleeves, etc.) | Pass
18 | Blockouts / void formers secure and correctly located | Pass
19 | Waterstops correctly positioned at construction joints | N/A
SAFETY & ACCESS |  |  |  | 100%
20 | Safe access to pour point — platforms / scaffolding in place | Pass
21 | Edge protection around open formwork tops | Pass
22 | Sufficient lighting for the pour (if night work) | N/A
OVERALL ASSESSMENT |  |  |  | NOT READY
Inspector Name:
Signature: |  |  | Date:
Pour Authorised:

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.