## Cover
EBRORA
ebrora.com
Rebar Fixing Inspection Log
Record reinforcement fixing inspections with bar size, spacing, cover, and lap length verification against design drawings.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Rebar Inspection' sheet. The summary panel shows total inspections and pass/fail rates.
2. Enter each inspection with the element reference, drawing number, date, and the bar sizes/spacing specified.
3. Record the actual bar sizes and spacing found during inspection. Also record the measured cover and lap lengths.
4. The 'Bars OK', 'Spacing OK', 'Cover OK', and 'Laps OK' columns use Pass/Fail dropdowns for each check.
5. Overall Result auto-calculates: PASS (all four checks pass), FAIL (any check fails), or INCOMPLETE.
6. Any failed element must be corrected and re-inspected before the pour is authorised.
7. Expand optional columns [+] for MTC reference, tying wire check, spacer type, and congestion assessment.
8. Cross-reference this log with the formwork checklist — both must pass before concrete is placed.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | PASS — all checks satisfactory
| Red | FAIL — one or more checks failed
Tips
• Always check cover with a cover meter after fixing — spacers alone don't guarantee correct cover if displaced.
• Verify bar marks match the bending schedule — wrong bar shapes are a common cause of rebar rejection.
• Lap lengths vary by bar size and concrete grade — refer to the structural engineer's lap length schedule, not rules of thumb.

## Rebar Inspection
REBAR FIXING INSPECTION LOG
Total Inspections |  | Pass |  | Fail |  | Pass Rate |  | Outstanding |  | Completion %
5 |  | 3 |  | 2 |  | 60% |  | 0 |  | 100%
▸ Optional Fields — Click [+] to expand
Insp Ref | Date | Element | Drawing Ref | Bar Sizes (Specified) | Spacing (Specified) | Bars OK | Spacing OK | Cover OK | Laps OK | Overall Result | Inspector | Notes | MTC Ref | Tying Wire OK | Spacer Type | Congestion Assessment
RI-001 | 2026-02-10 | Pad Foundation PF-01 | RC-101 | T16 @ 200 c/c B.W. | 200 c/c | Pass | Pass | Pass | Pass | PASS | M. Evans | All checks satisfactory | MTC-005 | Pass | Concrete spacers | OK
RI-002 | 2026-02-12 | Ground Beam GB-01 | RC-102 | T20 top & btm, T10 links | 150 c/c links | Pass | Pass | Pass | Pass | PASS | M. Evans |  | MTC-005 | Pass | Plastic chairs | OK
RI-003 | 2026-02-13 | Column C4 | RC-103 | T25 main, T10 links @ 175 | 175 c/c | Pass | Fail | Pass | Pass | FAIL | J. Patel | Link spacing 220mm — too wide. Rectify. | MTC-005 | Pass | Plastic spacers | Tight
RI-004 | 2026-02-14 | Slab Bay 1 — Bottom Mat | RC-104 | T12 @ 200 c/c B.W. | 200 c/c | Pass | Pass | Pass | Pass | PASS | M. Evans |  | MTC-005 | Pass | Concrete spacers | OK
RI-005 | 2026-02-15 | Retaining Wall W2 — Face A | RC-106 | T16 vert @ 150, T12 horiz @ 200 | 150/200 | Pass | Pass | Fail | Pass | FAIL | J. Patel | Cover 22mm measured — spec requires 40mm min. Add spacers. | MTC-005 | Pass | Concrete spacers | OK

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.