## Cover
EBRORA
ebrora.com
WIS Log
Track every Work Inspection Sheet from issue through inspection, sign-off and close-out — maintain a complete quality record of all inspected works.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — WIS Log
Step-by-Step Instructions
1. | Go to the 'WIS Log' sheet. Enter the Project Name and Contract Number in the info strip at the top.
2. | Each WIS is automatically assigned a sequential reference (WIS-001, WIS-002, etc.) when a Description is entered in column C.
3. | Enter the Date Issued in column B — the date the WIS was raised and given to the inspection team.
4. | Enter a clear description of the work activity being inspected in column C. Be specific: include location, structure reference, or chainage.
5. | Select the Discipline from the dropdown in column D to allow filtering by trade or engineering discipline.
6. | Select the ITP Reference in column E — this links the WIS to the relevant hold/witness/review point in your Inspection & Test Plan.
7. | Set the WIS Type in column F: Hold Point (work cannot proceed without sign-off), Witness Point (inspector invited but work can proceed if no response), or Review Point.
8. | Enter the Inspection Date in column G when the physical inspection takes place. Column H calculates the number of days the WIS has been open.
9. | Use the Status dropdown (column I) to track progress. A WIS marked 'Failed' triggers a red row — raise an NCR and record it in column J.
10. | Record the Inspector's name in column K and any sign-off notes or outstanding actions in column L. Expand Optional Columns M–P for ITP pack reference, drawing number, location and file path.
Colour Key
Closed / Passed — Inspection complete, work accepted. No further action.
Failed — Inspection carried out. Work does not meet requirements. NCR raised.
Inspection Due — WIS issued and waiting for the inspection to take place.
Open — WIS issued. Hold Point: work cannot proceed.
Cancelled — WIS formally withdrawn (e.g., scope changed before inspection).
Light teal cells — User input / editable fields.
Dark navy header rows — Do not edit.
Tips
* | Never close a WIS without a physical inspection having taken place. A WIS closed on paper without a site visit is a quality failure and an audit liability. The inspector's signature on the WIS document is the evidence.
* | For Hold Points, work must physically stop until the WIS is signed off by the Employer's Representative. If the ER does not attend within the notified period (typically 24–48 hours under the ITP), the contractor can proceed but must record the ER no-show.
* | Link each WIS back to the ITP pack number (Optional Column M). At handover, you'll need to demonstrate that every hold/witness point was addressed — a complete WIS log mapped to the ITP pack is the cleanest way to do that.

## WIS Log
Project Name: |  | [Enter Project Name] |  |  |  | Contract No: |  | [Contract No] |  |  |  | ▸ Optional Fields — Click [+] to expand
WIS Ref | Date Issued | Work Activity / Description | Discipline | ITP Reference | WIS Type | Inspection Date | Days Open | Status | NCR Ref | Inspector | Notes / Sign-Off Comments | ITP Pack Ref | Drawing No. | Location / Chainage | File Path / Link
WIS-001 | 2025-01-13 | Blinding & Kicker to Primary Tank Base Slab — Grid A1–A4 | Civil | ITP-CV-001 HP-03 | Hold Point | 2025-01-15 |  | Closed |  | J. Hargreaves | Blinding level +/- 5mm. Kicker aligned. ER signed off 15/01. | CV-ITP-001 | WRC-ST-0003 Rev C | Primary Tank Formation Ch0+100
WIS-002 | 2025-01-22 | Reinforcement Fix & Inspection — Primary Tank Walls, 1st Lift | Structural | ITP-ST-002 HP-01 | Hold Point | 2025-01-24 | 426 | Passed |  | S. Patel | Cover confirmed 50mm. Laps correct. Starter bars clean. ER attended. | ST-ITP-002 | WRC-ST-0004 Rev B | Primary Tank Walls Grid B1–B4
WIS-003 | 2025-02-04 | Pipe Laying — DN300 DI Inlet Main, Zone 3, Ch0+050 to Ch0+120 | Civil | ITP-CV-003 WP-02 | Witness Point | 2025-02-06 |  | Closed |  | T. Walsh | Bedding depth 150mm as specified. Jointing checked. ER not in attendance — notice given. | CV-ITP-003 | WRC-CV-0001 Rev C | Zone 3 Inlet Main
WIS-004 | 2025-02-18 | Formwork Inspection — Inlet Chamber Walls, 2nd Pour | Structural | ITP-ST-002 HP-02 | Hold Point |  | 399 | Inspection Due |  |  | Hold Point — awaiting ER availability to attend. Concrete pour booked 25/02. | ST-ITP-002 | WRC-ST-0005 Rev A | Inlet Chamber
WIS-005 | 2025-03-01 | HDPE Duct Laying — 110mm Cable Duct, Route MCC to FCV-201 | Electrical | ITP-EL-004 WP-01 | Witness Point | 2025-03-03 | 388 | Failed | NCR-031 | C. Roberts | Duct depth insufficient in three locations — min cover 600mm not achieved. NCR-031 raised. | EL-ITP-004 | WRC-EL-0011 Rev A | MCC to FCV-201 route
TOTAL | 5 | CLOSED/PASSED | 3 | INSPECTION DUE | 1 | ISSUED (OPEN) | 0 | FAILED | 1 | NCRs LINKED | 1 | HOLD POINTS | 3
Formulas:
Days Open = IF(AND([Date Issued]<>"",[Status]<>"Closed",[Status]<>"Cancelled"),TODAY()-[Date Issued],"")

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.