## Cover
EBRORA
ebrora.com
Kerbing & Drainage Progress Log
Track kerbing and linear drainage installation progress with automatic meterage calculations, alignment checks, and backfill status.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Kerb & Drainage Log' sheet. The summary shows total planned vs installed metres.
2. Enter each kerb or drainage run with its reference, type, and design length (m).
3. As installation progresses, update the 'Installed (m)' column. % Complete auto-calculates.
4. Record the alignment check result (Pass/Fail) and the backfill/haunching status.
5. Status auto-calculates: COMPLETE (100% + alignment pass + backfill done), IN PROGRESS, or NOT STARTED.
6. The Running Total column tracks cumulative installed metres across all runs.
7. Expand optional columns [+] for bedding spec, joint type, and as-built level check.
8. Use this alongside the road layer tracker for a full picture of external works progress.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | Complete / Pass
| Amber | In Progress / Partial
| Red | Not Started / Fail
Tips
• Check kerb line and level against design every 10m — small alignment errors compound over long runs.
• Haunching must be complete before trafficking — unsupported kerbs will shift under vehicle loads.
• Record channel/slot drain runs separately from kerbs — they have different installation and testing requirements.

## Kerb & Drainage Log
KERBING & DRAINAGE PROGRESS LOG
Planned (m) |  | Installed (m) |  | Overall % |  | Runs Complete |  | Alignment Passed |  | Runs
380 |  | 280 |  | 73.68% |  | 2 |  | 3 |  | 5
▸ Optional Fields — Click [+] to expand
Run Ref | Type | Location / Description | Design Length (m) | Installed (m) | % Complete | Running Total (m) | Alignment Check | Backfill / Haunching | Status | Date | Notes | Bedding Spec | Joint Type | Level Check
KR-01 | HB2 Kerb | Main Access Road — LHS | 120 | 85 | 70.83% | 85 | Pass | Partial | IN PROGRESS | 2026-02-15 | Haunching 60% done | C20 Concrete | Mortar | Pass
KR-02 | HB2 Kerb | Main Access Road — RHS | 120 | 120 | 100% | 205 | Pass | Complete | COMPLETE | 2026-02-18 | Complete — signed off | C20 Concrete | Mortar | Pass
KR-03 | BN Bullnose | Car Park Island 1 | 45 | 45 | 100% | 250 | Pass | Complete | COMPLETE | 2026-02-20 |  | C20 Concrete | Mortar | Pass
KR-04 | Channel Block | Car Park — Bay Drainage | 80 | 30 | 37.5% | 280 | Pending | Not Started | IN PROGRESS | 2026-02-22 | Alignment check pending | C20 Concrete | Butt
KR-05 | Slot Drain | Service Yard Entrance | 15 | 0 | 0% | 280 |  | Not Started | NOT STARTED |  | Awaiting materials

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.