## Cover
EBRORA
ebrora.com
Backfill Material Approval Register
Track backfill material sources through sampling, testing, and formal approval with automatic status and review age tracking.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Material Approvals' sheet. The summary shows approval status breakdown and pending items.
2. Enter each material source with its description, supplier/quarry, intended use, and SHW classification.
3. Record the date the sample was submitted for testing and the lab reference number.
4. When test results return, enter the date received and the test outcome (Compliant/Non-Compliant).
5. The approval status is set manually by the engineer: Approved, Rejected, Conditional, or Pending.
6. 'Days Since Submission' auto-calculates — pending items over 14 days highlight amber, over 21 days red.
7. Expand optional columns [+] for PSD results, MCV, CBR, chemical analysis, and source location.
8. Never use a material on site until it appears as 'Approved' on this register.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | Approved — material cleared for use
| Amber | Conditional or Pending review
| Red | Rejected — do not use
Tips
• SHW classifications: Class 1 (general), Class 2 (cohesive), Class 6 (capping) — always match to your earthworks spec.
• Re-test material if the source changes or if the quarry face moves to a different stratum.
• Keep original lab test certificates filed alongside this register for audit and adoption purposes.

## Material Approvals
BACKFILL MATERIAL APPROVAL REGISTER
Total Sources |  | Approved |  | Pending |  | Rejected |  | Conditional |  | Approval Rate
5 |  | 3 |  | 1 |  | 1 |  | 0 |  | 60%
▸ Optional Fields — Click [+] to expand
Mat. Ref | Material Description | Supplier / Quarry | Intended Use | SHW Class | Date Submitted | Lab Ref | Results Date | Test Outcome | Approval Status | Days Since Submission | Notes | PSD Result | MCV | CBR (%) | Source Location
BF-001 | Granular fill — 6F5 recycled aggregate | Smiths Recycling, Theale | Pipe bedding & surround | Type 1 Sub-base | 2026-02-01 | LAB-5501 | 2026-02-08 | Compliant | Approved | 7 | PSD within SHW limits | Well graded | N/A | N/A | SP 6543 7123
BF-002 | Cohesive fill — brown sandy clay | Site-won (Zone A strip) | General backfill | Class 2 | 2026-02-05 | LAB-5510 | 2026-02-14 | Compliant | Approved | 9 | MCV 12 — suitable | N/A | 12 | N/A | On-site stockpile
BF-003 | Type 1 sub-base — limestone | Hanson Quarry, Whatley | Road sub-base layer | Type 1 Sub-base | 2026-02-10 | LAB-5520 | 2026-02-18 | Compliant | Approved | 8 |  | Well graded | N/A | 85 | BA5 2QA
BF-004 | Capping layer — Class 6N | J Murphy Recycling | Capping below sub-base | Class 6 | 2026-02-15 | LAB-5535 |  | Awaiting | Pending | 36 | Results expected 28/02 |  |  |  | RG7 4SA
BF-005 | Sandy gravel — imported | Unknown quarry | Trench backfill | Class 1 | 2026-02-12 | LAB-5528 | 2026-02-20 | Non-Compliant | Rejected | 8 | Excessive fines — 35% passing 63µm. Rejected. | Poorly graded | 8 | 15 | Unknown
Formulas:
Approval Rate = IF([Date Submitted]="","",IF([Results Date]<>"",[Results Date]-[Date Submitted],TODAY()-[Date Submitted]))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.