## Cover
EBRORA
ebrora.com
Geotextile / Membrane Installation Record
Record geotextile and membrane installations with panel tracking, overlap verification, seam testing, and coverage calculations.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Installation Record' sheet. The summary shows total coverage area and pass/fail rates.
2. Enter each panel/roll with its reference, date installed, membrane type, and location/zone.
3. Record the panel dimensions (length × width) — the area auto-calculates in m².
4. Check and record overlap widths. The template flags overlaps below the minimum specified (typically 150mm).
5. For welded membranes, record the seam test result (Pass/Fail) and test method (air lance, vacuum box, etc.).
6. Overall Result auto-calculates: PASS (overlap OK + seam OK), FAIL (either fails), or N/A (no seam test needed).
7. Expand optional columns [+] for roll/batch number, MTC reference, weather conditions, and installer details.
8. Running Total Area tracks cumulative m² installed across all panels.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | PASS — overlap and seam satisfactory
| Amber | Overlap marginal (100–149mm)
| Red | FAIL — overlap below minimum or seam failed
Tips
• Never install geomembranes in wet or windy conditions — moisture prevents proper welding and wind lifts loose panels.
• Minimum overlap for separation geotextiles is typically 300mm; for HDPE liners it's 150mm welded — always check your spec.
• Photograph each panel layout before covering — this provides evidence of overlap and seam positions for the QA file.

## Installation Record
GEOTEXTILE / MEMBRANE INSTALLATION RECORD
Total Area (m²) |  | Panels Installed |  | Pass |  | Fail |  | Pass Rate |  | Seams Tested
447.5 |  | 5 |  | 4 |  | 0 |  | 100% |  | 5
▸ Optional Fields — Click [+] to expand
Panel Ref | Date | Membrane Type | Location / Zone | Length (m) | Width (m) | Area (m²) | Min Overlap Spec (mm) | Actual Overlap (mm) | Overlap OK? | Seam Test Method | Seam Result | Overall Result | Running Total (m²) | Notes | Roll / Batch No | MTC Ref | Weather | Installer
GT-001 | 2026-02-10 | Separation Geotextile | Attenuation Basin — Base | 25 | 4.5 | 112.5 | 300 | 350 | OK | N/A | N/A | PASS | 112.5 | Terram 1000 — separation only | R-4421 | MTC-GT-01 | Dry, calm | ABC Civils
GT-002 | 2026-02-10 | HDPE Liner | Attenuation Basin — Base Panel 1 | 20 | 5 | 100 | 150 | 160 | OK | Air Lance | Pass | PASS | 212.5 | 1.5mm HDPE — factory welded seam tested | R-4422 | MTC-HD-01 | Dry, calm | Specialist Linings Ltd
GT-003 | 2026-02-11 | HDPE Liner | Attenuation Basin — Base Panel 2 | 20 | 5 | 100 | 150 | 155 | OK | Air Lance | Pass | PASS | 312.5 |  | R-4423 | MTC-HD-01 | Dry, calm | Specialist Linings Ltd
GT-004 | 2026-02-11 | HDPE Liner | Attenuation Basin — Side Panel 1 | 15 | 5 | 75 | 150 | 180 | OK | Vacuum Box | Pass | PASS | 387.5 | Side slope — anchored at crest | R-4424 | MTC-HD-01 | Light breeze | Specialist Linings Ltd
GT-005 | 2026-02-12 | Filter Geotextile | French Drain — Zone B | 30 | 2 | 60 | 300 | 250 | MARGINAL | N/A | N/A | PENDING | 447.5 | Overlap below spec — re-lay required | R-4425 | MTC-GT-02 | Dry | ABC Civils
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.