## Cover
EBRORA
ebrora.com
Piling Record Sheet
Record driven or bored pile installation data with automatic depth variance, set compliance, and integrity test tracking.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Piling Record' sheet. The summary panel shows total piles planned, installed, and compliance statistics.
2. Enter each pile with its reference, date installed, pile type, design length, and design toe level.
3. After installation, record the actual installed length and the actual toe level achieved.
4. Depth Variance (m) auto-calculates: actual toe minus design toe. Positive = deeper than required (good for driven piles).
5. For driven piles, enter the final set reading (mm per blow) — the template checks against the target set.
6. Overall Status auto-calculates based on depth compliance and set criteria: COMPLIANT, REVIEW, or NON-COMPLIANT.
7. Expand optional columns [+] for rig type, hammer energy, concrete volume (CFA/bored), and integrity test results.
8. Filter by status to identify problem piles requiring engineer review or remedial action.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | COMPLIANT — meets design requirements
| Amber | REVIEW — marginal, needs engineer check
| Red | NON-COMPLIANT — does not meet spec
Tips
• Record pile data in real-time during installation — don't rely on memory at the end of the shift.
• For CFA piles, monitor concrete overconsumption (actual vs theoretical volume) — >20% excess may indicate ground loss.
• Always cross-reference this log with the pile integrity test results when they come back — flag any anomalies immediately.

## Piling Record
PILING RECORD SHEET
Total Planned |  | Installed |  | Compliant |  | Review |  | Non-Compliant |  | Compliance %
5 |  | 5 |  | 4 |  | 0 |  | 1 |  | 80%
Progress: 100% installed ¦ Avg depth variance: 0.02m
▸ Optional Fields — Click [+] to expand
Pile Ref | Date | Pile Type | Design Length (m) | Design Toe Level (m) | Actual Length (m) | Actual Toe Level (m) | Depth Variance (m) | Target Set (mm/blow) | Actual Set (mm/blow) | Set OK? | Overall Status | Notes | Rig Type | Hammer Energy (kJ) | Concrete Vol (m³) | Integrity Test
P-001 | 2026-02-10 | Driven Precast | 12 | 30.15 | 12.3 | 29.85 | -0.3 | 25 | 22 | OK | COMPLIANT | Achieved set at 12.3m | Junttan PM25 | 60 |  | Pass
P-002 | 2026-02-10 | Driven Precast | 12 | 30.15 | 11.8 | 30.35 | 0.2 | 25 | 24 | OK | COMPLIANT | Slightly short — within tolerance | Junttan PM25 | 60 |  | Pass
P-003 | 2026-02-11 | CFA (Bored) | 15 | 27.15 | 15.2 | 26.95 | -0.2 |  |  |  | COMPLIANT | CFA — no set reading | Soilmec SR-40 |  | 8.5 | Awaiting
P-004 | 2026-02-11 | Driven Precast | 12 | 30.15 | 10.5 | 31.65 | 1.5 | 25 | 35 | HIGH | NON-COMPLIANT | Refused early — high set. Engineer review needed | Junttan PM25 | 60 |  | Defect Found
P-005 | 2026-02-12 | Driven Precast | 12 | 30.15 | 12.1 | 30.05 | -0.1 | 25 | 20 | OK | COMPLIANT | Good installation | Junttan PM25 | 60 |  | Pass
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.