## Cover
EBRORA
ebrora.com
Reinstatement Works Tracker
Track reinstatement of excavations through every stage from dig to sign-off — with NRSWA compliance tracking, defect liability monitoring, and days-remaining alerts.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Reinstatement Tracker' sheet. The pipeline summary at the top shows how many reinstatements are at each stage — from Excavated through to Signed Off.
2. | Each row tracks one excavation/reinstatement. Enter the Ref, Location, Works Type, and Permit Reference.
3. | Set the Current Stage using the dropdown. The six stages are: Excavated, Backfilled, Temp Reinstatement, Perm Reinstatement, Inspected, Signed Off.
4. | Enter the Excavation Date and Target Completion. The 'Days Remaining' column calculates automatically and highlights red when overdue.
5. | Expand optional columns for backfill material, compaction test results, surface type, final inspection date, defect liability end date, and cost.
6. | Under NRSWA, you typically have specific timeframes for interim and permanent reinstatement. Use this tracker to ensure you don't miss those deadlines.
Stage Pipeline
1. Excavated — Dig complete, works in progress. (Red tint)
2. Backfilled — Excavation backfilled and compacted. (Orange tint)
3. Temp Reinstatement — Temporary surface applied. (Yellow tint)
4. Perm Reinstatement — Permanent surface laid. (Green tint)
5. Inspected — Final inspection completed. (Blue tint)
6. Signed Off — Accepted by authority / client. (Purple tint)
Tips
Tip 1: | Under NRSWA Section 71, interim reinstatement must typically be completed within a set period after backfilling. Use the Target Completion date to track this — overdue reinstatements attract penalty charges from the highway authority.
Tip 2: | Filter by Current Stage = 'Temp Reinstatement' to identify all sites waiting for permanent reinstatement. Programme these into your look-ahead to avoid a backlog.
Tip 3: | The Defect Liability End date in the optional columns tracks the guarantee period (typically 2–3 years for permanent reinstatements). Set a reminder to inspect before this date expires.

## Reinstatement Tracker
REINSTATEMENT WORKS TRACKER
Project: | Riverside Gateway — Highways Works |  | Authority: | Salford City Council Highways |  | Updated: | 2026-03-22
PIPELINE SUMMARY | [8 empty] | Overdue:
Excavated |  | Backfilled | Temp Reinstatement |  | Perm Reinstatement | Inspected |  | Signed Off | 0
1 |  | 1 | 1 |  | 1 | 1 |  | 1
Ref | Location / Street | Works Type | Permit Ref | Excavation Date | Current Stage | Target Completion | Responsible | Days Remaining | ▸ Optional Fields — Click [+] to expand
RW-001 | Regent Road — outside No. 42-48 | Carriageway | SP-2026-0441 | 2026-02-10 | Perm Reinstatement | 2026-04-10 | Briggs GW | 19 | Type 1 sub-base + AC20 | Pass | Asphalt |  |  | 3200
RW-002 | Chapel Street — junction with Irwell St | Footway | SP-2026-0442 | 2026-02-18 | Temp Reinstatement | 2026-03-30 | Briggs GW | 8 | Type 1 sub-base | Pass | Cold-lay tarmac (temp) |  |  | 850
RW-003 | Irwell Street — northbound lane | Carriageway | SP-2026-0443 | 2026-03-01 | Backfilled | 2026-03-25 | Briggs GW | 3 | 6F5 recycled aggregate | Pending
RW-004 | Site access road — south gate verge | Verge | N/A (private) | 2026-03-05 | Excavated | 2026-04-05 | Site team | 14 |  |  | Topsoil/Turf
RW-005 | Regent Road — service trench (gas) | Service Trench | SP-2026-0445 | 2026-01-20 | Signed Off | 2026-03-20 | Cadent Gas |  | Type 1 + sand surround | Pass | Asphalt | 2026-03-15 | 2028-03-15 | 4100
RW-006 | Chapel Street — footway crossing reinstatement | Footway | SP-2026-0446 | 2026-02-25 | Inspected | 2026-03-25 | Briggs GW | 3 | Type 1 sub-base | Pass | Flags | 2026-03-20 | 2028-03-20 | 1650
Formulas:
Days Remaining = IF(AND([Updated:]<>"",[Current Stage]<>"Signed Off"),[Updated:]-TODAY(),"")

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.