## Cover
EBRORA
ebrora.com
Road / Pavement Layer Tracker
Track pavement construction progress layer by layer across road sections with automatic completion calculations and area totals.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Layer Tracker' sheet. Each row is a road section; columns represent pavement layers from bottom to top.
2. Enter the section reference, description, chainage, and total area (m²) for each section.
3. For each layer (Subgrade to Surface Course), select the status: Complete, In Progress, Not Started, or N/A.
4. The Section % column auto-calculates based on how many applicable layers are complete (excluding N/A).
5. The summary panel shows total area, area by layer completion stage, and overall programme progress.
6. Use the teal layer-band header to see which construction phase the project is primarily in.
7. Expand optional columns [+] for layer thickness checks, compaction test refs, and material cert refs.
8. Update weekly — this gives a clear visual of road construction progress for programme reporting.
Colour Key
| Light teal | Editable — select layer status
| Dark navy | Headers
| Green | Complete — layer finished
| Amber | In Progress — layer partially done
| Red | Not Started — layer not begun
Tips
• Each layer must be tested and approved before the next is laid — don't mark layers complete without compaction/level sign-off.
• Mark layers N/A where the pavement design doesn't include them (e.g. no capping on rock subgrade).
• Use this alongside the compaction test register to ensure every section has test coverage at every layer.

## Layer Tracker
ROAD / PAVEMENT LAYER TRACKER
Total Area (m²) |  | Sections |  | Fully Complete |  | In Progress |  | Not Started |  | Overall %
4410 |  | 5 |  | 0 |  | 4 |  | 27 |  | 6.559%
Layer Progress: Subgrade 80% ¦ Sub-base 60% ¦ Base 20% ¦ Surface 0%
SECTION IDENTIFICATION |  |  |  |  | PAVEMENT LAYER STATUS (bottom → top) | [5 empty] | PROGRESS |  | ▸ Optional
Section Ref | Description | Ch From | Ch To | Area (m²) | Subgrade | Capping | Sub-base | Base Course | Binder Course | Surface Course | Section % | Notes | Thickness Check | Compaction Ref | Material Cert
RD-01 | Main Access Road — Section 1 | 0+000 | 0+120 | 840 | Complete | Complete | Complete | In Progress | Not Started | Not Started | 50% | Base course laying in progress | OK | CT-003 | MTC-Agg-01
RD-02 | Main Access Road — Section 2 | 0+120 | 0+250 | 910 | Complete | Complete | In Progress | Not Started | Not Started | Not Started | 33.33% | Sub-base 50% laid | OK | CT-004 | MTC-Agg-01
RD-03 | Car Park Area A | N/A | N/A | 1200 | Complete | N/A | Complete | Complete | Complete | In Progress | 80% | Surface course scheduled next week | OK | CT-005 | MTC-Agg-02
RD-04 | Car Park Area B | N/A | N/A | 950 | Complete | N/A | Complete | Not Started | Not Started | Not Started | 40% | Awaiting base course material delivery
RD-05 | Service Road — Loop | 0+000 | 0+085 | 510 | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 0% | Utility crossings still outstanding
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.