## Cover
EBRORA
ebrora.com
Cashflow Forecast
vs Actual
Monthly S-curve cashflow tracking with planned, actual, and forecast spend
including cumulative totals and variance analysis.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Cashflow' sheet. The top section is a financial summary; the data grid below tracks monthly spend.
2. | Enter the Contract Value in cell C3 (light teal = input cell).
3. | The grid has 6 rows of data across 12 monthly columns: Planned Spend, Actual Spend, Forecast Spend, then cumulative versions of each.
4. | Enter Planned Monthly Spend values from your baseline programme/cost plan.
5. | Enter Actual Monthly Spend as each month is certified/paid.
6. | Enter Forecast Monthly Spend for future months (your best estimate of what's still to come).
7. | Cumulative rows auto-calculate as running totals — these form your S-curve data.
8. | The Variance section at the bottom shows monthly and cumulative differences between Planned and Actual.
9. | The financial summary auto-updates with total spend, remaining budget, and % spent.
Colour Key
Light teal cells (#E8F6F7) = User input / editable fields
Dark navy headers = Do not edit
White cells = Auto-calculated formulas
Green variance = Under-spend (actual < planned)
Red variance = Over-spend (actual > planned)
Tips
Tip 1: | Update actual spend monthly, on the same day as your valuation. Consistency makes trends visible.
Tip 2: | Use the cumulative rows to plot an S-curve chart in Excel — select Cum. Planned, Cum. Actual, and Cum. Forecast and insert a line chart.
Tip 3: | The monthly variance row is your early warning system. Two consecutive red months means the cost plan needs re-baselining.

## Cashflow
Cashflow Forecast vs Actual
Contract Value: | 2850000 |  | Total Planned: | 2700000 |  | Total Actual to Date: | 913000
Remaining Budget: | 1937000 |  | % Spent: | 32.04% |  | Variance (Plan vs Actual): | 1787000
▼ Monthly Cashflow Data
| Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Total
Planned Monthly Spend | 120000 | 180000 | 250000 | 320000 | 350000 | 310000 | 280000 | 240000 | 200000 | 180000 | 150000 | 120000 | 2700000
Actual Monthly Spend | 115000 | 195000 | 268000 | 335000 | [8 empty] | 913000
Forecast Monthly Spend | 115000 | 195000 | 268000 | 335000 | 360000 | 325000 | 290000 | 245000 | 210000 | 185000 | 155000 | 125000 | 2808000
Cumulative Planned | 120000 | 300000 | 550000 | 870000 | 1220000 | 1530000 | 1810000 | 2050000 | 2250000 | 2430000 | 2580000 | 2700000 | 2700000
Cumulative Actual | 115000 | 310000 | 578000 | 913000 | 913000 | 913000 | 913000 | 913000 | 913000 | 913000 | 913000 | 913000 | 913000
Cumulative Forecast | 115000 | 310000 | 578000 | 913000 | 1273000 | 1598000 | 1888000 | 2133000 | 2343000 | 2528000 | 2683000 | 2808000 | 2808000
Monthly Variance (Plan - Actual) | 5000 | -15000 | -18000 | -15000 | 350000 | 310000 | 280000 | 240000 | 200000 | 180000 | 150000 | 120000 | 1787000
Cumulative Variance | 5000 | -10000 | -28000 | -43000 | 307000 | 617000 | 897000 | 1137000 | 1337000 | 1517000 | 1667000 | 1787000 | 1787000

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.