## Cover
EBRORA
ebrora.com
Cost-to-Complete Forecast
Time-phased monthly cost forecast with EAC calculation,
variance tracking, and cumulative spend projections by category.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Cost Forecast' sheet. The top section shows the project-level EAC (Estimate at Completion) summary: Budget, Spent to Date, Committed, Cost to Complete, EAC, and Variance.
2. | The main section is a time-phased monthly forecast grid. Each row is a cost category. The left columns (A–H) show the financial summary; the right columns (I onwards) show the forecast monthly spend for the next 12 months.
3. | For each category, enter the Budget (£), Spent to Date (£), and Committed (£) in the light teal cells. Then enter your forecast spend for each future month across the grid.
4. | Cost to Complete = sum of all monthly forecast values. EAC = Spent to Date + Cost to Complete. Variance = Budget – EAC. These all calculate automatically.
5. | The bottom rows contain a Monthly Total (sum of all categories per month) and a Cumulative Total (running total across months) for S-curve reporting.
Layout Explanation
6. | The left fixed columns (A–H) summarise the overall financial position per category. The scrollable right section (I onwards) contains the monthly forecast grid. Freeze panes keep the left columns visible as you scroll.
7. | Update the month headers (row 12) to match your project’s remaining programme. The template defaults to a 12-month forward view.
Colour Key
Light teal cells (#E8F6F7) — User input (budgets, actuals, monthly forecasts).
Dark navy headers — Do not edit.
Teal band rows — Category section headers.
Grey rows — Totals and cumulative rows with formulas.
Green variance — Underspend (EAC below budget).
Red variance — Overspend (EAC exceeds budget).
Amber % Complete — 80–99% of budget committed or spent.
Tips
Tip 1: | Update this forecast monthly. Carry forward any unspent forecast from the current month into the next — don’t just delete it or the CTC will understate.
Tip 2: | The cumulative row at the bottom is your forecast cashflow curve. Use it to plot an S-curve against the original programme cashflow for earned value reporting.
Tip 3: | Cross-reference the Budget column with your Budget vs Actual tracker (Template 59) and the Committed column with your Invoice Tracker (Template 60) for a consistent cost position.

## Cost Forecast
COST-TO-COMPLETE FORECAST — TIME-PHASED MONTHLY GRID
Total Budget (£) |  | Spent to Date (£) |  | Committed (£) |  | MONTHLY FORECAST PERIOD
3724000 |  | 1897000 |  | 1185700 |  | Apr 2026 → Mar 2027 Enter forecast spend per category per month in the grid below. Cost to Complete and EAC update automatically.
Cost to Complete (£) |  | EAC (£) |  | Variance (Budget – EAC)
740500 |  | 2637500 |  | 1086500
FINANCIAL SUMMARY | [7 empty] | FORECAST MONTHLY SPEND (£)
Cost Code | Category | Budget (£) | Spent to Date (£) | Committed (£) | Cost to Complete (£) | EAC (£) | Variance (£) | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Total Forecast (£)
1.0 | Preliminaries | 496000 | 350000 | 139200 | 109000 | 459000 | 37000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 10000 | 8000 | 5000 | 2000 | 0 | 109000
2.0 | Substructure | 590000 | 553000 | 20500 | 16500 | 569500 | 20500 | 8000 | 5000 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500
3.0 | Superstructure | 1180000 | 702000 | 328000 | 150000 | 852000 | 328000 | 42000 | 38000 | 35000 | 25000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
4.0 | M&E Services | 865000 | 235000 | 558000 | 342000 | 577000 | 288000 | 18000 | 25000 | 35000 | 42000 | 48000 | 55000 | 45000 | 35000 | 22000 | 12000 | 5000 | 0 | 342000
5.0 | External Works | 218000 | 15000 | 140000 | 123000 | 138000 | 80000 | 0 | 0 | 5000 | 10000 | 18000 | 22000 | 25000 | 20000 | 12000 | 8000 | 3000 | 0 | 123000
6.0 | Contingency & Risk | 375000 | 42000 | 0 | 0 | 42000 | 333000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | [12 empty] | 0
[5 empty] | 0 | 0 | 0 | [12 empty] | 0
[5 empty] | 0 | 0 | 0 | [12 empty] | 0
[5 empty] | 0 | 0 | 0 | [12 empty] | 0
| PROJECT TOTAL | 3724000 | 1897000 | 1185700 | 740500 | 2637500 | 1086500 | 80000 | 80000 | 90500 | 89000 | 88000 | 89000 | 82000 | 65000 | 42000 | 25000 | 10000 | 0 | 740500
| CUMULATIVE TOTAL | [6 empty] | 1977000 | 2057000 | 2147500 | 2236500 | 2324500 | 2413500 | 2495500 | 2560500 | 2602500 | 2627500 | 2637500 | 2637500 | 2637500

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.