## Cover
EBRORA
ebrora.com
Daywork Sheet
Record labour, plant, and materials for daywork activities
with automatic cost calculation and on-cost percentages.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Daywork Sheet' tab. Fill in the header block first: project name, contractor, daywork sheet number, date, location on site, and a description of the work carried out.
2. | The sheet has three sections — Labour, Plant, and Materials. Each is a mini-table with its own columns and a subtotal row.
3. | In the Labour section, enter each operative’s name, trade, hours worked (normal and overtime), and their hourly rates. The Amount column calculates automatically.
4. | In the Plant section, enter each item of plant, the hours or days used, and the rate. Amount calculates automatically.
5. | In the Materials section, enter each material, quantity, unit, and unit rate. Amount calculates automatically.
6. | The Cost Summary at the bottom totals all three sections, adds the on-cost/overhead percentage (editable, default 12.5%), and calculates the Total Daywork Value including VAT.
Sign-Off
7. | Both the contractor’s representative and the employer’s/CA’s representative should sign and date the sheet. Daywork must be agreed on the day or as close to the event as possible.
8. | Unsigned or late daywork sheets are one of the most common reasons claims are rejected at final account.
Colour Key
Light teal cells (#E8F6F7) — User input. Enter your data here.
Dark navy headers — Do not edit. Section headers.
Teal section banners — Labour / Plant / Materials section markers.
Grey rows — Subtotal and calculation rows with formulas.
Tips
Tip 1: | Complete and get signatures on the same day the work is done. Under most standard forms (JCT, NEC), daywork must be verified promptly to be valid.
Tip 2: | Photograph the daywork activity and attach the photo reference to the sheet. This provides evidence if the daywork is later disputed.
Tip 3: | Cross-reference the daywork sheet number against your Variation Order Register — daywork often supports or evidences a VO claim.

## Daywork Sheet
DAYWORK SHEET
Project Name: |  | Riverside Business Park — Phase 2 |  | Daywork Sheet No: | DW-027
Main Contractor: |  | Kier Construction Ltd |  | Date: | 2026-02-18
Subcontractor: |  | McCann Electrical Ltd |  | Instruction Ref: | SI-042
Location on Site: |  | Level 2 riser cupboard, Zone B |  | Linked VO Ref: | VO-009
Description of Work: |  | Additional fire stopping to M&E service penetrations through 2-hour fire-rated wall in Level 2 riser. Not included in original scope — required following Building Control inspection comment BC-014.
SECTION 1: LABOUR
Name / Operative | Trade / Grade | Normal Hours | Overtime Hours | Rate (Normal) (£/hr) | Rate (OT) (£/hr) | Amount (£)
J. Williams | Electrician | 8 | 2 | 32.5 | 48.75 | 357.5
S. Patel | Electrician’s Mate | 8 | 2 | 24 | 36 | 264
R. Hughes | Fire Stopper (specialist) | 8 | 0 | 38 | 57 | 304
K. Brennan | Labourer | 4 | 0 | 18.5 | 27.75 | 74
LABOUR SUBTOTAL | [5 empty] | 999.5
SECTION 2: PLANT & EQUIPMENT
Plant / Equipment | Description | Quantity | Unit | Rate (£) |  | Amount (£)
Core drill rig | Hilti DD250 + diamond core bits | 1 | day | 185 |  | 185
Dust extraction unit | 110V dust suppression | 1 | day | 45 |  | 45
SDS drill | Hilti TE 30-A36 cordless | 1 | day | 35 |  | 35
PLANT SUBTOTAL | [5 empty] | 265
SECTION 3: MATERIALS
Material | Specification / Size | Quantity | Unit | Unit Rate (£) |  | Amount (£)
Intumescent fire sealant | Hilti CP 606 — 310ml cartridge | 12 | nr | 8.95 |  | 107.4
Fire batt mineral wool | Rockwool Fire Barrier — 60mm | 6 | m² | 14.5 |  | 87
Intumescent pipe collar | Promat PROMASEAL — 110mm | 4 | nr | 32 |  | 128
Acrylic sealant | White, fire-rated, 300ml | 4 | nr | 5.75 |  | 23
MATERIALS SUBTOTAL | [5 empty] | 345.4
COST SUMMARY
A. Labour Subtotal |  |  |  |  | 999.5
B. Plant & Equipment Subtotal |  |  |  |  | 265
C. Materials Subtotal |  |  |  |  | 345.4
D. Net Subtotal (A + B + C) |  |  |  |  | 1609.9
E. On-Costs / Overheads & Profit |  |  |  |  | 12.5% | 201.2375
F. Total Daywork Value (excl. VAT) |  |  |  |  | 1811.1375
G. VAT @ 20% |  |  |  |  | 362.2275
TOTAL DAYWORK VALUE (incl. VAT) |  |  |  |  | 2173.365
CONFIRMATION & SIGN-OFF
I confirm that the labour, plant, and materials listed above were employed/used on the date and for the work described.
Contractor’s Representative: |  |  |  | Employer’s / CA’s Representative:
Signed / Name / Date |  |  |  | Signed / Name / Date

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.