## Cover
EBRORA
ebrora.com
Prime Cost Items
Ledger
Track PC and Provisional Sum items with budget allowances,
actual spend, variance, and supplier details.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'PC Items Ledger' sheet. The financial summary auto-calculates from data rows below.
2. | Each row is one Prime Cost (PC) or Provisional Sum (PS) item from the contract BOQ.
3. | Enter the BOQ Allowance — the amount included in the contract for each PC/PS item.
4. | As quotations are received, record the quoted amount. Once approved, enter the Approved Spend.
5. | Actual Spend is the final invoiced/certified amount. Variance auto-calculates (BOQ Allowance minus Actual Spend).
6. | Positive variance = saving (green). Negative variance = overspend (red). Track these for final account adjustment.
7. | Record the Supplier and update the Status: Not Tendered, Tendered, Quoted, Approved, Complete, Cancelled.
Colour Key
Light teal cells (#E8F6F7) = User input / editable fields
Dark navy headers (#1B2A4A) = Do not edit
Green variance = Under-spend / saving
Red variance = Overspend
Amber = Tendered or Quoted (in progress)
Tips
Tip 1: | PC items must be competitively tendered under most NEC contracts. Record all quotations received, not just the winning bid.
Tip 2: | The variance on PC/PS items is a common source of final account adjustment. Keep this ledger current.
Tip 3: | Filter by Status = 'Not Tendered' to see which items still need procurement action.

## PC Items Ledger
Prime Cost Items Ledger — Financial Summary
| Total BOQ Allowance: | 418000 |  | Total Items: | 7 |  | PC Items Allowance: | 183000
| Total Actual Spend: | 209500 |  | Items Complete: | 4 |  | PS Items Allowance: | 235000
| Total Variance: | 208500 |  | Items Not Tendered: | 1
▼ PC & PS Items
Item Ref | Description | Type | BOQ Allowance (£) | Quotations Recd (£) | Approved Spend (£) | Actual Spend (£) | Variance (£) | % Expended | Status | Supplier | Notes
PC-001 | Utility diversions — gas, electric, water, telecoms | PS | 150000 | 138000 | 138000 | 138000 | 12000 | 92% | Complete | Various | Actual less than PS allowance
PC-002 | Structural steelwork — kiosk frames | PC | 35000 | 32500 | 32500 | 31800 | 3200 | 90.86% | Complete | Steelcraft Ltd | Saving due to design simplification
PC-003 | UV disinfection system — supply only | PC | 120000 | 118000 | 118000 | 0 | 120000 | 0% | Approved | Trojan Technologies | Delivery expected month 8
PC-004 | Landscaping and ecology mitigation | PS | 45000 | 52000 | 0 | 0 | 45000 | 0% | Quoted | TBC | 3 quotes received — all above PS allowance
PC-005 | Traffic management — temporary signals | PS | 25000 | 0 | 0 | 0 | 25000 | 0% | Not Tendered |  | Deferred to Phase 2
PC-006 | Specialist welding — stainless steel pipework | PC | 28000 | 26500 | 26500 | 27200 | 800 | 97.14% | Complete | WeldPro Services | Slight overspend on additional welds
PC-007 | CCTV drainage survey | PS | 15000 | 12500 | 12500 | 12500 | 2500 | 83.33% | Complete | DrainSurvey UK | Under PS allowance
GRAND TOTAL |  |  | 418000 | 379500 | 327500 | 209500 | 208500 | 50.12%

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.