## Cover
EBRORA
ebrora.com
BOQ Re-Measurement
Sheets
Re-measure BOQ line items with original vs revised quantities,
variance calculations, sign-off tracking, and financial summary.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Re-Measurement' sheet. The top section (rows 2–6) is a financial summary that auto-calculates from the data below.
2. | Data entry starts at row 9. Each row is one BOQ line item being re-measured.
3. | Enter the Item Ref and Description to match your contract BOQ. Select the Unit from the dropdown.
4. | Enter the Original Qty and Original Rate from the contract BOQ. The Original Value calculates automatically (Qty × Rate).
5. | Enter the Re-Measured Qty (actual site quantity) and Agreed Rate (may differ from original if rate is adjusted).
6. | Re-Measured Value, Variance (£), and % Change all calculate automatically. Do not edit these columns.
7. | Record who measured, who checked, and the sign-off date for audit trail.
8. | Expand optional columns for drawing refs, location/chainage, measurement sheet numbers, agreement status, and valuation period.
Colour Key
Light teal cells (#E8F6F7) = User input / editable fields
Dark navy headers (#1B2A4A) = Do not edit
White cells with formulas = Auto-calculated, do not edit
Green variance = Favourable (re-measured value less than original)
Red variance = Adverse (re-measured value more than original)
Negative values shown in red with brackets: (£1,234.00)
Tips
Tip 1: | Re-measure as you go — don't leave it all to final account. Monthly re-measurement keeps valuations accurate and disputes manageable.
Tip 2: | Always get re-measurements jointly checked. A measurement signed by both parties is much harder to dispute later.
Tip 3: | The financial summary at the top gives you the headline variance instantly — use it at commercial review meetings.

## Re-Measurement
BOQ Re-Measurement — Financial Summary
| Original BOQ Total: | 150800 |  | Items Measured: | 5
| Re-Measured Total: | 164097.5 |  | Items Agreed: | 3
| Overall Variance (£): | 13297.5 |  | Favourable Items: | 2
| Overall Variance (%): | 8.818% |  | Adverse Items: | 3
▼ BOQ Line Items
Item Ref | Description | Unit | Original Qty | Original Rate (£) | Original Value (£) | Re-Measured Qty | Agreed Rate (£) | Re-Measured Value (£) | Variance (£) | % Change | Measured By | Checked By | Sign-Off Date | Notes | Drawing Ref | Location / Chainage | Measurement Sheet No | Agreed (Y/N) | Valuation Period
1.01 | Excavation to formation level — inlet works | m³ | 2400 | 18.5 | 44400 | 2850 | 18.5 | 52725 | 8325 | 18.75% | J. Davies | R. Evans | 2026-02-22 | Rock encountered below 2.5m — additional qty | DWG-INL-003 | Ch. 0+000 to 0+045 | MS-001 | Yes | VP-06
1.02 | Disposal of excavated material to tip | m³ | 2400 | 12.75 | 30600 | 2850 | 12.75 | 36337.5 | 5737.5 | 18.75% | J. Davies | R. Evans | 2026-02-22 | Increased in line with excavation qty | DWG-INL-003 | Ch. 0+000 to 0+045 | MS-001 | Yes | VP-06
2.01 | Reinforced concrete C35/45 — base slabs | m³ | 180 | 165 | 29700 | 172 | 165 | 28380 | -1320 | -4.444% | A. Khan | M. Thompson | 2026-03-04 | Slightly less than BOQ — design optimisation | DWG-STR-012 | Inlet PStn base | MS-002 | Yes | VP-06
2.02 | Formwork to vertical faces | m² | 420 | 45 | 18900 | 455 | 45 | 20475 | 1575 | 8.333% | A. Khan | M. Thompson | 2026-03-04 | Additional shutter faces from design change | DWG-STR-012 | Inlet PStn walls | MS-003 | No
3.01 | Supply and install 150mm ductile iron pipe | m | 320 | 85 | 27200 | 308 | 85 | 26180 | -1020 | -3.75% | S. Patel |  |  | Shorter run confirmed on site — awaiting check | DWG-PW-005 | Ch. 0+100 to 0+408 | MS-004 | No
GRAND TOTAL |  |  |  |  | 150800 |  |  | 164097.5 | 13297.5 | 8.818%

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.