## Cover
EBRORA
ebrora.com
BOQ Tracker
Track BOQ line items with % complete, value earned, and drawing/spec references.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'BOQ Tracker' sheet. The top section is a financial summary. Data rows start at row 10.
2. | Each row is one BOQ line item. Enter the Item Ref, Description, Drawing Ref, and Spec Clause.
3. | Enter Unit, Qty, and Rate from the contract BOQ. BOQ Value calculates automatically (Qty × Rate).
4. | Update the % Complete column each valuation period. Value Earned and Remaining calculate automatically.
5. | The financial summary updates in real-time: total BOQ value, value earned, % complete, and remaining.
6. | Use the Drawing Ref and Spec Clause columns to link each item to its design basis — essential for re-measurement disputes.
Colour Key
Light teal cells (#E8F6F7) = User input / editable fields
Dark navy headers (#1B2A4A) = Do not edit
White formula cells = Auto-calculated
Green = 100% complete
Amber = 25-99% complete
Red = 0% complete
Tips
Tip 1: | Update % complete monthly in line with valuations. Consistent updates prevent disputes at final account.
Tip 2: | Filter by Drawing Ref to see all BOQ items associated with a specific drawing — useful for re-measurement.
Tip 3: | The Remaining Value column shows your exposure. Sort by Remaining (largest first) to focus on high-value incomplete items.

## BOQ Tracker
BOQ Tracker — Financial Summary
| Total BOQ Value: | 415100 |  | Total BOQ Items: | 10
| Value Earned to Date: | 230260 |  | Items at 100%: | 2
| Overall % Complete: | 55.47% |  | Items at 0%: | 1
| Remaining Value: | 184840 |  | Items In Progress: | 7
▼ BOQ Line Items
BOQ Item Ref | Description | Drawing Ref | Spec Clause | Unit | Qty | Rate (£) | BOQ Value (£) | % Complete | Value Earned (£) | Remaining (£) | Notes
1.01 | Excavation to formation — inlet works | DWG-INL-003 | CESWI Cl.601 | m³ | 2400 | 18.5 | 44400 | 85% | 37740 | 6660 | Re-measurement pending — additional qty expected
1.02 | Disposal of excavated material | DWG-INL-003 | CESWI Cl.602 | m³ | 2400 | 12.75 | 30600 | 85% | 26010 | 4590
2.01 | RC C35/45 base slabs — inlet PStn | DWG-STR-012 | BS 8500 | m³ | 180 | 165 | 29700 | 100% | 29700 | 0 | Complete — cube test results all pass
2.02 | Formwork to vertical faces | DWG-STR-012 | CESWI Cl.611 | m² | 420 | 45 | 18900 | 75% | 14175 | 4725 | Walls 75% complete
2.03 | B500B reinforcement | DWG-STR-012 | CESWI Cl.612 | t | 48 | 1250 | 60000 | 80% | 48000 | 12000
3.01 | 150mm DI pipe supply & install | DWG-PW-005 | CESWI Cl.501 | m | 320 | 85 | 27200 | 60% | 16320 | 10880 | 60% laid — awaiting pressure test
3.02 | DN600 penstock valve | DWG-SPS-002 | Spec M/31 | nr | 3 | 8500 | 25500 | 33% | 8415 | 17085 | 1 of 3 installed
4.01 | MCC Panel supply & install | DWG-EL-008 | Spec E/01 | nr | 1 | 45000 | 45000 | 100% | 45000 | 0 | Energised and tested
4.02 | Cable tray & containment | DWG-EL-008 | CESWI Cl.701 | m | 280 | 35 | 9800 | 50% | 4900 | 4900
5.01 | Fine screen — 3mm (revised) | DWG-INL-004 | Spec M/15 | nr | 2 | 62000 | 124000 | 0% | 0 | 124000 | CE-001 — awaiting delivery
GRAND TOTAL | [6 empty] | 415100 | 55.47% | 230260 | 184840

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.