## Cover
EBRORA
ebrora.com
Final Account Changes
Log & Agreement Tracker
Track all variations, claims, and adjustments to the final account
with contractor claim vs PM assessment, agreement status, and forecast.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Final Account Log' sheet. The financial summary at the top auto-calculates from data rows below.
2. | Enter the Original Contract Sum in cell C3 (the only manual input in the summary block).
3. | Data rows start at row 10. Each row is one change to the final account: a variation, claim, re-measurement adjustment, or credit.
4. | Record the Contractor's Claimed value and the PM's Assessed value. The Agreed Value is entered once both parties reach agreement.
5. | The Variance column auto-calculates: Contractor Claim minus PM Assessment. This shows the gap to be negotiated.
6. | Track Agreement Status: Not Assessed, Under Negotiation, Agreed, Disputed, Withdrawn.
7. | The summary block calculates: Total Agreed Changes, Total Disputed, and Forecast Final Account.
8. | Expand optional columns for linked CE refs, evidence, valuation period, payment certification, and final account line.
Colour Key
Light teal cells (#E8F6F7) = User input / editable fields
Dark navy headers (#1B2A4A) = Do not edit
White formula cells = Auto-calculated, do not edit
Green = Agreed or credit (negative/favourable variance)
Amber = Under Negotiation
Red = Disputed or adverse variance
Tips
Tip 1: | Agree changes as you go. A final account with 50 disputed items at the end of a project is a recipe for adjudication.
Tip 2: | The variance column is your negotiation tool. Sort by largest variance to focus on the items that matter most commercially.
Tip 3: | Update this log monthly and present at commercial review meetings. The Forecast Final Account figure is the number your FM needs.

## Final Account Log
Final Account — Financial Summary
| Original Contract Sum: | 2850000 |  | Total Items: | 7 |  | Contractor Total Claim: | 431925
| Total Agreed Changes: | 225650 |  | Items Agreed: | 4 |  | PM Total Assessment: | 306950
| Total Under Negotiation: | 130200 |  | Items Disputed: | 1 |  | Claim vs Assessment Gap: | 124975
| Total Disputed: | 64000 |  | Items Outstanding: | 2
| Forecast Final Account: | 3075650
▼ Final Account Changes
Ref | Change Type | Description | NEC Clause | Contractor Claim (£) | PM Assessment (£) | Agreed Value (£) | Variance (£) | Agreement Status | Date Agreed | Notes | Linked CE Ref | Supporting Evidence | Valuation Period | Payment Certified | Final Account Line
FA-001 | Variation | Change to inlet screen type — 6mm to 3mm fine screens per revised EA requirement | Cl 60.1(1) | 82000 | 68000 | 74500 | 14000 | Agreed | 2026-02-07 | Agreed at £74,500 following negotiation | CE-001 | QUO-CE-001, MS-001 | VP-04 | Yes | 4.01
FA-002 | Re-Measurement | Inlet excavation additional quantity — rock encountered below 2.5m | Cl 60.4 | 52725 | 48150 | 48150 | 4575 | Agreed | 2026-02-22 | Agreed at PM assessment — rates per BOQ | CE-003 | MS-001, PHOTO-INL-001 | VP-05 | Yes | 1.01
FA-003 | Credit | Omission of Phase 1 landscaping — deferred to Phase 2 | Cl 60.1(1) | -35000 | -35000 | -35000 | 0 | Agreed | 2026-01-23 | Negative CE agreed | CE-002 |  | VP-03 | Yes | 8.01
FA-004 | Claim | Prolongation claim — 3 weeks delay due to ground conditions at storm tanks | Cl 60.1(12) | 126000 | 84000 | 0 | 42000 | Under Negotiation |  | Contractor claims 3 weeks @ £42k/wk. PM assessing at 2 weeks. | CE-004 | Programme analysis |  | No
FA-005 | Daywork | Emergency dewatering during storm event — 3 days pump and operator | Cl 60.1(1) | 4200 | 3800 | 0 | 400 | Under Negotiation |  | Rates disputed — PM applying schedule of rates not daywork |  | DW-001 | VP-05 | No
FA-006 | Provisional Sum Adjustment | Utility diversions — PS £150k, actual spend £138k based on quotations received | Cl 60.1(1) | 138000 | 138000 | 138000 | 0 | Agreed | 2026-03-09 | PS adjustment agreed — actual less than allowance |  | Utility quotes | VP-06 | Yes | 9.01
FA-007 | Claim | Loss of productivity due to working restrictions adjacent to live process — 8 week period | Cl 60.1(12) | 64000 | 0 | 0 | 64000 | Disputed |  | PM rejects — states risk was Contractor's under contract | CE-006 | Site diaries, labour records |  | No
GRAND TOTALS |  |  |  | 431925 | 306950 | 225650 | 124975

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.