## Cover
EBRORA
ebrora.com
Provisional Sum Tracker
Monitor provisional sum allowances against instructed and
expended amounts with automatic drawdown tracking and balance alerts.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'PS Tracker' sheet. The top section shows a drawdown summary: total PS allowance in the contract, total amount instructed, total expended to date, and the remaining balance.
2. | Each row represents one provisional sum from the contract. Enter the PS Ref, the description as it appears in the bills, the PS Type (Defined or Undefined), and the Original Allowance (£).
3. | As the PM issues instructions against a provisional sum, enter the Instructed Amount (£) — this is the value of work actually ordered. For defined PS items, this is the tendered sum for the work; for undefined, it’s the PM’s instructed amount.
4. | Update the Expended to Date (£) as costs are incurred. The Balance Remaining and % Drawn columns calculate automatically.
5. | Update the Status as each PS progresses: Not Yet Instructed → Instructed → In Progress → Complete → Final Account Agreed.
Defined vs Undefined PS
Defined PS (JCT/NEC) — The work is described in enough detail for the contractor to price. The contractor includes the PS in their tender. Adjustment is the difference between the PS allowance and the actual instructed cost.
Undefined PS — The work is not sufficiently defined at tender. The contractor does not price it. The PM instructs the work and it is valued separately. The full allowance is available.
Optional Fields
6. | Click [+] to expand optional fields: Bill/Section Ref, Date Instructed, Instruction Ref, Adjustment to Contract Sum (£), Linked VO Ref, and Responsible Party.
7. | The Adjustment column auto-calculates the difference between the Original Allowance and the Instructed Amount — this is the add/omit to the contract sum.
Colour Key
Light teal cells (#E8F6F7) — User input.
Dark navy headers — Do not edit.
Green % Drawn — Under 80% of allowance used.
Amber % Drawn — 80–99% of allowance used.
Red % Drawn — 100%+ of allowance used (overspent).
Green Balance — Positive balance remaining (underspend).
Red Balance — Negative balance (overspend against allowance).
Tips
Tip 1: | Review this tracker monthly alongside the Budget vs Actual template. Provisional sums are one of the most common sources of final account movement — track them closely.
Tip 2: | For undefined PS items, ensure the PM formally instructs before any work starts. Work carried out without a formal instruction may not be recoverable.
Tip 3: | At final account stage, filter by Status ≠ 'Final Account Agreed' to identify any outstanding PS items still requiring reconciliation.

## PS Tracker
PROVISIONAL SUM TRACKER — DRAWDOWN MONITOR
Total PS Allowance (£) |  | Total Instructed (£) |  | Total Expended to Date (£) |  | Total Balance Remaining (£) |  | Overall % Drawn
408000 |  | 322000 |  | 263500 |  | 144500 |  | 64.58%
Defined PS |  | Undefined PS |  | Not Yet Instructed | Instructed | In Progress | Complete | Final Account Agreed
3 |  | 3 |  | 1 | 1 | 3 | 1 | 0
▸ Optional Fields — Click [+] to expand
PS Ref | Description | PS Type | Original Allowance (£) | Instructed Amount (£) | Expended to Date (£) | Balance Remaining (£) | % Drawn | Status | Notes | Bill / Section Ref | Date Instructed | Instruction Ref | Adjustment to Contract Sum (£) | Linked VO Ref | Responsible Party
PS-001 | Provisional sum for utility diversions (gas, water, BT) | Undefined | 85000 | 62000 | 58500 | 26500 | 68.82% | In Progress | UKPN diversion complete. Gas diversion in progress. | 3/14A | 2025-08-12 | AI-023 | -23000 | VO-006 | Site Manager
PS-002 | Provisional sum for ground investigation and remediation | Undefined | 120000 | 95000 | 95000 | 25000 | 79.17% | Complete | All remediation works complete. Awaiting final account agreement. | 2/7B | 2025-07-05 | AI-018 | -25000 | VO-001 | Project Manager
PS-003 | Provisional sum for artwork installation to main reception | Defined | 35000 | 0 | 0 | 35000 | 0% | Not Yet Instructed | Client reviewing artist proposals. Expected instruction Q2 2026. | 5/22C |  |  | -35000 |  | Client PM
PS-004 | Provisional sum for specialist acoustic treatment to plant rooms | Defined | 48000 | 52000 | 38000 | 10000 | 79.17% | In Progress | Instructed amount exceeds PS by £4k due to additional room. | 4/11D | 2025-10-20 | AI-031 | 4000 | VO-008 | M&E Coordinator
PS-005 | Provisional sum for external signage and wayfinding | Undefined | 25000 | 22000 | 0 | 25000 | 0% | Instructed | Subcontractor appointed. Works to start March 2026. | 5/19A | 2026-01-08 | AI-041 | -3000 |  | Site Manager
PS-006 | Provisional sum for IT/data cabling and containment | Defined | 95000 | 91000 | 72000 | 23000 | 75.79% | In Progress | First fix complete. Second fix ongoing. | 4/15E | 2025-09-15 | AI-027 | -4000 |  | M&E Coordinator
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
TOTALS |  |  | 408000 | 322000 | 263500 | 144500 | 64.58% | [5 empty] | -86000

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.