## Cover
EBRORA
ebrora.com
Retention Release Tracker
Track retention held against each subcontract package with
automatic two-tranche release at PC and end of defects liability.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Retention Tracker' sheet. The top section has a three-block retention pool summary: Total Retention Held, Released to Date, and Still Outstanding — plus a visual breakdown of the two release tranches.
2. | Each row is one subcontract package. Enter the Package Ref, Subcontractor name, the Certified Value to Date (£), and the Retention % (default 5%, editable per row).
3. | Retention Held calculates automatically as Certified Value × Retention %. This is the total retention being withheld against that package.
4. | Under most standard forms, retention is released in two halves: 50% at Practical Completion (PC) and the remaining 50% at the end of the Defects Liability Period (DLP).
5. | Enter the PC Date and DLP End Date for each package. The Release Status column auto-calculates whether PC Release or DLP Release is due based on today’s date. Mark releases as actioned using the PC Released and DLP Released Yes/No dropdowns.
Release Logic
PC Release Amount = 50% of Retention Held. Due when the PC Date is reached.
DLP Release Amount = remaining 50% of Retention Held. Due when DLP End Date is reached.
Retention Still Held = Retention Held – amounts actually released (based on Yes/No flags).
The template does not auto-release funds — you must confirm each release by setting the dropdown to 'Yes'. This prevents accidental early release.
Colour Key
Light teal cells (#E8F6F7) — User input.
Dark navy headers — Do not edit.
Green Release Status — Fully released (both PC and DLP released).
Amber Release Status — PC released, DLP retention still held.
Blue Release Status — PC due (PC date passed but not yet released).
Red Release Status — DLP overdue (DLP end date passed but not released).
Grey — Not yet due (both milestones in future).
Tips
Tip 1: | Review this tracker monthly and at every valuation. Subcontractors are entitled to retention release — late release can trigger interest claims under the Housing Grants Act 1996.
Tip 2: | Always confirm PC and DLP completion formally before releasing retention. A signed practical completion certificate or making-good certificate should be on file.
Tip 3: | Cross-reference the PC and DLP dates with your Snagging/Defects List (Template 26) to ensure all defects are resolved before releasing the final 50%.

## Retention Tracker
RETENTION RELEASE TRACKER
Total Retention Held (£) |  |  | Total Released to Date (£) |  |  | Retention Still Outstanding (£) |  |  | Packages Tracked
80800 |  |  | 14375 |  |  | 66425 |  |  | 6
PC Releases Due (date passed) |  |  | PC Releases Made |  |  | DLP Releases Due (date passed) |  |  | DLP Releases Made
1 |  |  | 1 |  |  | 0 |  |  | 0
Standard retention: 5% (3% on some contracts). Release: 50% at Practical Completion, 50% at end of Defects Liability Period (typically 12 months post-PC).
▸ Optional Fields — Click [+] to expand
[5 empty] | TRANCHE 1: PC RELEASE |  | TRANCHE 2: DLP RELEASE
Package Ref | Subcontractor | Certified Value to Date (£) | Retention % | Retention Held (£) | PC Date | PC Released? | DLP End Date | DLP Released? | Retention Still Held (£) | Release Status | Notes | Contract Value (£) | Subcontract Ref | Defects Outstanding | Payment Cert Ref
PKG-01 | Murphy Ground Engineering | 575000 | 5% | 28750 | 2025-11-15 | Yes | 2026-11-15 | No | 14375 | PC Released | PC retention released IPC-06. DLP active. | 620000 | SC-001 | 0 | IPC-06
PKG-02 | Severfield UK Ltd | 490000 | 5% | 24500 | 2026-03-20 | No | 2027-03-20 | No | 24500 | PC Due | Steel frame complete. Awaiting formal PC cert. | 520000 | SC-002 | 2 | IPC-08
PKG-03 | Kawneer UK | 185000 | 5% | 9250 |  |  |  | No | 9250 | Not Yet Due | Curtain wall installation ongoing. PC not yet reached. | 310000 | SC-003 | N/A | IPC-07
PKG-04 | McCann Electrical Ltd | 225000 | 5% | 11250 |  |  |  | No | 11250 | Not Yet Due | Electrical first fix in progress. | 480000 | SC-004 | N/A | IPC-07
PKG-05 | Trend Controls Ltd | 42000 | 5% | 2100 |  |  |  | No | 2100 | Not Yet Due | BMS design and procurement stage. | 90000 | SC-005 | N/A
PKG-06 | Wates Interiors | 165000 | 3% | 4950 |  |  |  | No | 4950 | Not Yet Due | Drylining Phase 1 complete. 3% retention per subcontract. | 340000 | SC-006 | N/A | IPC-07
TOTALS |  | 1682000 |  | 80800 |  |  |  |  | 66425 |  |  | 2360000
Formulas:
Release Status = IF([Retention Held (£)]="","",IF(AND([Retention Still Outstanding (£)]="Yes",[DLP Released?]="Yes"),"Fully Released",IF(AND([Retention Still Outstanding (£)]="Yes",[DLP Released?]="No"),IF(AND([DLP End Date]<>"",[DLP End Date]<=TODAY()),"DLP Due","PC Released"),IF(AND([PC Date]<>"",[PC Date]<=TODAY(),[Retention Still Outstanding (£)]="No"),"PC Due","Not Yet Due"))))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.