## Cover
EBRORA
ebrora.com
Valuation Evidence
Pack Index
Index and track all supporting evidence for interim valuations
organised by valuation period with submission status tracking.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Evidence Index' sheet. Evidence is organised into sections by Valuation Period (VP-01, VP-02, etc.).
2. | Each teal section header represents one valuation period. Evidence items are listed underneath each header.
3. | For each evidence item, record: Item Ref, Evidence Type (from dropdown), Description, linked BOQ Item, Value Claimed.
4. | Enter the Source Document Ref (e.g., photo filename, measurement sheet number, delivery ticket number).
5. | Track the Status: Not Compiled, In Progress, Complete, Submitted, Verified by PM.
6. | Record the Submitted Date when evidence is formally submitted with the valuation application.
7. | Add new valuation period sections by copying a section block and updating the header.
8. | The Grand Summary at the top shows totals across all periods.
Colour Key
Light teal cells (#E8F6F7) = User input / editable fields
Dark navy headers (#1B2A4A) = Do not edit
Teal section headers = Valuation period dividers
Green = Complete / Submitted / Verified
Amber = In Progress
Red = Not Compiled
Tips
Tip 1: | Compile evidence as the work happens — don't wait until valuation day. Photos taken on the day of concreting are worth ten taken a month later.
Tip 2: | Cross-reference every evidence item to a BOQ line. The PM will assess your valuation faster if they can trace each claim to evidence.
Tip 3: | Keep a physical or digital folder per valuation period that mirrors this index. The index is the map; the folder is the territory.

## Evidence Index
Valuation Evidence Pack — Grand Summary
Total Evidence Items: | 13 | Complete / Submitted / Verified: | 7 |  | Not Compiled: | 1
Total Value Claimed: | 179700
▼ Evidence by Valuation Period
VP-01 — Valuation Period 1 (01 Oct 2025 – 31 Oct 2025)
Item Ref | Evidence Type | Description | BOQ Item Ref | Value Claimed (£) | Source Document Ref | Status | Submitted Date | Notes
VP01-001 | Progress Photos | Inlet works excavation — formation level reached, bulk dig complete | 1.01 | 44400 | PHOTO-INL-001 to 015 | Verified by PM | 2025-12-24 | 15 geotagged photos
VP01-002 | Measurement Sheet | Joint measurement of inlet excavation quantities — 2,400m³ original | 1.01 | 44400 | MS-001 | Verified by PM | 2025-12-24 | Signed by both QS
VP01-003 | Delivery Ticket | Concrete delivery tickets for base slab — C35/45, 85m³ delivered | 2.01 | 14025 | DT-CON-001 to 008 | Submitted | 2025-12-26
VP01-004 | Test Certificate | Concrete cube test results — 7-day and 28-day strengths | 2.01 | 0 | LAB-CUB-001 | Complete |  | Results all pass
VP01-005 | Plant Return | Excavator and dump truck daily plant returns — weeks 1-4 | 1.01 | 0 | PR-001 to PR-020 | In Progress |  | 3 returns missing — chasing operator
|  |  | VP-01 Subtotal: | 102825
VP-02 — Valuation Period 2 (01 Nov 2025 – 30 Nov 2025)
Item Ref | Evidence Type | Description | BOQ Item Ref | Value Claimed (£) | Source Document Ref | Status | Submitted Date | Notes
VP02-001 | Progress Photos | Storm tank excavation and sheet piling — piles driven to depth | 1.02 | 36337.5 | PHOTO-SPS-001 to 022 | Submitted | 2026-01-23 | 22 photos inc. pile driving
VP02-002 | Measurement Sheet | Storm tank excavation re-measurement — additional rock encountered | 1.02 | 36337.5 | MS-002 | Submitted | 2026-01-25 | Rock class claimed under EW-001
VP02-003 | Daywork Record | Emergency dewatering — 3 days pump hire and operator during flood event |  | 4200 | DW-001 | Complete |  | Signed daywork sheets attached
VP02-004 | As-Built Drawing | Inlet works as-built — foundation level survey | 1.01 | 0 | AB-INL-001 Rev.A | In Progress |  | Survey complete, drawing being updated
VP02-005 | Inspection Record | Hold point inspection — base slab reinforcement before pour | 2.01 | 0 | IR-STR-003 | Not Compiled |  | Need to retrieve from ITP pack
|  |  | VP-02 Subtotal: | 76875
VP-03 — Valuation Period 3 (01 Dec 2025 – 31 Dec 2025)
Item Ref | Evidence Type | Description | BOQ Item Ref | Value Claimed (£) | Source Document Ref | Status | Submitted Date | Notes
|  |  | VP-03 Subtotal: | 0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.