## Cover
EBRORA
ebrora.com
Value Engineering
Register
Triage and score VE ideas against cost, time, and carbon savings
with weighted scoring, risk assessment, and implementation tracking.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'VE Register' sheet. Each row is one value engineering idea or proposal.
2. | Describe the VE idea and estimate the cost saving (£), time saving (weeks), and CO₂ reduction (tonnes).
3. | Score each idea on 5 criteria using a 1–5 scale (1=low impact/benefit, 5=high): Cost Saving, Time Saving, CO₂ Reduction, Risk (1=high risk, 5=low risk), and Feasibility (1=difficult, 5=easy).
4. | The Weighted Score auto-calculates using the weights in the weight row (row 9). Default weights: Cost 30%, Time 20%, CO₂ 20%, Risk 15%, Feasibility 15%.
5. | The Grade auto-assigns: A (score ≥4.0), B (3.0–3.9), C (2.0–2.9), D (<2.0). Green/Amber/Red colouring matches.
6. | Track the Status: Proposed, Under Review, Approved, Implemented, Rejected.
7. | The summary block shows total VE ideas, implemented savings, and CO₂ reduction achieved.
Colour Key
Light teal cells (#E8F6F7) = User input / editable fields
Dark navy headers (#1B2A4A) = Do not edit
Green = Grade A (score ≥ 4.0) or Approved/Implemented status
Amber = Grade B (score 3.0–3.9) or Under Review
Red = Grade C/D (score < 3.0) or Rejected
Score cells: 1–5 scale with validation
Tips
Tip 1: | Run a VE workshop early in the project. The biggest savings come from design-stage ideas, not construction-stage tweaks.
Tip 2: | Don't just track cost — the CO₂ column is increasingly important for water company carbon targets and social value scoring.
Tip 3: | Sort by Weighted Score to prioritise implementation. Focus on Grade A ideas first.

## VE Register
Value Engineering Register — Summary
| Total VE Ideas: | 7 |  | Approved (not yet implemented): | 2
| Implemented: | 3 |  | Total Est. CO₂ Saved: | 22 t
| Total Est. Cost Saving: | 48000 |  | Avg Weighted Score: | 3.2214
▼ VE Ideas & Scoring
VE Ref | Description | Discipline | Proposed By | Est. Cost Saving (£) | Est. Time Saving (wks) | Est. CO₂ Reduction (t) | Score: Cost | Score: Time | Score: CO₂ | Score: Risk | Score: Feasibility | Weighted Score | Grade | Status | Notes
WEIGHTS → | [6 empty] | 30% | 20% | 20% | 15% | 15% | 100% | 100%
← Score 1 (low) to 5 (high) →
VE-001 | Replace precast concrete manholes with GRP — lighter, faster install, no cranage | Civil | J. Davies | 28000 | 2 | 8 | 4 | 4 | 3 | 4 | 5 | 3.95 | B | Implemented | Saved 2 weeks on manhole installation programme
VE-002 | Omit brick retaining wall, replace with gabion baskets using site-won stone | Structural | R. Evans | 15000 | 1 | 12 | 3 | 2 | 4 | 3 | 4 | 3.15 | B | Implemented | Reused excavated rock — significant CO₂ saving
VE-003 | Switch to solar-powered telemetry at remote borehole sites | Electrical | S. Patel | 8000 | 0 | 5 | 3 | 1 | 3 | 4 | 4 | 2.9 | C | Approved | Eliminates need for mains power connection
VE-004 | Use HDPE instead of DI for non-pressure gravity sewers | Mechanical | A. Khan | 22000 | 1 | 6 | 4 | 3 | 3 | 3 | 4 | 3.45 | B | Under Review | Weight saving reduces plant requirements
VE-005 | Combine storm tanks 3 & 4 into single larger tank — reduce dividing wall | Structural | M. Thompson | 45000 | 3 | 15 | 5 | 4 | 4 | 2 | 2 | 3.7 | B | Proposed | High saving but significant design change — risk assessment needed
VE-006 | Replace painted mild steel handrails with GRP — eliminate repainting lifecycle cost | Mechanical | J. Davies | 5000 | 0 | 2 | 2 | 1 | 2 | 5 | 5 | 2.7 | C | Implemented | Low cost saving but zero maintenance benefit
VE-007 | Prefabricate MCC panels offsite — reduce wet trade interface on site | Electrical | S. Patel | 0 | 2 | 3 | 1 | 4 | 2 | 4 | 4 | 2.7 | C | Approved | Time saving is main driver — no cost saving

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.