## Cover
EBRORA
ebrora.com
Claim / Dispute Register
Track claims and disputes through escalation stages with
three-tier financial exposure analysis and resolution monitoring.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Claim Register' sheet. The top section has three panels: a Financial Exposure Summary (left) showing best/likely/worst case totals, an Escalation Stage Pipeline (centre), and a Resolution Summary (right).
2. | Each row represents one claim or dispute. Enter the Claim Ref, Date Identified, Claimant (who is making the claim), Respondent (who the claim is against), Direction (By Us / Against Us), and a clear description.
3. | Set the Escalation Stage as the claim progresses: Identified → Notified → Negotiation → Adjudication → Arbitration / Litigation → Settled / Withdrawn.
4. | For each claim, enter the three-tier financial exposure: Best Case (£), Likely Case (£), and Worst Case (£). These feed the exposure summary at the top for board reporting.
5. | When a claim is resolved, enter the Settled Amount and update the stage to 'Settled'. The Variance column shows the difference between the Settled and Likely amounts.
Financial Exposure Explained
Best Case — The minimum realistic exposure. Assumes all arguments succeed and the most favourable interpretation applies.
Likely Case — The most probable outcome based on current evidence and legal/commercial advice. Use this for management reporting.
Worst Case — The maximum realistic exposure. Assumes all arguments fail and adverse findings apply.
Direction matters: 'By Us' claims are potential income; 'Against Us' claims are potential cost.
Optional Fields
6. | Click [+] to expand: Contract Clause, Claim Category, Date Notified, Legal Advisor, Next Action, Next Action Date, Days Open, and Linked CE/VO/Correspondence Refs.
7. | The Days Open column auto-calculates from Date Identified. Claims open for >90 days flag amber; >180 days flag red.
Colour Key
Light teal cells (#E8F6F7) — User input.
Dark navy headers — Do not edit.
Blue — Stage is 'Identified' or 'Notified' (early stage).
Amber — Stage is 'Negotiation' (active discussion).
Orange — Stage is 'Adjudication' (formal dispute).
Red — Stage is 'Arbitration / Litigation' (escalated).
Green — Stage is 'Settled'.
Grey — Stage is 'Withdrawn'.
Tips
Tip 1: | Review this register monthly at board level. The Likely Case total is the figure that should be reflected in your project cost report as a risk-adjusted allowance.
Tip 2: | Keep detailed claim files separate from this register. This template is a summary tracker — the evidence, chronology and quantum should sit in the claim file referenced in the Linked Refs column.
Tip 3: | Always take legal advice before referring a dispute to adjudication. The 28-day adjudication timetable is extremely compressed — preparation must be complete before the Notice of Adjudication is issued.

## Claim Register
CLAIM / DISPUTE REGISTER — FINANCIAL EXPOSURE TRACKER
FINANCIAL EXPOSURE SUMMARY |  |  |  |  | ESCALATION STAGE PIPELINE |  |  |  |  | DIRECTION SUMMARY
Best Case Total (£) |  | 54000 |  |  | Identified | Notified | Negotiation | Adjudication |  | Claims By Us | 2
Likely Case Total (£) |  | 101500 |  |  | 1 | 1 | 1 | 0 |  | Claims Against Us | 2
Worst Case Total (£) |  | 153000 |  |  | Arbitration / Litigation | Settled | Withdrawn |  |  | Active (not settled) | 3
Total Settled (£) |  | 42500 |  |  | 0 | 1 | 0 |  |  | Total Claims | 4
▸ Optional Fields — Click [+] to expand
CLAIM DETAILS | [6 empty] | FINANCIAL EXPOSURE MATRIX
[7 empty] | ● Best | ● Likely | ● Worst
Claim Ref | Date Identified | Claimant | Respondent | Direction | Description | Escalation Stage | Best Case (£) | Likely Case (£) | Worst Case (£) | Settled Amount (£) | Variance (£) | Notes | Contract Clause | Claim Category | Date Notified | Legal Advisor | Next Action | Next Action Date | Days Open | Linked Refs
CLM-001 | 2025-07-15 | Kier Construction | Riverside Developments | By Us | Extension of time claim — 3 weeks delay due to unforeseen ground conditions in Zone A requiring additional piling | Settled | 28000 | 42500 | 55000 | 42500 | 0 | Settled as part of CE-001. Final account agreed. | Cl 60.1(12) | Extension of Time | 2025-07-22 | Beale & Company | File closed |  |  | Closed
CLM-002 | 2025-10-08 | Kier Construction | Riverside Developments | By Us | Prolongation costs — 3-week weather delay (Storm Éowyn) impacting prelims and programme | Negotiation | 18000 | 32000 | 45000 | 0 | -32000 | Quotation CE-002 submitted. QS assessing. | Cl 60.1(13) | Loss & Expense | 2025-10-15 |  | Chase PM for assessment response | 2026-03-28 |  | 165
CLM-003 | 2025-12-01 | Riverside Developments | Kier Construction | Against Us | Defects claim — alleged water ingress through curtain wall system at Level 3 north elevation | Notified | 0 | 15000 | 35000 | 0 | -15000 | Investigation underway. Kawneer attending site next week. |  | Defects | 2025-12-05 | Kennedys Law | Attend joint inspection with Kawneer | 2026-04-02 |  | 111
CLM-004 | 2026-01-20 | Murphy Ground Engineering | Kier Construction | Against Us | Subcontractor claim for additional prelims during extended piling programme | Identified | 8000 | 12000 | 18000 | 0 | -12000 | Reviewing subcontract terms and daywork records. | SC Cl 4.3 | Payment |  |  | Review DW records DW-001 to DW-012 | 2026-03-25 |  | 61
Formulas:
Linked Refs = IF(AND([Date Identified]<>"",[Escalation Stage]<>"Settled",[Escalation Stage]<>"Withdrawn"),TODAY()-[Date Identified],IF([Date Identified]<>"","Closed",""))
Days Open = IF(AND([Date Identified]<>"",[Escalation Stage]<>"Settled",[Escalation Stage]<>"Withdrawn"),TODAY()-[Date Identified],IF([Date Identified]<>"","Closed",""))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.