## Cover
EBRORA
ebrora.com
Compensation Event Register
Track NEC compensation events through each contractual stage
with automatic deadline monitoring and value tracking.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'CE Register' sheet. The top band shows live counts by stage: how many CEs are at Notified, Quotation, Assessment, Implemented, and how many have been Withdrawn or Not Accepted.
2. | Each row tracks one compensation event. Enter the CE Ref, Date Notified, the NEC clause (e.g. 60.1(1)), a description, and the current Stage using the dropdown.
3. | As the CE progresses, fill in the key milestone dates: Date Quotation Submitted, Date PM Responded, and Date Implemented. The Quotation Deadline and Days Remaining columns calculate automatically based on NEC timescales.
4. | Enter the Contractor’s Quotation (£) when submitted and the Agreed/Assessed Value (£) once the PM makes their assessment. Variance calculates automatically.
5. | The Quotation Deadline column adds 3 weeks (21 days) to the notification date per NEC Clause 62.3. If you’ve passed the deadline without a quotation, the cell highlights red.
NEC Workflow Stages
Notified — CE has been notified to the PM under Clause 61.
Quotation — Contractor is preparing or has submitted quotation under Clause 62.
Assessment — PM is assessing the quotation under Clause 64/65.
Implemented — CE has been implemented and value agreed.
Not Accepted — PM has decided the event is not a CE.
Withdrawn — Contractor has withdrawn the notification.
Optional Fields
6. | Click [+] to expand optional fields: Linked EW Ref (Early Warning), PM Response Date, PM Response, Time Impact (weeks), Programme Impact Description, and Linked VO Ref.
7. | Linking to the Early Warning register is good practice under NEC4 — it evidences that the matter was raised proactively.
Colour Key
Light teal cells (#E8F6F7) — User input.
Dark navy headers — Do not edit.
Blue — Stage is 'Notified'.
Amber — Stage is 'Quotation' or 'Assessment'.
Green — Stage is 'Implemented'.
Red — Stage is 'Not Accepted', or quotation deadline has passed.
Grey — Stage is 'Withdrawn'.
Tips
Tip 1: | Under NEC4, the Contractor must notify a CE within 8 weeks of becoming aware (Clause 61.3). Log events immediately — late notifications can be time-barred.
Tip 2: | Always link CEs to Early Warnings where possible. The Early Warning Register (Template 64) cross-references with this register.
Tip 3: | Review this register fortnightly in your commercial/PM meeting. Filter by Stage = 'Quotation' and sort by Quotation Deadline to prioritise submissions.

## CE Register
COMPENSATION EVENT REGISTER — NEC WORKFLOW TRACKER
Total CEs |  | Total Quoted (£) |  | Total Agreed (£) |  | Net Variance (£) |  | Overdue Quotations
5 |  | 92500 |  | 42500 |  | -50000 |  | 2
Notified |  | Quotation |  | Assessment |  | Implemented |  | Not Accepted |  | Withdrawn
2 |  | 1 |  | 1 |  | 1 |  | 0 |  | 0
NEC4 Key Timescales: 61.3 — Notify within 8 weeks ¦ 62.3 — Submit quotation within 3 weeks of instruction ¦ 64.1/65.1 — PM responds within 2 weeks of quotation
▸ Optional Fields — Click [+] to expand
CE Ref | Date Notified | NEC Clause | Description | Stage | Quotation Deadline | Contractor Quotation (£) | Agreed / Assessed (£) | Variance (£) | Notes | Linked EW Ref | Date Quotation Submitted | PM Response Date | PM Response | Time Impact (Weeks) | Programme Impact | Linked VO Ref
CE-001 | 2025-07-22 | 60.1(1) | Unforeseen ground conditions — soft spots requiring additional piling at Grid J7-K8 | Implemented | 2025-08-12 | 48000 | 42500 | -5500 | Implemented IPC-03. Final account agreed. | EW-003 | 2025-08-05 | 2025-08-18 | Accepted | 2 | 2-week delay to substructure | VO-001
CE-002 | 2025-09-10 | 60.1(4) | 3-week weather delay — Storm Éowyn. Prelim costs and programme impact. | Assessment | 2025-10-01 | 32000 | 0 | -32000 | Quotation submitted. PM reviewing with QS. | EW-007 | 2025-09-28 | 2025-10-08 | Revised Quotation Requested | 3 | 3-week critical delay | VO-003
CE-003 | 2025-11-05 | 60.1(1) | Building Control requirement for additional fire stopping to Level 2 risers | Quotation | 2025-11-26 | 12500 | 0 | -12500 | Quotation in preparation. Daywork records DW-027 to DW-031. | EW-012 |  |  |  | 0 |  | VO-004
CE-004 | 2025-12-12 | 60.1(8) | PM instruction to change external cladding colour from RAL 7016 to RAL 9005 | Notified | 2026-01-02 | 0 | 0 | 0 | Awaiting PM instruction to submit quotation. |  |  |  |  | 0
CE-005 | 2026-01-18 | 60.1(12) | Contractor notified late access to Zone D due to third-party utility diversion delay | Notified | 2026-02-08 | 0 | 0 | 0 | EW raised. Awaiting PM decision on CE status. | EW-018 |  |  |  | 0
Formulas:
Quotation Deadline = IF([Date Notified]<>"",[Date Notified]+21,"")

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.