## Cover
EBRORA
ebrora.com
Early Warning / CE
Aging Dashboard
Monitor NEC early warnings and compensation events with response SLAs,
aging buckets, overdue alerts, and status breakdown.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | This template has two working sheets: 'Dashboard' (KPIs and aging analysis) and 'EW & CE Log' (detailed register).
2. | Start with the 'EW & CE Log' sheet. Each row is one Early Warning or Compensation Event.
3. | Enter the Ref, Type, Date Raised, Description, NEC Clause, Raised By, and Response Due Date.
4. | The 'Age (Days)' column auto-calculates from Date Raised to today (or to Response Date if responded).
5. | The 'Overdue' column flags Yes/No based on whether the age exceeds the SLA (14 days for EW, 28 days for CE).
6. | Update the Status as items progress: Open, Responded, Under Assessment, Agreed, Rejected, Withdrawn.
7. | The Dashboard auto-updates with KPI tiles, aging bucket counts, and status breakdowns pulling from the log.
Colour Key
Light teal cells (#E8F6F7) = User input / editable fields
Dark navy headers (#1B2A4A) = Do not edit
Green = Agreed/Withdrawn/Responded or within SLA
Amber = Under Assessment or approaching SLA
Red = Overdue (past SLA), Open with no response, or Rejected
Tips
Tip 1: | Review the aging buckets weekly. Anything in the 29+ day bucket without a response is a contract compliance failure.
Tip 2: | The SLA for EW response is typically 2 weeks under NEC4. CEs have 4 weeks. Adjust in your log if your contract differs.
Tip 3: | Use the Dashboard at commercial meetings — the aging chart instantly shows whether the PM is keeping pace with notifications.

## Dashboard
Early Warning / CE — Aging Dashboard
Total Early Warnings |  | Total Comp. Events |  | Overdue Items | Avg Age (Days)
5 |  | 5 |  | 0 | 12.3
Aging Analysis — Early Warnings |  |  |  |  | Status Breakdown — All Items
Aging Bucket | Open | Responded | Total | % of EWs | Status | EWs | CEs | Total
0–7 days | 1 | 2 | 3 | — | Open | 2 | 1 | 3
8–14 days | 1 | 1 | 2 | — | Responded | 2 | 0 | 2
15–28 days | 0 | 0 | 0 | — | Under Assessment | 0 | 1 | 1
29+ days | 0 | 0 | 0 | — | Agreed | 1 | 2 | 3
[5 empty] | Rejected | 0 | 1 | 1
Aging Analysis — Compensation Events |  |  |  |  | Withdrawn | 0 | 0 | 0
Aging Bucket | Open | Responded | Total | % of CEs
0–14 days | 0 | 3 | 3 | —
15–28 days | 1 | 0 | 1 | —
29–42 days | 0 | 0 | 0 | —
43+ days | 0 | 1 | 1 | —

## EW & CE Log
Ref | Type | Date Raised | Description | NEC Clause | Raised By | Response Due | Response Date | Age (Days) | SLA (Days) | Overdue | Status | Cost Impact (£) | Time Impact (wks) | Notes
EW-001 | Early Warning | 2026-01-23 | Ground conditions worse than GI report at storm tanks | Cl 16.1 | Contractor | 2026-02-06 | 2026-01-28 | 5 | 14 | No | Responded | 45000 | 2 | Discussed at RRM
EW-002 | Early Warning | 2026-02-07 | UV system supplier delay — 6 week potential | Cl 16.1 | PM | 2026-02-21 | 2026-02-10 | 3 | 14 | No | Responded | 0 | 0 | Alternative sourcing underway
EW-003 | Early Warning | 2026-03-14 | Asbestos found in existing building | Cl 16.1 | Contractor | 2026-03-28 |  | 10 | 14 | No | Open | 0 | 0 | Survey commissioned
EW-004 | Early Warning | 2026-03-19 | Utility diversion works may clash with highway closure restrictions | Cl 16.1 | Contractor | 2026-04-02 |  | 5 | 14 | No | Open | 0 | 0
EW-005 | Early Warning | 2026-02-22 | Concrete supply shortage reported by supplier | Cl 16.1 | Contractor | 2026-03-08 | 2026-03-02 | 8 | 14 | No | Agreed | 0 | 0 | Resolved — alternative supplier
CE-001 | Compensation Event | 2026-02-12 | Instructed change: inlet screens 6mm to 3mm | Cl 60.1(1) | PM | 2026-03-12 | 2026-02-17 | 5 | 28 | No | Under Assessment | 82000 | 3 | Quotation submitted
CE-002 | Compensation Event | 2026-01-23 | Omission of Phase 1 landscaping — credit | Cl 60.1(1) | PM | 2026-02-20 | 2026-01-25 | 2 | 28 | No | Agreed | -35000 | -1 | Negative CE
CE-003 | Compensation Event | 2026-02-22 | Additional excavation quantity — rock at storm tanks | Cl 60.4 | Contractor | 2026-03-22 | 2026-03-04 | 10 | 28 | No | Agreed | 48150 | 0 | Rates per BOQ
CE-004 | Compensation Event | 2026-02-27 | Prolongation claim — 3 weeks delay ground conditions | Cl 60.1(12) | Contractor | 2026-03-27 |  | 25 | 28 | No | Open | 126000 | 3 | Under review by PM
CE-005 | Compensation Event | 2026-02-02 | Working restrictions adj. live process — productivity loss | Cl 60.1(12) | Contractor | 2026-03-02 |  | 50 | 28 | No | Rejected | 64000 | 0 | PM states contractor risk
Formulas:
Age (Days) = IF([Date Raised]="","",IF([Response Date]<>"",[Response Date]-[Date Raised],TODAY()-[Date Raised]))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.