## Cover
EBRORA
ebrora.com
Variation Order Register
Track, manage and report on all contract variations from
identification through to approval and final account reconciliation.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Variation Order Register' sheet. The top section contains a live dashboard summarising your variation orders by status, value and variance.
2. | Scroll down to the register table (starting at row 9). Each row represents one variation order (VO). Enter data in the light teal cells.
3. | Start with the VO Ref — use your project's numbering convention (e.g. VO-001). Enter the date raised, a clear description, who raised it, and the current status.
4. | Enter the Estimated Value (£) when the VO is first identified. Once the client or PM approves or adjusts the value, enter the Approved Value (£).
5. | Use the Status dropdown to track each VO through its lifecycle: Draft → Submitted → Under Review → Approved / Rejected → Implemented.
6. | The dashboard at the top updates automatically — use it in progress meetings and monthly commercial reports.
Optional Fields
7. | Click the [+] button above the right-hand columns to expand optional fields: Contract Clause, Subcontractor, Client Response Date, Days Outstanding, Programme Impact, and Variation Type.
8. | Days Outstanding calculates automatically from the date raised. It highlights red when a VO has been unresolved for more than 30 days.
Colour Key
Light teal cells (#E8F6F7) — User input. Enter your data here.
Dark navy headers — Do not edit. Column headers and dashboard labels.
Green — Status is 'Approved' or 'Implemented'.
Amber — Status is 'Under Review'.
Red — Status is 'Rejected', or Days Outstanding exceeds 30 days.
Blue — Status is 'Submitted'.
Grey — Status is 'Draft'.
Tips
Tip 1: | Review the register weekly in your commercial meeting. Filter by Status = 'Submitted' or 'Under Review' to chase outstanding items.
Tip 2: | Always log a VO the moment it's identified, even as 'Draft' with an estimated value of £0. Early logging prevents items falling through the cracks.
Tip 3: | Use the Variation Type optional field (Addition / Omission / Substitution) to quickly filter and report the nature of changes at final account stage.

## Variation Order Register
VARIATION ORDER REGISTER — DASHBOARD
Total VOs |  | Total Estimated (£) |  | Total Approved (£) |  | Variance (£)
5 |  | 42500 |  | 25300 |  | -17200
Draft |  | Submitted |  | Under Review |  | Approved |  | Rejected |  | Implemented
1 |  | 1 |  | 1 |  | 2 |  | 0 |  | 0
▸ Optional Fields — Click [+] to expand
VO Ref | Date Raised | Description | Raised By | Status | Estimated Value (£) | Approved Value (£) | Notes | Contract Clause | Subcontractor | Client Response Date | Days Outstanding | Programme Impact | Variation Type
VO-001 | 2025-09-15 | Additional piling to east retaining wall due to unforeseen ground conditions | Site Manager | Approved | 45000 | 42500 | Ground investigation confirmed soft spots | Cl 60.1 | Murphy Ground Engineering | 2025-10-02 | 17 | Yes | Addition
VO-002 | 2025-10-03 | Omission of timber cladding to Block C — replaced with render system | Client PM | Approved | -18000 | -17200 | Client instruction CI-034 | Cl 14.3 | Wates Interiors | 2025-10-10 | 7 | No | Substitution
VO-003 | 2025-11-12 | Extended prelims due to 3-week weather delay (Storm Éowyn) | Contracts Manager | Under Review | 32000 | 0 | Awaiting QS assessment | Cl 60.1 |  |  | 130 | Yes | Addition
VO-004 | 2025-12-01 | Additional fire stopping to risers — Building Control requirement | Design Manager | Submitted | 8500 | 0 | Design change notice DCN-017 issued | Cl 61.1 | Kier Fire Protection |  | 111 | No | Addition
VO-005 | 2026-01-20 | Omission of landscaping Phase 2 — deferred to separate contract | Client PM | Draft | -25000 | 0 | Pending formal instruction |  |  |  | 61 | No | Omission
Formulas:
Days Outstanding = IF(AND([Date Raised]<>"",OR([Total Approved (£)]="Draft",[Total Approved (£)]="Submitted",[Total Approved (£)]="Under Review")),TODAY()-[Date Raised],IF(AND([Date Raised]<>"",[Implemented]<>""),[Implemented]-[Date Raised],""))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.