## Cover
EBRORA
ebrora.com
Contract Correspondence Log
Log all formal contract correspondence with two-way
direction tracking, response monitoring, and overdue alerts.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Correspondence Log' sheet. The top section has two summary panels: a Direction Summary (left) showing sent vs received counts and a Response Monitor (right) tracking outstanding and overdue responses.
2. | Each row represents one piece of formal correspondence. Enter the Ref, Date, Direction (Sent/Received), From, To, Subject, Type, and whether a Response is Required.
3. | If a response is required, enter the Response Deadline. The Days to Deadline column calculates automatically. When the response arrives, enter the Response Received Date and the Response Ref to link the chain.
4. | Use the Type dropdown to categorise: Letter, Email, Notice, Instruction, Certificate, Claim, or Other. This enables filtering for specific correspondence categories.
5. | The Response Status column auto-calculates: shows 'Responded' (green) if a response date exists, 'Overdue' (red) if the deadline has passed, 'Pending' (amber) if awaiting response, or blank if no response required.
Optional Fields
6. | Click [+] to expand optional fields: Contract Clause, Confidential flag, Hard Copy Location, Linked RFI/CE/VO Ref, Filed By, and File/Folder Ref.
7. | The Linked Ref field lets you cross-reference correspondence to your RFI Log, CE Register, or Variation Order Register.
Colour Key
Light teal cells (#E8F6F7) — User input.
Dark navy headers — Do not edit.
Light blue Direction — Sent (outgoing correspondence).
Light green Direction — Received (incoming correspondence).
Green Response Status — Responded (response received on time).
Amber Response Status — Pending (response required, deadline not yet passed).
Red Response Status — Overdue (deadline passed, no response received).
Tips
Tip 1: | Log every piece of formal correspondence the same day it is sent or received. Gaps in the correspondence record are a common weakness in dispute proceedings.
Tip 2: | Use the filter on Direction = 'Received' and Response Required = 'Yes' to generate a weekly action list of items requiring your response.
Tip 3: | For NEC contracts, formal notices and communications are time-bound. Use this log alongside the CE and EW registers to evidence that all notifications were issued within contractual timescales.

## Correspondence Log
CONTRACT CORRESPONDENCE LOG
DIRECTION SUMMARY | [5 empty] | RESPONSE MONITOR
Total Correspondence |  |  | 5 |  |  | Responses Required |  |  | 4
Sent (→ Outgoing) |  |  | 3 |  |  | Responded |  |  | 3
Received (← Incoming) |  |  | 2 |  |  | Pending (in time) |  |  | 0
[6 empty] | Overdue |  |  | 1
▸ Optional Fields — Click [+] to expand
Ref | Date | Direction | From | To | Subject | Type | Response Required | Response Deadline | Response Status | Notes | Response Received | Response Ref | Contract Clause | Confidential | Linked RFI/CE/VO | Filed By
CC-001 | 2025-07-10 | Sent | Kier Construction (PM) | Riverside Developments (Employer) | Early Warning Notice — potential ground condition risk Zone A | Notice | Yes | 2025-07-24 | Responded | EW-001 raised same date | 2025-07-18 | CC-004 | Cl 15.1 | No | EW-001 | J Williams
CC-002 | 2025-07-15 | Received | Riverside Developments (Employer) | Kier Construction (PM) | Client Instruction CI-034: Change cladding system to Block C | Instruction | Yes | 2025-07-29 | Responded | Triggers VO-002 | 2025-07-25 | CC-005 | Cl 14.3 | No | VO-002 | S Patel
CC-003 | 2025-08-05 | Sent | Kier Construction (PM) | Capita (Designer) | RFI-003: Drainage invert level conflict between civil and structural drawings | Letter | Yes | 2025-08-19 | Responded | Formal follow-up to verbal RFI | 2025-08-22 | CC-008 |  | No | RFI-003 | J Williams
CC-004 | 2025-07-18 | Received | Riverside Developments (Employer) | Kier Construction (PM) | Acknowledgement of EW-001 — PM agrees matter to be discussed at RRM | Letter | No |  |  | Response to CC-001 |  |  | Cl 15.1 | No | EW-001 | S Patel
CC-005 | 2025-09-28 | Sent | Kier Construction (PM) | Riverside Developments (Employer) | CE Notification — Building Control fire stopping requirement (CE-003) | Notice | Yes | 2025-10-12 | Overdue | Formal Cl 61.3 notification |  |  | Cl 61.3 | No | CE-003 | J Williams
Formulas:
Response Status = IF([Response Required]<>"Yes","",IF([Response Received]<>"","Responded",IF(AND([Response Deadline]<>"",[Response Deadline]<TODAY()),"Overdue",IF([Response Deadline]<>"","Pending",""))))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.