## Cover
EBRORA
ebrora.com
Drawing Register
Track every IFC drawing, revision and approval status across all disciplines — from first issue to as-built.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2025 — All rights reserved

## Instructions
How to Use This Template — Drawing Register
Step-by-Step Instructions
1. | Go to the 'Drawing Register' sheet. Enter your Project Name and Contract Number in the fields at the top.
2. | For each drawing, type the Drawing Number in column B. Column A auto-generates a sequential reference (DWG-001, DWG-002, etc.).
3. | Select the Revision from the dropdown in column C. Update this each time a new revision is issued — never overwrite old revisions, add a new row.
4. | Use the Discipline dropdown (column E) to assign the drawing to the correct engineering discipline.
5. | Use the Status dropdown (column F) to set the current state. Row highlighting updates automatically.
6. | Enter the issue date in column G. Record the name or initials of the issuing engineer in column H.
7. | If this drawing supersedes a previous revision, enter the old ref and revision in column I for traceability.
8. | Use column J for comments — e.g., 'Linked to NCR-045', 'Awaiting CDM coordinator approval', or special distribution notes.
9. | Click the [+] button above columns K–N to expand Optional Fields: P&ID cross-references, spec clauses, originator company, and file paths.
10. | Use the AutoFilter arrows on row 2 to filter or sort by discipline, status, revision, or date.
Colour Key
IFC — Issued for Construction. Fully approved, ready for build.
For Construction — Approved and released for construction use.
For Review — Out with client or engineer. Not yet approved for construction.
Superseded — This revision replaced by a newer issue. Row is greyed out.
Cancelled — Drawing formally withdrawn. Do not use.
Light teal cells — User input / editable fields.
Dark navy header rows — Do not edit.
Tips
* | Agree your drawing numbering convention with the designer before the first issue. Standard format: [Project Code]-[Discipline]-[Number] (e.g., WRC-CV-0001). Inconsistent numbering creates problems for ISO 19650 compliance and the H&S file.
* | Never delete a superseded row. Change the Status to 'Superseded' and record the superseding drawing number in the Notes column. This preserves your full audit trail.
* | At the start of each week, filter Status = 'For Review' to see which drawings need chasing. Under NEC4, the contract sets a response period — typically 14 calendar days — so track it.

## Drawing Register
Project Name: |  |  | [Enter Project Name] |  |  | Contract No: |  | [Contract No] |  | ▸ Optional Fields — Click [+] to expand
Ref | Drawing No. | Revision | Title | Discipline | Status | Date Issued | Issued By | Supersedes | Notes | P&ID / Drawing Ref | Related Spec Clause | Originator Company | File Path / Link
DWG-001 | WRC-CV-0001 | C | Site Access Road & Haul Route — General Arrangement | Civil | IFC | 2025-01-15 | J. Hargreaves | WRC-CV-0001 Rev B | Approved. Phase 1 haul route only — see drawing notes. |  | CESWI 6th Ed. | Hargreaves Consulting | //server/drawings/WRC-CV-0001-C.pdf
DWG-002 | WRC-ST-0003 | B | Primary Sedimentation Tank — Reinforcement Details | Structural | For Construction | 2025-02-03 | S. Patel | WRC-ST-0003 Rev A | 2nd pour rebar details added Rev B. Confirmed by SE. |  | BS 8500 | Structural Partners Ltd | //server/drawings/WRC-ST-0003-B.pdf
DWG-003 | WRC-ME-0012 | P02 | MHPP — Inlet Works General Arrangement | Mechanical | For Review | 2025-02-20 | T. Walsh |  | Awaiting client comment period close 07/03/25. | P&ID-IN-001 | DD ENV 1991 | Walsh MEP Ltd
DWG-004 | WRC-EL-0005 | A | MCC-01 Panel Schedule & Wiring Diagram | Electrical | Superseded | 2024-11-10 | C. Roberts | WRC-EL-0005 Rev - | Superseded Rev B — supply voltage uprated to 415V. |  | BS 7671:2018 | Roberts Electrical | //server/drawings/WRC-EL-0005-A-OLD.pdf
DWG-005 | WRC-IN-0002 | P01 | P&ID — Inlet Screening & Grit Removal | Instrumentation | For Review | 2025-03-01 | A. Nkosi |  | First issue — process team review in progress. | SCADA-IDF-001 | ISO 10628 | InControl Systems Ltd
TOTAL DRAWINGS | 5 | IFC | 1 | FOR CONSTRUCTION | 1 | FOR REVIEW | 2 | SUPERSEDED | 1 | CANCELLED | 0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.