## Cover
EBRORA
ebrora.com
Change Control Log
(NEC Early Warnings & CEs)
Track early warnings and compensation events
with time/cost impact assessment and NEC compliance tracking.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Change Control Log' sheet. Each row tracks one Early Warning (EW) or Compensation Event (CE) under NEC.
2. | Enter the Ref (e.g., EW-001 or CE-001), select the Type (Early Warning or Compensation Event), and record the Date Raised.
3. | Describe the matter clearly — for EWs, describe the risk; for CEs, describe the event and its contractual basis.
4. | Link related EWs and CEs using the Linked EW/CE column. Most CEs should trace back to an Early Warning.
5. | Record the estimated Time Impact (delay in days) and Cost Impact (£). These feed the summary totals.
6. | Track the Status through the NEC workflow: Notified → Under Assessment → Quotation Submitted → Agreed → Implemented (or Withdrawn/Rejected).
7. | The Response Due Date helps track NEC time-bar compliance — EWs require a risk reduction meeting within 2 weeks; CE quotations within 3 weeks.
8. | Expand optional columns for PM Response details, quotation values, and assessment/implementation dates.
Colour Key
Light teal cells = User input / editable
Dark navy headers = Do not edit
Green = Agreed or Implemented
Amber = Under Assessment or Quotation Submitted
Red = Rejected, Withdrawn, or overdue (past Response Due Date without resolution)
Tips
Tip 1: | Under NEC, early warnings are not optional — Clause 15.1 requires notification 'as soon as' you become aware. Log them immediately.
Tip 2: | Always link CEs back to their originating EW. Unlinked CEs suggest the early warning process isn't being followed.
Tip 3: | Track the Response Due Date religiously. NEC time-bars are enforced — a missed deadline can mean a lost entitlement.

## Change Control Log
Ref | Type | Date Raised | Description | Raised By | Risk Register Ref | Linked EW/CE | Time Impact (days) | Cost Impact (£) | Status | Response Due Date | Notes | PM Response | Quotation Submitted | Quotation Value (£) | Assessment Date | Implemented Date
EW-001 | Early Warning | 2026-01-23 | Risk of delay to storm tank construction due to prolonged wet weather forecast. Ground conditions deteriorating — may need additional temporary works. | J. Davies | RR-015 | CE-001 | 15 | 0 | Implemented | 2026-02-06 | Risk reduction meeting held. Temp works approved. | Additional temp works instructed under CE-001 |  |  | 2026-02-02 | 2026-02-12
EW-002 | Early Warning | 2026-02-07 | Potential clash between new MCC cable routes and existing live services identified during survey. May require re-routing. | S. Patel | RR-022 |  | 5 | 0 | Under Assessment | 2026-02-21 | GPR survey commissioned to confirm | Awaiting GPR results
CE-001 | Compensation Event | 2026-02-02 | Additional temporary works to storm tank excavation due to unforeseen ground conditions (Clause 60.1(12)). Linked to EW-001. | J. Davies |  | EW-001 | 15 | 47500 | Agreed | 2026-02-23 | Quotation accepted at PM assessment | PM accepted quotation as submitted | Yes | 47500 | 2026-02-27 | 2026-03-04
CE-002 | Compensation Event | 2026-02-22 | Late provision of IFC drawings for RAS pump station structural slab (Clause 60.1(5)). 10 working days late. | M. Thompson |  |  | 8 | 12000 | Quotation Submitted | 2026-03-15 | PM reviewing quotation |  |  | Yes | 1932-11-07
EW-003 | Early Warning | 2026-03-14 | Supplier has notified 6-week delay on SCADA panel delivery. May impact wet commissioning programme. | R. Evans | RR-031 |  | 0 | 0 | Notified | 2026-03-28 | Risk reduction meeting scheduled for next week
SUMMARY | Total Items: | 5 | Early Warnings: | 3 | Comp Events: | 2 | Total Cost Impact: | 59500 | Total Time Impact: | 43 days

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.