## Cover
EBRORA
ebrora.com
Design Change Control Log
Track every proposed design change from origination through approval chain sign-off — with cost, time and programme impact captured at the point of change.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — Design Change Control Log
Step-by-Step Instructions
1. | Go to the 'Design Change Log' sheet. Enter the Project Name and Contract Number in the info strip at the top.
2. | Each change is automatically assigned a sequential reference (DCR-001, DCR-002, etc.) once a Description is entered in column C.
3. | Enter the Date Raised in column B and a clear, specific description of the proposed change in column C.
4. | Record who originated the change request in column D — this could be the Client, Designer, Contractor, Statutory Authority, or Site (field-generated change).
5. | Select the Change Type in column E: Design Change, Scope Addition, Scope Reduction, Value Engineering, Statutory Requirement, or Error Correction.
6. | Identify the Discipline affected in column F so changes can be filtered and tracked by engineering team.
7. | Record the Estimated Cost Impact in column G (+ for addition, - for reduction) and the Estimated Time Impact in calendar days in column H.
8. | Track the approval chain in columns I and J: Designer Review (column I) and Client Approval (column J). Both must be completed before the change is implemented.
9. | Set the overall Status in column K. A change must not be implemented on site until Status = Approved. Changes pending approval are amber; rejected changes are red.
10. | Use column L for notes — cross-reference the linked drawing revision, NEC compensation event number, or any conditions attached to approval. Expand Optional Columns M–P for CE links, cost breakdown and file references.
Colour Key
Approved — Change has been through the full approval chain and is cleared for implementation.
Under Review / Pending — Change is in the approval chain. Do not implement on site yet.
Rejected — Change has been reviewed and declined. Record the reason in Notes.
Withdrawn — Change request formally withdrawn by the originator.
Implemented — Change approved and incorporated into design/build. Drawings revised.
Light teal cells — User input / editable fields.
Dark navy header rows — Do not edit.
Tips
* | Never allow a design change to be implemented on site without a written approval trail. A verbal 'yes' from the designer or PM is not a change approval. Under NEC4, an uninstructed change can affect your entitlement to a compensation event.
* | Log the cost and time impact at the point of raising, even if only an estimate. This creates the baseline for the compensation event or variation claim. Estimates updated once the change is approved.
* | Link each approved design change to the relevant drawing revision. If a change triggers a drawing update, ensure the Drawing Register (Template 01) is also updated and the revised IFC drawing is re-issued before work restarts.

## Design Change Log
Project Name: |  | [Enter Project Name] |  |  |  | Contract No: |  | [Contract No] |  |  |  | ▸ Optional Fields — Click [+] to expand
DCR Ref | Date Raised | Change Description | Originated By | Change Type | Discipline | Cost Impact (£) | Time Impact (Days) | Designer Review | Client Approval | Status | Notes / CE Link | CE / EW Ref | Linked Drawing Rev | Cost Breakdown Ref | File Path / Link
DCR-001 | 2025-01-20 | Increase inlet screen channel width from 800mm to 1000mm to accommodate future flow upgrade. | Client | Scope Addition | Civil | 45000 | 14 | Approved | Approved | Approved | CE-012 raised. IFC drawings WRC-CV-0004 Rev C to be issued. Programme extended 14 days. | CE-012 | WRC-CV-0004 Rev C
DCR-002 | 2025-02-05 | Substitute specified ductile iron valves (PN16) with stainless steel equivalents — lead time saving. | Contractor | Value Engineering | Mechanical | -8500 | -7 | Approved | Approved | Approved | VE saving agreed. SS valves meet spec. NEC CE-015 agreed. Saving shared 50/50. | CE-015 | WRC-ME-0008 Rev B | VE-003 cost breakdown
DCR-003 | 2025-02-18 | Relocate kiosk from position K1 to K3 — clash with existing buried services (unknown at design stage). | Site / Field | Design Change | Electrical | 12000 | 5 | Approved | Pending | Pending | EW-019 raised. Structural check complete. Awaiting client confirmation of revised kiosk position. | EW-019 / CE pending | WRC-EL-0007 Rev -
DCR-004 | 2025-03-04 | Remove secondary clarifier overflow weir — Statutory requirement from EA consent variation. | Statutory Authority | Statutory Requirement | Process | 22000 | 10 | Approved | Pending | Under Review | EA consent variation ref EA-WRC-2025-007. Designer confirming weir removal feasibility. |  | WRC-PR-0003 Rev -
DCR-005 | 2025-03-10 | Proposal to omit acoustic fencing to Site Entrance — client rejected on planning grounds. | Contractor | Scope Reduction | Civil | -6000 | -3 | Rejected | Rejected | Rejected | Client rejected — planning condition requires acoustic screen. No change to scope.
TOTAL DCRs | 5 | APPROVED | 2 | PENDING | 1 | REJECTED | 1 | NET COST IMPACT (£) | 36500 | NET TIME IMPACT (DAYS) | 7

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.