## Cover
EBRORA
ebrora.com
Document Transmittal Register
Track document transmittals with recipient acknowledgement and response monitoring.
Log outgoing and incoming documents with purpose codes and delivery confirmation.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. | Open the 'Transmittal Register' sheet. The dashboard shows total transmittals, acknowledgement rate, and overdue responses.
2. | Log each document transmittal with a unique reference, date sent, recipient, and the documents included.
3. | Select the purpose from the dropdown: For Approval, For Information, For Construction, For Review, or As Requested.
4. | When the recipient acknowledges receipt, enter the date. Unacknowledged transmittals >7 days turn amber, >14 days turn red.
5. | For 'For Approval' transmittals, track the response: Approved, Approved with Comments, Rejected, or No Response.
6. | Expand optional columns for document revision, number of copies, delivery method, and follow-up notes.
7. | This register provides an audit trail of all formal document exchanges — essential for contractual correspondence records.
Colour Key
Light teal — user input
Dark navy — headers
Green — Acknowledged / Approved
Amber — Awaiting response (>7 days) / Approved with Comments
Red — Overdue (>14 days) / Rejected
Tips
• | Always send transmittals for formal document submissions — email alone is not a contractual record unless stated in the contract.
• | Number transmittals sequentially and maintain a single register. Don't let different team members keep separate logs.
• | For NEC contracts, use this alongside the Early Warning and Compensation Event registers for complete correspondence tracking.

## Transmittal Register
DOCUMENT TRANSMITTAL REGISTER
Transmittal Summary |  |  |  |  | Response Status (Approvals Only)
Total Sent: | 5 | Acknowledged: | 4 |  | Approved: | 2 | With Comments: | 1
Awaiting Ack: | 1 | Ack Rate: | 80% |  | Rejected: | 0
TRANSMITTAL LOG
Trans. Ref | Date Sent | To (Recipient) | From | Document Title / Description | Purpose | No. of Docs | Ack. Date | Response | Days to Ack | Revision | Delivery Method | Response Date | Notes
TR-001 | 2026-02-05 | Client Design Team | Main Contractor | Foundation design drawings RC-101 to RC-105 (Rev P03) | For Approval | 5 | 2026-02-07 | Approved | 2 | P03 | Email |  | 2026-02-12 | Approved without comment. Proceed to construction.
TR-002 | 2026-02-12 | Structural Engineer | Main Contractor | Concrete mix design submission — C35/45 and C10 blinding | For Approval | 2 | 2026-02-13 | Approved with Comments | 1 | Rev A | Document Portal |  | 2026-02-20 | Cement content query — clarified and approved.
TR-003 | 2026-02-20 | Client PM | Main Contractor | Monthly progress report — February 2026 | For Information | 1 | 2026-02-21 | N/A — For Info Only | 1 |  | Email
TR-004 | 2026-03-01 | Planning Supervisor | Main Contractor | Updated Construction Phase Plan (Rev 03) | For Review | 1 | 2026-03-03 | Approved | 2 | Rev 03 | Document Portal |  | 2026-03-10 | Minor comments incorporated. Rev 04 issued.
TR-005 | 2026-03-10 | Client Design Team | Main Contractor | Steelwork fabrication drawings S-301 to S-315 | For Approval | 15 |  | No Response | 13 | P01 | Email |  | Chased 17/03. Awaiting response.
Formulas:
Days to Ack = IF(AND([Date Sent]<>"",[Ack. Date]<>""),[Ack. Date]-[Date Sent],IF([Date Sent]<>"",TODAY()-[Date Sent],""))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.