## Cover
EBRORA
ebrora.com
RFI Log
Track all Requests for Information from submission to response,
with built-in response time monitoring and overdue alerts.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'RFI Log' sheet. The top band (rows 1–7) shows live KPIs: total RFIs, open count, overdue count, and average response time in days.
2. | Enter each new RFI on a fresh row in the register (starting row 10). Fill in the light teal cells — RFI Ref, Date Raised, Subject, Raised By, Addressed To, Priority, and Status.
3. | Set the Date Response Required — this is the contractual or agreed deadline for a response. The template will automatically flag overdue items.
4. | When a response is received, enter the Date Response Received. The Days to Respond column calculates automatically.
5. | Update the Status dropdown as the RFI progresses: Open → Responded → Closed. Mark as Void if withdrawn.
Optional Fields
6. | Click the [+] button above the right-hand columns to expand optional fields: Discipline, Drawing/Doc Ref, Response Summary, Impact on Programme, Impact on Cost, and Linked VO Ref.
7. | Use these for detailed tracking and cross-referencing with your variation order register.
Colour Key
Light teal cells (#E8F6F7) — User input. Enter your data here.
Dark navy headers — Do not edit. Column headers and KPI labels.
Green — Priority 'Low', or Status 'Closed'.
Amber — Priority 'Medium', or Status 'Responded' (awaiting close-out).
Red — Priority 'High', Status 'Overdue', or Date Response Required has passed with no response.
Blue — Status is 'Open' (awaiting response).
Tips
Tip 1: | Review the RFI Log weekly. Filter by Status = 'Open' and sort by Date Response Required to prioritise chasing.
Tip 2: | Always record the RFI even if you get a verbal response — log it, then follow up in writing. The log is your audit trail.
Tip 3: | Use the Linked VO Ref optional field to connect RFIs that result in variations. This makes final account reconciliation much easier.

## RFI Log
RFI LOG — PERFORMANCE TRACKER
Total RFIs |  | Open |  | Overdue |  | Avg Response (Days)
5 |  | 2 |  | 0 |  | 9
Open |  | Responded |  | Closed |  | Void
2 |  | 1 |  | 2 |  | 0
▸ Optional Fields — Click [+] to expand
RFI Ref | Date Raised | Subject | Raised By | Addressed To | Priority | Status | Notes | Discipline | Date Response Required | Date Response Received | Days to Respond | Drawing / Doc Ref | Linked VO Ref
RFI-001 | 2025-08-05 | Confirmation of structural steel connection detail at Grid J7-K8 | Site Engineer | Structural Designer | High | Closed | Response confirmed bolted connection per Rev P3 | Structural | 2025-08-12 | 2025-08-11 | 6 | SK-2045-Rev-P3
RFI-002 | 2025-09-18 | Clarification on finished floor level tolerance for raised access flooring | M&E Coordinator | Architect | Medium | Closed | ±5mm confirmed per spec clause 3.4.2 | Architectural | 2025-09-25 | 2025-09-27 | 9 | DRG-A-201
RFI-003 | 2025-11-02 | Drainage invert levels conflict between civil and structural drawings | Setting Out Engineer | Civil Designer | High | Responded | Revised levels issued — awaiting updated drawing | Civil | 2025-11-09 | 2025-11-14 | 12 | DRG-C-410 | VO-003
RFI-004 | 2025-12-10 | Specification for fire stopping material to service penetrations in risers | Fire Stopping Sub | Fire Engineer | High | Open | Chased 15/12, 22/12, 05/01 | Fire | 2025-12-17 |  |  | SPEC-FS-001 | VO-004
RFI-005 | 2026-01-08 | Confirmation of external paint colour RAL reference for cladding panels | Site Manager | Architect | Low | Open |  | Architectural | 2026-01-22 |  |  | DRG-A-305

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.