## Cover
EBRORA
ebrora.com
Submittal Register
Track design and material submittals through the full review cycle
from initial submission to final approval with revision control.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Submittal Register' sheet. The top band shows live counts: total submittals, how many are pending, under review, approved, and rejected or requiring resubmission.
2. | Each row represents one submittal package. Enter a unique Submittal Ref (e.g. SUB-001), the date submitted, a clear title, the discipline, the current revision letter, and the review status.
3. | Set the Date Required — this is the date by which a review response is needed to avoid programme impact. Overdue items are automatically flagged red.
4. | When the reviewer returns comments, update the Status dropdown and enter the Date Returned. The Review Duration column calculates automatically.
5. | If a submittal is rejected, create a new row for the resubmission with the next revision letter and link back using the same Submittal Ref prefix.
Optional Fields
6. | Click the [+] button to expand optional fields: Subcontractor, Reviewer, Date Returned, Review Duration, Spec Section, and Drawing/Doc Ref.
7. | The Spec Section field helps cross-reference submittals against contract specification clauses for QA audits.
Colour Key
Light teal cells (#E8F6F7) — User input. Enter your data here.
Dark navy headers — Do not edit. Column headers and KPI labels.
Green — Status is 'Approved'.
Light green — Status is 'Approved with Comments'.
Amber — Status is 'Under Review'.
Blue — Status is 'Pending' (not yet issued for review).
Red — Status is 'Rejected', or Date Required has passed without approval.
Purple — Status is 'Resubmit'.
Tips
Tip 1: | Issue submittals in batches by discipline and track them in your look-ahead programme. Late submittals are one of the most common causes of programme delay.
Tip 2: | Always log the revision letter. If a submittal is rejected and resubmitted, keep the original row and add a new row for the resubmission — this gives you a complete audit trail.
Tip 3: | Filter by Status = 'Under Review' and sort by Date Required to identify which responses need chasing this week.

## Submittal Register
SUBMITTAL REGISTER — REVIEW CYCLE TRACKER
Total Submittals |  | Awaiting Review |  | Approved (All) |  | Overdue Reviews
5 |  | 2 |  | 2 |  | 3
Pending |  | Under Review |  | Approved |  | Approved with Comments |  | Rejected |  | Resubmit
1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0
▸ Optional Fields — Click [+] to expand
Submittal Ref | Date Submitted | Title / Description | Discipline | Revision | Status | Date Required | Notes | Subcontractor | Reviewer | Date Returned | Review Duration (Days) | Spec Section | Drawing / Doc Ref
SUB-001 | 2025-07-14 | Structural steel shop drawings — Main frame Zones A-C | Structural | B | Approved | 2025-07-28 | Approved at Rev B after connection detail amendments | Severfield UK | Lead Structural Engineer | 2025-07-25 | 11 | S-3.2.1 | SK-STL-101 to 118
SUB-002 | 2025-08-03 | Curtain wall system product data and thermal calculations | Architectural | A | Approved with Comments | 2025-08-17 | Approved subject to updated U-value calcs for north elevation | Kawneer UK | Architect | 2025-08-19 | 16 | A-5.1.4 | DRG-CW-201
SUB-003 | 2025-09-22 | BMS controls wiring diagrams and point schedule | Electrical | P2 | Under Review | 2025-10-06 | Issued to M&E consultant 23/09 | Trend Controls | M&E Consultant |  |  | E-7.3.1 | DRG-EL-401
SUB-004 | 2025-10-10 | Fire damper product data and installation methodology | Fire | A | Rejected | 2025-10-24 | Rejected — product not on approved list. Resubmit with Ruskin alternative. | Swegon Ltd | Fire Engineer | 2025-10-22 | 12 | F-4.2.3 | SPEC-FD-001
SUB-005 | 2025-11-05 | Landscaping planting schedule and maintenance plan | Landscape | P1 | Pending | 2025-11-19 | Awaiting subcontractor submission |  |  |  |  | L-9.1.1 | DRG-LS-301

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.