## Cover
EBRORA
ebrora.com
Vendor Document Register
Index every vendor-supplied datasheet, O&M manual, FAT/SAT procedure and certificate — organised by supplier, with submission and approval status tracked.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — Vendor Document Register
Step-by-Step Instructions
1. | Go to the 'Vendor Document Register' sheet. Enter the Project Name and Contract Number in the info strip.
2. | The register is organised into supplier sections, each introduced by a teal section header. Add new rows within the relevant supplier section.
3. | Enter the Document Reference in column A — this should be the vendor's own document number, prefixed with the supplier code if helpful (e.g. WAL-OM-001).
4. | Enter the Document Title in column B. Be specific: include the equipment tag, system, and document type.
5. | Select the Document Type in column C from the dropdown: Datasheet, O&M Manual, FAT Procedure, SAT Procedure, GA Drawing, Wiring Diagram, Test Certificate, IOM, Spare Parts List, or Warranty Certificate.
6. | Enter the Supplier name in column D and the document Revision in column E.
7. | Set the Required By date in column F — when the document must be received to avoid impacting commissioning or handover.
8. | Update the Status in column G as documents are received and reviewed. The row colour updates automatically.
9. | Enter the Received Date (column H) and Approved Date (column I) as these milestones are reached.
10. | Section subtotals calculate approved/accepted counts and percentage completion per supplier. Use this to chase outstanding documents ahead of handover.
Colour Key
Approved / Received & Accepted — Document formally reviewed and accepted for the O&M file.
Under Review — Document received and being reviewed. Awaiting approval.
Submitted — Document received but review not yet started.
Outstanding — Document not yet received. Required By date may be at risk.
Superseded — Replaced by a later revision. Retained for audit record.
Light teal subtotal rows — Auto-calculated section completions.
Tips
* | Chase vendor documents at least 8 weeks before practical completion. O&M manuals in particular require review time — a 500-page manual cannot be reviewed the week before handover.
* | FAT and SAT procedures must be submitted and approved before the test takes place, not after. Approving a procedure post-FAT is meaningless and will be challenged during the handover audit.
* | Set up a transmittal system — every document submission should come with a transmittal record. Log the transmittal reference in column M so you have proof of when the document was formally received.

## Vendor Document Register
Project Name: |  | [Enter Project Name] |  |  |  | Contract No: |  | [Contract No]
VENDOR DOCUMENT REGISTER SUMMARY |  |  |  | TOTAL | -261 | APPROVED | 7 | OUTSTANDING | 3 | % COMPLETE | 46.67%
Doc Ref | Document Title | Document Type | Supplier | Rev | Required By | Status | Date Received | Date Approved | Reviewed By | Notes | File Ref / Path | Transmittal Ref | Tag / System Ref
Supplier 1 — Walsh MEP Ltd ¦ Pumps, Valves & Mechanical Equipment
WAL-DS-001 | Centrifugal Pump PST-01 — Product Datasheet | Datasheet | Walsh MEP Ltd | 2 | 2025-01-15 | Approved | 2025-01-10 | 2025-01-22 | T. Walsh | Approved Rev 2. Performance curve confirmed. | /docs/WAL-DS-001-Rev2.pdf | TR-001
WAL-OM-001 | Pump PST-01 / PST-02 — O&M Manual | O&M Manual | Walsh MEP Ltd | 1 | 2025-03-31 | Under Review | 2025-03-05 |  | T. Walsh | Rev 1 received 05/03. Review in progress — target approval 25/03. | /docs/WAL-OM-001-Rev1.pdf | TR-012
WAL-FAT-001 | Pump Station PST-01 — FAT Test Procedure | FAT Procedure | Walsh MEP Ltd | 1 | 2025-02-14 | Approved | 2025-02-05 | 2025-02-12 | T. Walsh | Approved. FAT conducted 18/02/25. Report WAL-FAT-RPT-001. | /docs/WAL-FAT-001-Rev1.pdf | TR-007
WAL-DS-002 | FCV-101 / FCV-201 — Flow Control Valve Datasheet | Datasheet | Walsh MEP Ltd | 1 | 2025-01-31 | Approved | 2025-01-28 | 2025-02-03 | T. Walsh |  |  | TR-003
WAL-SP-001 | PST-01 / PST-02 — Spare Parts List | Spare Parts List | Walsh MEP Ltd | 1 | 2025-04-30 | Outstanding |  |  |  | Required for O&M file. Chase with supplier.
Section totals — | [5 empty] | 3 | 5 | 60%
Supplier 2 — Roberts Electrical Ltd ¦ MCC, Switchgear & Electrical Equipment
ROB-DS-001 | MCC-01 Panel Schedule & General Arrangement | GA Drawing | Roberts Electrical | B | 2025-02-28 | Approved | 2025-02-20 | 2025-03-03 | C. Roberts | Rev B approved. Includes updated trip curves. | /docs/ROB-DS-001-RevB.pdf | TR-009
ROB-WD-001 | MCC-01 Wiring Diagram — Full Set | Wiring Diagram | Roberts Electrical | B | 2025-02-28 | Approved | 2025-02-20 | 2025-03-03 | C. Roberts |  |  | TR-009
ROB-OM-001 | MCC-01 — O&M Manual inc. Protection Settings | O&M Manual | Roberts Electrical | 1 | 2025-04-14 | Submitted | 2025-03-10 |  |  | Received 10/03. Review not yet started. | /docs/ROB-OM-001-Rev1.pdf | TR-015
ROB-CERT-001 | MCC-01 — Factory Test Certificate | Test Certificate | Roberts Electrical | 1 | 2025-02-28 | Received & Accepted | 2025-03-03 | 2025-03-05 | C. Roberts | Signed test cert from manufacturer. Filed. | /docs/ROB-CERT-001.pdf | TR-010
Section totals — | [5 empty] | 3 | 4 | 75%
Supplier 3 — InControl Systems Ltd ¦ SCADA, PLC & Instrumentation
ICS-SAT-001 | SCADA / PLC System — SAT Test Procedure | SAT Procedure | InControl Systems | 1 | 2025-04-30 | Outstanding |  |  |  | SAT procedure required 4 weeks before commissioning date.
ICS-OM-001 | SCADA System — O&M Manual | O&M Manual | InControl Systems | 0 | 2025-05-31 | Not Yet Required |  |  |  | Due with final software. Earliest issue May 2025.
ICS-DS-001 | Flow Transmitter FT-301 — Datasheet & Calibration Cert | Datasheet | InControl Systems | 1 | 2025-03-14 | Approved | 2025-03-08 | 2025-03-12 | A. Nkosi | HART calibration cert included. | /docs/ICS-DS-001.pdf | TR-014
Section totals — | [5 empty] | 1 | 3 | 33.33%

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.