## Cover
EBRORA
ebrora.com
Tree Protection Inspection Record
Record tree protection measures and track inspection results per BS 5837:2012.
Register retained trees and log recurring protection inspections with condition scoring.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. | Open the 'Tree Protection Record' sheet. It has two sections: a Tree Register (top) listing all retained trees, and an Inspection Log (below).
2. | Complete the Tree Register first. Enter each retained tree or group with its species, category (A/B/C per BS 5837), TPZ radius, and protection measures installed.
3. | In the Inspection Log below, record each site inspection. Select the tree ID, date, and score each protection aspect: Fencing, Ground Protection, Signage, and Root Zone.
4. | Score each aspect as Good, Fair, or Poor. The overall condition auto-calculates. Poor scores turn red for immediate attention.
5. | Record any damage observed and the corrective action taken in the notes columns.
6. | The summary dashboard counts inspections by condition and calculates your overall tree protection compliance rate.
7. | Share the inspection log with your arboriculturist at monthly site meetings.
Colour Key
Light teal — user input / editable
Dark navy — headers, do not edit
Green — Good condition / compliant
Amber — Fair (minor issues, monitor)
Red — Poor (immediate corrective action required)
Tips
• | Inspect tree protection weekly and after any plant movements near retained trees.
• | Never store materials, park plant, or route services through a Tree Protection Zone without arboricultural approval.
• | Any damage to a protected tree could be a criminal offence under a Tree Preservation Order — report immediately.

## Tree Protection Record
RETAINED TREE REGISTER
Tree ID | Species | Category | TPZ (m) | RPA (m²) | Protection Installed | TPO? | Location | Condition at Start | Arborist Notes
T-01 | English Oak (Quercus robur) | A | 7.2 | 163 | Heras fencing at TPZ + ground protection boards | Yes | NW boundary — Plot 1 | Good | Mature specimen, excellent form. Crown spread 12m.
T-02 | Silver Birch (Betula pendula) | B | 4.8 | 72 | Heras fencing at TPZ | No | Eastern boundary — Plot 5 | Good | Multi-stem, some deadwood in crown — retain.
T-03 | Beech (Fagus sylvatica) | A | 8.5 | 227 | Heras fencing + root protection cellular system | Yes | Central avenue — retained feature | Good | TPO protected. No-dig zone for all services.
T-04 | Scots Pine (Pinus sylvestris) | B | 5.2 | 85 | Heras fencing at TPZ | No | Southern boundary — near compound | Fair | Some lower limb damage from previous works.
T-05 | Field Maple (Acer campestre) | C | 3 | 28 | Heras fencing at TPZ | No | Haul road verge — ch. 0+080 | Fair | Small specimen. Fencing minimum distance.
G-01 | Mixed hedgerow (group) | B | 3 |  | Heras fencing full length + root barrier | No | Eastern boundary hedge — 85m length | Good | Important Hedgerow. 5m buffer maintained.
TREE PROTECTION INSPECTION LOG
Inspection Summary |  |  | Total: | 8 | Good: | 5 | Fair: | 2 | Poor: | 1
Tree ID | Date | Inspector | Fencing | Ground Prot. | Signage | Root Zone | Overall | Damage Observed | Action Taken | Next Review
T-01 | 2026-03-02 | M. Okafor | Good | Good | Good | Good | Good | None |  | 2026-03-09
T-02 | 2026-03-02 | M. Okafor | Good | N/A | Good | Good | Good | None |  | 2026-03-09
T-03 | 2026-03-02 | M. Okafor | Good | Good | Good | Good | Good | None |  | 2026-03-09
T-04 | 2026-03-02 | M. Okafor | Fair | N/A | Good | Fair | Fair | Fence panel leaning — post loose | Post re-driven and braced | 2026-03-09
T-01 | 2026-03-09 | J. Barton | Good | Good | Good | Good | Good | None |  | 2026-03-16
T-03 | 2026-03-09 | J. Barton | Good | Good | Fair | Good | Fair | Warning sign missing from east side | Replacement sign ordered and installed 10/03 | 2026-03-16
T-04 | 2026-03-09 | J. Barton | Good | N/A | Good | Poor | Poor | Excavator tracked through edge of TPZ | Area hand-dug to check roots. No damage. Additional barrier installed. | 2026-03-16
G-01 | 2026-03-09 | J. Barton | Good | N/A | Good | Good | Good | None |  | 2026-03-16

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.